## 📖 README
플랜트구매품질팀 통합관리 대시보드 - Excel 입력 양식
사용 방법
1. 아래 시트탭의 각 시트(프로젝트_현황 / 프로젝트_구매품질 실적 / 프로젝트_NCR처리현황 / PQAN / TPA_목록 / TPA_집행현황 / TPA_월별대금청구현황 / 인력운영_현황 / 인력운영_세부내역 / 출장현황 / 주요현안)에 데이터를 입력합니다.
2. 1행의 컬럼명(헤더)은 절대 변경하지 마세요. 시트명도 그대로 유지해야 합니다.
3. 데이터는 2행부터 입력합니다. 컬럼 순서는 자유롭게 변경해도 됩니다.
4. 작성이 끝나면 이 파일을 저장하고, 대시보드 HTML을 열어 'Excel 업로드' 버튼으로 불러옵니다.
5. 모든 KPI · 표 · 차트 · 조직도 · PQAN · TPA가 자동으로 채워집니다.
주요 입력 규칙
• 프로젝트_구매품질 실적 시트: 단계 컬럼(MR/TBE/PO/PIM/IRC)에 '완료'를 입력하면 100%로 처리됩니다.
• TPA_집행현황 시트: 금액은 USD 또는 KRW 중 한쪽만 입력해도 환율로 자동 환산됩니다 (USD 단위, 백만 단위 아님).
• 단계 컬럼: 'Active', 'Mechanical Completion', 'Bid' 중 하나로 입력해주세요.
• Mechanical Completion 상태 프로젝트는 TPA Warning 로직에서 자동 제외됩니다.
• 프로젝트_현황 시트의 계약가는 백만 단위 (USD M / KRW M)로 입력합니다.
• 날짜 필드(Issue Date / Due Date / Closed Date, 출발일, 복귀일, PQAN 배포일자 등)는 Excel 날짜 형식 또는 YYYY-MM-DD로 입력해주세요.
신규 시트 입력 가이드
• 프로젝트_NCR처리현황 시트: Main Vendor / Sub Vendor / 공종 / Issued by 포함 flat 컬럼. 작업공종·근본원인·처리분류는 대·중·(소)분류 분리 입력 후 HPMS 계층으로 자동 변환됩니다. Action Status 컬럼은 대시보드 확장 행에서 직접 입력 후 Excel 재다운로드 시 자동 저장됩니다.
• PQAN 시트: 동일 PQAN No. 중복 입력 허용 (이미지/내용을 여러 행으로 분리). 대시보드는 자동으로 통합 표시합니다.
- 이미지 URL (Teams) 컬럼은 Teams 채널 메시지의 공유 링크를 그대로 입력합니다. 화면에는 직접 노출되지 않고 hover/click 팝오버로 표시됩니다.
• TPA_목록 시트: 등록평가 · 정기평가 점수는 100점 만점 기준 숫자(예: 71, 93.3) 또는 텍스트(N/A 등)로 입력합니다.
• TPA_집행현황 시트: 기존 TPA 시트 데이터를 그대로 사용합니다. 단계 컬럼은 프로젝트_현황과 동일 규칙.
• TPA_월별대금청구현황 시트: 청구연월은 YYYY-MM 형식, 단위는 USD 또는 KRW 입력 (대시보드 환율로 USD 환산).
• 인력운영_현황 시트: 직급(예: G3, M2)을 추가 입력하면 조직도/표에 그대로 표시됩니다.
• 인력운영_세부내역 시트: PO 단위 담당자/IRC 진행률을 입력합니다 (담당자(정), 담당자(부)).
• 출장현황 시트: 출장목적(FAT / PIM / Monitoring / 공장검사 / 업체실사 / 업체감사 / 교육 / 현안미팅)에 따라 색상이 자동 적용됩니다.
TPA Warning 기준 (참고)
• 예산 대비 집행 70% 초과 → '1차 청산추정 필요'
• 예산 대비 집행 90% 초과 → '2차 청산추정 및 예산외품의 검토 필요'
• 계약고 대비 집행 90% 초과 → '계약고 증액 필요'
단계별 가중치 (참고)
• MR 10% · TBE 10% · PO 10% · PIM 20% · IRC 100% 50%
• 가중 진척률 = (각 단계 진행률 × 가중치)의 합

## 프로젝트_현황
프로젝트 | HDEC 계약고 (USD) | 전체 계약고 (USD) | HDEC 계약고 (KRW) | 전체 계약고 (KRW) | 발주처 | 국가 | PD | PQCM | 단계 | 공정률 | 비고
MIP6 | 1484 | 1484 |  |  | Aramco | Saudi Arabia | - | - | Mechanical Completion | 100%
SM12 | 1318 | 1354 |  |  | Aramco | Saudi Arabia | 정준택 상무 | 장동철 책임 | Active | 99.96%
IBRU | 1814 | 3778 |  |  | BOC | Iraq | 정태수 소장 | - | Mechanical Completion | 100%
SHN1 |  |  | 2389100 | 5436800 | S-Oil | Korea | 이현영 실장 | 이해석 책임 | Active | 95.69%
ALOM | 584 | 730 |  |  | Hyenco | Algeria | 정민권 소장 | 윤희수 책임 | Active | 58.96%
VEQU | 952 | 1178 |  |  | EVN | Vietnam | 이윤석 소장 | 윤희수 책임 | Active | 98.95%
STA4 | 2136 | 2136 |  |  | satorp | Saudi Arabia | 임영빈 상무 | 최우석 책임 | Active | 87.28%
SAC2 | 1184 | 2369 |  |  | Aramco | Saudi Arabia | 김형철 실장 | 최종현 책임 | Active | 70.49%
CSSP | 3160 | 3160 |  |  | TotalEnergies | Iraq | 박수철 상무 | 정진우 책임 | Active | 6.3%
PNG1 | 1600 | 4000 |  |  | ExxonMobil | Papua New Genea | 최성식 팀장 | 강태준 책임 | Active | 0%
ALSM | 5800 | 5800 |  |  | HPLS | USA | 백철욱 상무 | 강태준 책임 | Bid | 0%

## 프로젝트_구매품질 실적
프로젝트 | MR_Total | MR_Done | TBE_Total | TBE_Done | PO_Total | PO_Done | PIM_Total | PIM_Done | IRC_100%_Total | IRC_100%_Done | NCR_Total | NCR_Done
MIP6 | 완료 | 완료 | 완료 | 완료 | 200 | 200 | 197 | 197 | 397 | 397 | 55 | 55
SM12 | 완료 | 완료 | 완료 | 완료 | 150 | 150 | 167 | 167 | 351 | 346 | 74 | 74
IBRU | 완료 | 완료 | 완료 | 완료 | 124 | 124 | 45 | 45 | 124 | 124 | 7 | 7
SHN1 | 완료 | 완료 | 완료 | 완료 | 24 | 24 | 17 | 17 | 40 | 29 | 15 | 15
ALOM | 완료 | 완료 | 완료 | 완료 | 74 | 74 | 28 | 28 | 74 | 52 | 16 | 16
VEQU | 완료 | 완료 | 완료 | 완료 | 96 | 96 | 37 | 37 | 96 | 95 | 9 | 9
STA4 | 완료 | 완료 | 완료 | 완료 | 159 | 159 | 99 | 97 | 122 | 54 | 51 | 42
SAC2 | 완료 | 완료 | 완료 | 완료 | 93 | 93 | 62 | 59 | 89 | 21 | 7 | 7
CSSP | 148 | 68 | 148 | 2 | 148 | 1 | 57 | 0 | 148 | 0 | 0 | 0
PNG1 | 30 | 10 | 30 | 5 | 30 | 2 | 17 | 0 | 30 | 0 | 0 | 0
ALSM | 미정 | 미정 | 미정 | 미정 | 미정 | 미정 | 미정 | 미정 | 미정 | 미정 | 미정 | 미정

## 프로젝트_NCR처리현황
작업공종 대공종 | 작업공종 중공종 | 작업공종 소공종 | 근본원인 대분류 | 근본원인 중분류 | 처리분류 | 프로젝트 | Issued by | NCR No. | PO No. | 공종 | 품목 | Main Vendor | Sub Vendor | Issue Date | Due Date | Closed Date | NCR Description | Action Status
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 현상태사용 | MIP6 | 현대건설 | NCR-OOK-MS019-001 | MS019 | MS | Dehydrator & Desalter_HIC Plate | Cameron | Voestalpine | 2020-02-13 | 2020-04-10 | 2020-04-03 | Specimens of plate 184477 produced from heat no° 721340 didn´t pass succesfully HIC test. Mesured CTR mean value = 5,86% ≥ max. CTR allowed 3%
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 폐기 | MIP6 | 현대건설 | NCR-OOK-MS020-001 | MS020 | MS | Water Oil Separator_HIC Plate | NAMEL | Voestalpine | 2020-03-09 | 2020-05-30 | 2020-03-23 | One plate width is not suitable to ordered plate width. It was found during mill's internal monitoring.
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 폐기 | MIP6 | 현대건설 | NCR-OOK-MS021-001 | MS021 | MS | LPPT_HIC Plate | TSM | Voestalpine | 2020-03-20 | 2020-05-31 | 2020-07-03 | Specimens of plate 187759 produced from heat no° 916271 didn´t pass succesfully HIC test. Mesured CLR mean value = 11,67% ≥ max. CLR allowed 10%
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 폐기 | MIP6 | 현대건설 | NCR-OOK-MS019-002 | MS019 | MS | Dehydrator & Desalter_HIC Plate | Cameron | Voestalpine | 2020-04-16 | 2020-06-30 | 2020-06-26 | Specimens of plate 195575 produced from heat no° 722639 does not meet requirements max. HIC figures. Mesured CT value exceed max. CTR allowed (3%)
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 폐기 | MIP6 | 현대건설 | NCR-OOK-MS021-002 | MS021 | MS | LPPT_HIC Plate | TSM | Voestalpine | 2020-05-07 | 2020-08-31 | 2020-07-03 | Applicable 01-SAMMS-016 (Jan 2018) requires following: Stepwise cracking in which the calculated average CLR of any of the specimen exceed 10%, and/or CTR of any of the specimens exceeds 3%, is not acceptable. The plate that failed the test, rejected.
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 폐기 | MIP6 | 현대건설 | NCR-OOK-MS021-003 | MS021 | MS | LPPT_HIC Plate | TSM | Voestalpine | 2020-05-07 | 2020-08-31 | 2020-07-03 | Applicable 01-SAMMS-016 (Jan 2018) requires following: Stepwise cracking in which the calculated average CLR exceed 10% average from 3 specimens, and/or CTR exceeds 3% average from 3 specimens, is not acceptable. The plate that failed the test, rejected.
전기 | 급.배전설비 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 수리 | MIP6 | 현대건설 | NCR-OOK-EL001-001 | EL001 | EL | 230KV GIS | ABB Switzerland | - | 2020-09-09 | 2020-11-20 | 2020-11-04 | The power frequency withstand voltage test of circuit breaker phase 1HC300153594 in close position at 460Kv (ITP step C1-9) was failed immediately after reaching 460kV. Hitachi-ABB to investigate, propose a corrective action and notify for a new test after correction.
기계.설비 | 기타 | 손상 | 자재 | 품목의 결함, 손상 및 제작불량 | 폐기 | MIP6 | 현대건설 | NCR-OOK-PI001-001 | PI001 | PI | CS SMLS PIPE | TPCO | - | 2020-09-17 | 2020-10-23 | 2020-10-15 | During Visual Inspection of normalized pipes furnished to Ident. Code I164201658 on 02~03-Sep-2020, TPI Inspector found Heat 609124 and Hdea 609125 pipes had different-depth dents in the body. As ASTM A106 doesn't specify definite acceptance criteria on dents, TPI inspector cited API5L relevant requirements as the acceptance limits. After measuring the flat-bottom dent depth, TPI inspector confirmed that two Heat 609124 pipes and two Heat 609125 pipes had severe dents exceeding 6.4mm. The four defective pipes were already rejected. Even so, it is not permitted that each pipe body had acceptable-depth dents.
기계.설비 | 일반기계_고정.회전 | 기타 | 자재 | 서류의 결함, 미비 | 재작업 | MIP6 | 현대건설 | NCR-OOK-MS020-002 | MS020 | MS | Water Oil Separator PKG | NOVEL ARABIA MIDDLE EAST LTD | - | 2021-02-22 | 2021-04-30 | 2021-04-22 | Receiving inspection below nonconformities on BOM Item # 222 (Nozzle N9A/B) Nozzle Pipe 10" Sch 80 SA 106 Gr.B Pipe (MTC#590004595-10 Rev.1)
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 폐기 | MIP6 | 현대건설 | NCR-OOK-MS020-003 | MS020 | MS | Water Oil Separator PKG | NOVEL ARABIA MIDDLE EAST LTD | - | 2021-02-22 | 2021-08-30 | 2021-07-06 | Receiving inspection observed below nozzles lengths discrepancy from approved drawing VD-MS020-004 Rev.0
기계.설비 | 일반기계_고정.회전 | 기타 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 현상태사용 | MIP6 | 현대건설 | NCR-OOK-MS013-001 | MS013 | MS | N2 Generation PKG | HADETEC | TANKBOUW | 2021-03-29 | 2021-04-30 | 2021-04-22 | The 2" Nozzle welds on the pre-filter were performed using SMAW. This is not as per the approved WPS/PQR. It should be welded with GTAW at this is the only option as per weld map.
기계.설비 | 일반기계_고정.회전 | 누수 | 자재 | 품목의 결함, 손상 및 제작불량 | 수리 | MIP6 | 현대건설 | NCR-OOK-MR026-001 | MR026 | MR | Water Injection Pump | TRILLIUM PUMPS ITALY SRL | - | 2021-04-08 | 2022-04-06 | 2021-10-22 | An Heavy Leakage around the Mechanical Seal Area of Drive End was detected during Performace Test close to the completion. Trillum decide to stop the pump in order to investigate the matter and avoiding damages on internal parts. Trillium together with John Crane (seal supplier) will investigate about the causes of the failure, and inform accordingly. Some pictures separately attached.
기계.설비 | 기타 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 폐기 | MIP6 | 현대건설 | NCR-OOK-PI002-2-001 | PI002-2 | PI | HIC Plate of CS Welded Pipe | Hyundai Steel | Hyundai Steel (Dangjin) | 2021-04-15 | 2022-01-15 | 2021-10-22 | Reference Document : 01-SAMSS-043, 175-010210, NACE TM0284, VD-PI002-012-2 (ITP) and VD-PI002-013-2 (HIC Test Procedure) During the test evaluation of HIC testing specimens (Heat No. R84401, R84406, and R84409) in HYUNDAI Steel Dang-Jin Facility on 13th April 2021 under witness by COMPANY and Contractor inspectors. Contractor found that several test specimens which from Heat No. R84401 and R84406 have out of acceptance criteria (CLR 10%, CTR 3%) as attachment #1, below table shows an information summarized of test result of failed specimens. Result : Heat No. R84401 & R84406 are rejected, Vendor shall investigate what is reasone of the failure and submit the detail RCA (Root Cause Analysis) report by 23rd April 2020.
기계.설비 | 일반기계_고정.회전 | 기타 | 자재 | 식별, 추적관리 미흡 | 현상태사용 | MIP6 | 현대건설 | NCR-OOK-MR026-002 | MR026 | MR | Water Injection Pump_Lubrication | Trillium Pumps | ENPRO | 2021-05-24 | 2021-10-20 | 2021-08-12 | Air Fin Tubes supplied by Tube Fin Limited (TFL) FAZELEY, Tamworth having size 25mm Dia x 1.65mm thickness against ENPRO PO No. MKL 1-20-03209 pertaining to ENPRO WO 191218-A to E. During weld, visual inspection it is observed that there is no any material tracebility on Fin Tubes supplied as above. These Fin Tubes had been used to fabricate the Air Fin Coolers. Beaing as a requirement of material tracability on pressure part with respect to UG 10 (ASME Sect VIII Div1), Manufacturer (ENPRO) fail to meet this requirement, hence all coolers pertaining to this IL107000186641 not accepable. ENPRO to respond with in 48 Hrs.with respect to MOM Cl. No. 9.5 of PIM.
기계.설비 | 기타 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 현상태사용 | MIP6 | 현대건설 | NCR-OOK-PI009-001 | PI009 | PI | RTR Piping | Future Pipe Industry | - | 2021-06-01 | 2021-12-01 | 2021-11-26 | FPI manufactured RTR Pipes and Fittings with different ASTM codes application compared to BM description. During Final Inspection, it is observed that below items were applied different ASTM codes
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 폐기 | MIP6 | 현대건설 | NCR-OOK-MS001-001 | MS001 | MS | Vessel I_Dish Head | Al Zamil | Wuhan Linmei | 2021-08-30 | 2022-02-19 | 2021-08-31 2021-10-26 2021-11-12 | For Head No.Y210520-1 (Tag No.M96-D-0319 / Q’ty :1EA / SA516-70 HIC), non-conformance was found as following (Attachment#1–GAD): 1. Out of Tolerance for dinmension of Height - Required height : 583.4± per approved drawing LMWM-2020-2396-08/Rev.2. - Actual height : 592mm 2. Out of Tolerance for Plate thickness - Required minimum thickness is 9mm per approved drawing ZHI-ENG-SKT-2396-08_01/Rev.0 - Measured thickness at the location of the knuckle area : min. 8.61
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 수리 | MIP6 | 현대건설 | NCR-OOK-MR001-001 | MR001 | MR | Centrifugal Compressor | GESA | NUOVO PIGNONE | 2021-11-19 | 2022-02-18 | 2022-04-07 | [Issue #1] The first issue has been found during machining on DGS housing. As per below snapshot the circular shape red highlighted, has been executed out of center around 2 mm and ENG disposition is: repair by weld and machining to restore as per drawing. [Issue #2] In the same casing we found an additional issue, tracked in our system with M2136025: 4 threaded holes have been machined out of center
기계.설비 | 일반기계_고정.회전 | 미시공 | 자재 | 기타 | 재작업 | MIP6 | 현대건설 | NCR-OOK-MR026-003 | MR026 | MR | Water Injection Pump | TRILLIUM PUMPS ITALY SRL | - | 2021-11-19 | 2022-09-15 | 2022-09-16 | During the Final Inspection / Visual and Dimensional check(ITP step P_0036779 / 01 to 03), it was found that double language English was not applied to WARNING LABEL on junction box inside, only English language applied.
기계.설비 | 일반기계_고정.회전 | 누수 | 자재 | 취급관리 미흡, 취급 손상 | 재작업 | MIP6 | 현대건설 | NCR-OOK-MR024-001 | MR024 | MR | WIP(OWSF) | AES Arabia | - | 2022-03-03 | 2022-07-22 | 2022-03-24 | During the receiving inspection - 24 inch pneumatic actuated valve tag # M97-AOV-0448 found hydraulic oil leaked
기계.설비 | 일반기계_고정.회전 | 기타 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 재작업 | MIP6 | 현대건설 | NCR-OOK-MS001-002 | MS001 | MS | Vessel I | Al Zamil | - | 2022-05-16 | 2022-07-10 | 2022-06-27 | Violation of approved WPS was found that welding was performing without preheating on Vessel (Tag No.M96-D-0319 / Nozzle “N2”).
기계.설비 | 일반기계_고정.회전 | 손상 | 자재 | 품목의 결함, 손상 및 제작불량 | 현상태사용 | MIP6 | 현대건설 | NCR-OOK-MS020-004 | MS020 | MS | Water Oil Separator PKG | NOVEL ARABIA MIDDLE EAST LTD | - | 2022-06-14 | 2022-06-10 | 2022-07-20 | During shop surveillance inspection, surface deformation (refer to below photos) observed on the roller holding long seam welds (LS # 1B, 7B, 17B & 23B) and its opposite roller side also for the equipment tag # M95-D-0210.
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 수리 | MIP6 | 현대건설 | NCR-OOK-MR024-002 | MR024 | MR | OWSF(WIP)_Pump | AES Arabia | Flowserve Worthington s.r.l | 2022-07-21 | 2022-11-30 | 2022-09-26 | Flowserve Worthignton machined two unnecessary holes on drive end and non-drive end sides of casings of items, M97-G-0002B and M97-G-0002C. Holes diameter is ½” NPT for all 4 holes. Meanwhile, the holes are not drilled on Tag. M97-G-0002A and M97-G-0002D.
전기 | 급.배전설비 | 미시공 | 자재 | 기타 | 재작업 | MIP6 | 현대건설 | NCR-OOK-EL008-001 | EL008 | EL | LV SWGR/MCC, Cablebus (M97-101-SG-001) | WESCOSA | - | 2022-08-30 | 2023-02-17 | 2023-04-27 | 04 Ea. PT disconnect switches are missing in 480V, 3200A, 3PH, 60HZ, 85kA―C Low Voltage Switchgear (tag# M97-101-SG-001) This issue was highlighted in the punch list issued at the time of FAT. As per vendor, the missing material will be fixed at site. Due to urgency of the delivery, the SWGR tag# M97-101-SG-001 is agreed to be shipped without 04 Ea disconnect switches. This NCR is issued on the advice of Saudi Aramco in order to follow up hte closure of the comment in the attached punch list with regard to the 04Ea missing disconnect swiches. The NCR will be closed by HDEC once the 04Ea missing disconnect swiches will be fixed at site by WESCOSA.
기계.설비 | 일반기계_고정.회전 | 기타 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 재작업 | MIP6 | 현대건설 | NCR-OOK-MS021-1-002 | MS021-1 | MS | LPPT_M95-D-0200 | ZAMIL PROCESS EQUIPMENT CO. LTD. | - | 2022-09-28 | 2023-03-10 | 2023-01-18 | The blasting and painting activities of internal surface (primer) was completed on 28th June 2022. The concecutive coating for successive coating (intermediate layer) was not performed within prescribed duration. It is not fulfilling the maximum over coating period requirement of data sheet of Paint Hempadur 85671 & SAES-H-101V.
기계.설비 | 일반기계_고정.회전 | 기타 | 시험.검사 | 절차서, 지침서의 미준수 | 재작업 | MIP6 | 현대건설 | NCR-OOK-MR016-001 | MR016 | MR | Oily Water Treatment Package _API Three Way Flow Splitter and vessel M97-D-0112 A/B M97-D-0116 A/B | DS21 | ABJ | 2022-10-18 | 2022-12-31 | 2023-01-19 | During the review of MTC, it was found that 1) For free issued material plates, as per 32-SAMSS-004 – Paragraph 12.1.12 required tensile testing is at ½ t location, in provided MTC’s tests are performed at ¼ t Location. MTC’S attached. 2) For free issued material plates (provided MTC’s specified only 2 cycles) as per 32-SAMSS-004- 12.1.9 (Two PWHT cycles to account for future repairs and/or alterations.) MTC’S attached.
전기 | 제어설비 | 미시공 | 자재 | 기타 | 재작업 | MIP6 | 현대건설 | NCR-OOK-EL003-001 | EL003 | EL | Control and Protective Panel | Hitachi Energy Ltd. | - | 2022-12-12 | 2023-06-11 | 2023-05-17 | Metrosils, Series, Shunt (Variable, Stabilizing, Non Linear) Resistors are not installed on all High Impedance Protection Panels. As per response received, the contractor HDEC will finalize the relay setting calculation and it will be shared with Vendor for procuremment of Metrosils, Series, Shunt (Variable, Stabilizing, Non Linear) Resistors. Due to urgency of the delivery of the material; the relay & protection panel (with tags as mentione below) will be dispatched without these metrosils and resistors, and it was agreed among HDEC & Hitachi that it will be fixed at site. The same information was shared with Saudi Aramco and their concurrence was obtained. This NCR is issued on the advice of Saudi Aramco in order to follow up the installation of missing metrosils & resistors in panels at site. The NCR will be closed by HDEC once the missing metrosils & resistors will be fixed in all panels (with tags as metioned below) at site. Panels Affected: M97-101-PRP-011/ 012/ 013/ 014/ 015/ 016/ 017/ 018/ 019/ 020/ 021/ 022/ 023/ 024/ 025/ 026/ 027/ 028/ 029/ 030/ 032 (total 21 Each) Requirements/
전기 | 제어설비 | 미시공 | 자재 | 기타 | 재작업 | MIP6 | 현대건설 | NCR-OOK-EL003-002 | EL003 | EL | Control and Protective Panel | Hitachi Energy Ltd. | - | 2022-12-12 | 2023-06-11 | 2022-12-16 | The 94 Trip Relay provided in the relay & protection panels is not furnished with two spare NC contacts as required by clause 13.3.3 of 16-SAMSS-514. Since no waiver was obtained by vendor Hitachi from CSD, therefore vendor shall provide these two spare NC contacts for each 94 Trip relay. Due to urgency of the delivery of the material; the relay & protection panel be dispatched without these two spare NC contacts. As confirmed by HDEC– this matter will be addressed and closed at site under contractor responsibility and HDEC will ensure full compliance to clause 13.3.3 of 16-SAMSS-514 for each panel having 94 Trip relay. The same information was shared with Saudi Aramco and their concurrence was obtained. This NCR is issued on the advice of Saudi Aramco in order to follow up the closure of this comment at site. The NCR will be closed by HDEC once compliance to clause 13.3.3 of 16-SAMSS-514 is ensured i.e. two spare NC contacts are added for each 94 Trip Relay. Panels Affected: All panels with 94 Trip Relay Installed
전기 | 제어설비 | 미시공 | 자재 | 기타 | 재작업 | MIP6 | 현대건설 | NCR-OOK-EL009-001 | EL009 | EL | Power System Automation | Schweitzer Engineering Laboratories | TIEPCO | 2022-12-16 | 2023-05-17 | 2024-11-29 | During the Final inspection of PSA panels at Sub-vendor, some punch p oints were not rectified by main vendor and sub-vendor. As per section 9.8 of SAEP-1151 requirement, contractor shall not release material with punch list items unless approval is obtained from company representative. Hence it was agreed with company representative to issue INCR for outstanding points along with conditional release. The punch list is attached along with this INCR. The affected panels are: M97-101-PSA-001 M97-107-PSA-001
기계.설비 | 일반기계_고정.회전 | 손상 | 자재 | 품목의 결함, 손상 및 제작불량 | 폐기 | MIP6 | 현대건설 | NCR-OOK-MR024-005 | MR024 | MR | OWSF(WIP)_CENTRIFUGAL PUMP(Assembly) M97-G-0004B(FILTER BACKWASH PUMP) | AES Arabia | Flowserve Worthington | 2022-12-07 | 2023-02-13 | 2022-12-17 | Spool damage were found during the receving inspection at Flowserve KSA. 1) Material / Size : Suple Duplex / Pipe / 1/2” Sch 80 2) Damaged spool parts(Attachement#1 : Marked DWG for the damaged 2 spools) 3) Service : Mechanical Seal Flushing Plan 32
기계.설비 | 저장탱크 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 재작업 | MIP6 | 현대건설 | NCR-OOK-MR024-006 | MR024 | MR | OWSF(WIP)_Sludge Silo | AES Arabia | Powertech | 2023-01-04 | 2023-05-30 | 2023-02-03 | Fabrication Error noted during Final Inspection of Sludge silo Tank No: M97-D-0011B. Dimensional error noted in welded support No: PSL10. As per drawing (VD-MR024-086-02 rev.2), the support should be placed at 41 Deg. when measuring from 270 Deg. towards 0 Deg., But the fabricator has placed the support at 49 Deg. he dimensions noted as 1544 MM but in actual achieved length as 1944 MM. So now, the vendor need to cut the support and shift to 400 MM (Relocation of support) to match with the top platform assembly
전기 | 급.배전설비 | 미시공 | 자재 | 기타 | 재작업 | MIP6 | 현대건설 | NCR-OOK-EL008-002 | EL008 | EL | LV SWGR/MCC, Cablebus (M97-107-MCC-006) | WESCOSA | - | 2023-01-09 | 2023-01-31 | 2023-05-17 | During the FAT of 480V LV controlgear tag #97-107-MCC-006, a concern was raised that in switchin assembly (feeder#) 18M -the frame rating (AF) and trip rating (AT) of the breaker installed is not matching with the approved SLD. WESCOSA later informed that the rating of the breaker shall be updated in the SLD and correct rating of the breaker to be installed shall be 600AF / 300AT. However, due to unavailability of the trip unit rated for 300AT, WESCOSA has installed 500AT trip unit. As per WESCOSA the correct trip unit (i.e. 300AT) will be available by mid of December 2022. Due to urgency of the delivery, the MCC tag# M97-107-MCC-006 is agreed to be shipped with 600AF/500AT breaker in feeder 18M with a condition that WESCOSA will replace the trip unit at site and after replacement breaker testing will be performed. This has been agreedbetween Saudi Aramco, HDEC & WESCOSA. This NCR is issued in order to follow up the closure of this comment (#29) in the attached punch list # EL008-WES-PL-003 Rev.01 updated 30 October 2022. The NCR will be closed bu HDEC once the trip unit is replaced and breaker is satisfactorily tested as site.
전기 | 급.배전설비 | 미시공 | 자재 | 기타 | 재작업 | MIP6 | 현대건설 | NCR-OOK-EL018-001 | EL018 | EL | Power Distribution Board (Non. Exp.) | Al Fanar Electrical Systems | - | 2023-01-25 | 2023-02-28 | 2024-11-29 | 02 Ea. 100A CBs are missing in LV Panel Board (tag# M97-107-PP-011). Additionally, 36 Ea. fuses are missing in space heater panel (tag# M97-107-CP-031). These issues/items were highlighted in the punch list issued at the time of FAT. As per vendor, the missing material will be fixed at site. Due to urgency of the delivery, the panel board tag# M97-107-PP-011 and space heater panel tag# M97-107-CP-031 are agreed to be shipped without 02 EA. CBs in panel board and 36 Ea. fuses in space heater panel. This has been agreed between vendor, contractor & Saudi Aamco. This NCR is issued on the advice of Saudi Aramco (SAIR) in order to follow up the closure of the comment in the attached punch list with regard to the missing CBs and fuses. The NCR will be closed by HDEC once the missing material will be fixed at site by Al Fanar.
기계.설비 | 기타 | 기타 | 자재 | 품목의 결함, 손상 및 제작불량 | 수리 | MIP6 | 현대건설 | NCR-OOK-PI047-001 | PI047 | PI | Lined Plug Valve | Flowserve Ahaus Germany | - | 2023-03-20 | 2023-06-20 | 2023-04-04 | During visual inspection of the painting the following imperfections were discovered on the majority of the valves as per below photographs. Furthermmore, it was established that the applicable coating systems were not applied in accordance with the requirements. APCS-1A and APCS-1D were combined / mixed up
기계.설비 | 기타 | 기타 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 재작업 | MIP6 | 현대건설 | NCR-OOK-PI047-002 | PI047 | PI | Lined Plug Valve | Flowserve Ahaus Germany | - | 2023-03-20 | 2023-06-20 | 2023-04-04 | 1.Manufacturer standard of Paiting for Gear box shall be clarified 2.Extention pieces are electro plated. Painting system Shall be clarified 3.Extention pieces are welded at the inside continuous welding is missing4.Extention pieces are not assembled
기계.설비 | 기타 | 기타 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 현상태사용 | MIP6 | 현대건설 | NCR-OOK-PI033-001 | PI033 | PI | Ball Valve (6") | Petrol Valves SPA | - | 2023-04-18 | 2023-07-03 | 2023-04-14 | For the Valve procured by Petrol valves, The valves body made of Carbon Steel and have an APCS 1D paint cycle. However Valve components (Trunnion and Caps) made of Inconel material are painted.
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 현상태사용 | MIP6 | 현대건설 | NCR-OOK-MR003-001 | MR003 | MR | Finned Tube for Air cooled H/E | HPS | Aircofin | 2023-05-14 | 2023-08-14 | 2023-05-18 | It was found that 11 pieces of un-finned end on one side in “Box number 10” were found to be out of tolerance.(Measured between 27 ~ 39mm). Another inspected “Box number 5”, All measured within Tolerance. DWG : 36mm (+3 / -0mm) Actual : 27 ~ 39mm
기계.설비 | 일반기계_고정.회전 | 기타 | 시험.검사 | 검사, 시험의 미시행 또는 미흡 | 재작업 | MIP6 | 현대건설 | NCR-OOK-MR005-001 | MR005 | MR | API PUMP(BB) | Sulzer Pump | Sulzer Pump UK | 2023-03-13 | 2023-10-03 | 2023-07-10 | For UK-IN-052 Rev.2 & UK-IN-053 Rev.1, inspection was proceed with only Vendor
기계.설비 | 일반기계_고정.회전 | 미시공 | 자재 | 기타 | 재작업 | MIP6 | 현대건설 | NCR-OOK-MR012-001 | MR012 | MR | (M97-G-0767)_FIRE WATER PUMP | Sulzer Pump | Sulzer Pump KSA | 2024-01-08 | 2024-06-31 | 2024-03-18 | 1. As per 34-SAMSS-831 section 11, An identification tag or nameplate of 316 stainless steel shall be attached securely to the equipment with SS or Monel fasteners. The tag shall be marked with raised alpha-numeric or die stamped with the proper information, The tag or nameplate shall be located so that the information can be read after installation of the equipment or components. But it was found that Saudi Aramco PO number not mentioned in the skid name plate. 2. LCS internal wiring shall be tagged as required by SAES-J-902, section16.1.1. All wiring shall be tagged at each end. Each wire tag shall have two labels. The first label (closest to the end of the wire) shall identify the terminal number to which the wire is physically connected. The other label shall be the terminal number of the connection of the opposite end of the wire.
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 품목의 결함, 손상 및 제작불량 | 재작업 | MIP6 | 현대건설 | NCR-OOK-MS006-001 | MS006 | MS | S&T Heat Exchanger | ZPEC | - | 2024-01-11 | 2024-05-03 | 2024-02-01 | During M95-E-0205A (after PWHT) tube side hydrostatic test it is observed that channel insulation ring ISR#01 cleats are cut from near the ring and the cleats falling at orientation 87.5°, 110°, 177.5°, 200°, 267.5°, 290°, 312.5° are deformed. Reason for cutting and deforming cleats are found to be bolt tightening access requirement for hydrostatic test preparation. Same deformation of cleats are observed on M95-E-0205B channel insulation ring ISR#01 which has been utilized for M95-E-0205A/B spare bundle tube side hydrostatic test.
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 식별, 추적관리 미흡 | 현상태사용 | MIP6 | 현대건설 | NCR-OOK-MS008-001 | MS008 | MS | Electrical Heater | Chromaolx | - | 2024-01-23 | 2024-03-29 | 2024-05-29 | 8" SCH 80 SMLS, 1/2"[12.7mm] WALL Tee was seen with manufacturer’s identification markings/Material B/SB564 as seen. The stamping of material type and grade did not match that seen on the supporting MTC reflecting B/SB366. The required material is B/SB366 not B/SB564.
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 식별, 추적관리 미흡 | 현상태사용 | MIP6 | 현대건설 | NCR-OOK-MS008-002 | MS008 | MS | Electrical Heater | Chromaolx | - | 2024-01-23 | 2024-07-29 | 2024-05-29 | The followed flanges are need to be re-stamped because it is not matched with the required material. 8" 600# RFWN, SCH 80 BORE : 6 pcs 2" 600# RFLWN : 4 pcs 8" 600# BLIND RF : 2 pcs 6” 2500# RTJ HB LWN : 4 pcs 2” 2500# RTJ RFLWN : 2 pcs The required marking: N08810 The actual marking: N08800 or N08811
기계.설비 | 일반기계_고정.회전 | 미시공 | 자재 | 기타 | 재작업 | MIP6 | 현대건설 | NCR-OOK-MR005(SSPC)-001 | MR005 | MR | Hot Oil Circulation Pump Tag # M95-G-0700 A/B/C | SULZER SAUDI PUMP COMPANY LIMITED | - | 2024-02-19 | 2024-08-18 | 2024-10-28 | During the final inspection of the Hot Oil Circulation Pump assembly (Tag # M95-G-0700 A/B/C), auxiliary piping (plan 23), temperature indicators (TI/TW), and associated piping, gaskets, and fasteners were found unsecured and not installed.
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 재작업 | MIP6 | 현대건설 | NCR-OOK-MR005(SSPC)-002 | MR005 | MR | Hot Oil Circulation Pump Tag # M95-G-0700 A/B/C | SULZER SAUDI PUMP COMPANY LIMITED | - | 2024-02-19 | 2024-08-18 | 2024-12-09 | During the final inspection of the pump assembly Hot Oil Circulation Pump Tag # M95-G-0700 A/B/C, a discrepancy was identified with the coating system applied to the casing washers. As per MR # MIP6-MR-MR-005 Rev C, Para 1.27.4, Coating system (M95-A-HE-100001) and specification SAES-H-001, and Coating system Map # M95-A-HE-100001 Rev A1, para 6.4 Fasteners (For pressure retaining equipment/piping, excluding structural fasteners), all fasteners, including casing washers, should be coated with ceramic fluoropolymer as per 09-SAMSS-107. However, during the inspection, it was found that the casing washers in the actual pump assembly were not PTFE coated.
기계.설비 | 일반기계_고정.회전 | 기타 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 재작업 | MIP6 | 현대건설 | NCR-OOK-MR012-002 | MR012 | MR | (M97-G-0767)_FIRE WATER PUMP | Sulzer Pump | Sulzer Pump KSA | 2024-02-26 | 2024-08-16 | 2024-06-28 | As per Painting Procedure for Diesel Fire Water Pump(VD-MR012-015 Rev.1) and Coating Map M95-A-CE-021000, APCS 1A-External and APCS-2A Internalshall be applied for Diesel Day Tank But Int / Ext Paint applied in reverse
기계.설비 | 일반기계_고정.회전 | 미시공 | 자재 | 기타 | 재작업 | MIP6 | 현대건설 | NCR-OOK-MS018-001 | MS018 | MS | Hot Oil Furnace PKG_Fuel gas skid | ITT | Sinergia | 2024-06-19 | 2024-10-30 | 2024-09-03 | Final inspection including pneumatic test for all flanged joints shall be performed at the skid-mounted unit manufacturer’s facility to ensure that the unit meets requirements as described in the project specifications. However, the following activity couldn’t be completed during the final inspection due to the below: 1. The final visual inspection & Pneumatic test had been done partially because some valves (4pcs for each skid / Total 8 pcs) need to be delivered as loose supplied items due to the delay in production and shall be installed at site. (Missing Valve list) -. HV-040(8”/2ea), HV-057(1”/2ea), HV-061(1”/2ea), HV-063(2”/2ea) 2. Further FAT punch closing carried out on 24th May 2024 and noted partial punches were closed and remaining punches were noted in open condition. -. Open Punch items : No.7, 8, 17, 20, 27, 35, 37, 38, 40, and 41 In this regards, both ARAMCO and HDEC requested to deliver the skids to site urgently considering site construction schedule. The remaining punches shall be closed at site. Also, Vendor confirmed that there is no affect the functionality and warranty of overall package.
전기 | 계기 | 미시공 | 자재 | 기타 | 재작업 | MIP6 | 현대건설 | NCR-OOK-IN005-001 | IN005 | IN | Pipeline Leak Detection System (PLDS) | Emerson Korea | - | 2024-06-11 | 2024-12-10 | 2024-10-28 | During the FAT inspection of PLDS Server cabinet at Emerson Saudi Arabia Company, some FAT punch points were not rectified and closed. As per section 9.8 of SAEP-1151 requirement, contractor shall not release material with punch list items unless approval is obtained from company representative.
기계.설비 | 일반기계_고정.회전 | 기타 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 폐기 | MIP6 | 현대건설 | NCR-OOK-MS006-001 | MS006 | MS | S&T Heat Exchanger | ZAMIL PROCESS EQUIPMENT COMPANY (ZPEC) | - | 2024-08-05 | 2024-09-19 | 2024-08-05 | During M95-E-0202A&B (after PWHT) shell side hydrostatic test in stacked condition the glue marks near the gasket area were observed and the glue was used on the gasket on tag no M95-E-0202B. As per 32-SAMSS-007 para 10.2.17 the use of shellacs, glues, lead etc on gaskets during testing is prohobitted.
전기 | 계기 | 미시공 | 자재 | 기타 | 재작업 | MIP6 | 현대건설 | NCR-OOK-IN002-001 | IN002 | IN | Analyzer System With Shelter | ISG | - | 2024-08-19 | 2024-10-31 | 2024-11-29 | 1) The Installation of Sampling Conditioning system is not done along with its tubing work in M95-AH-002 Analyzer shelter and this is the fufilling ITP :VD-IN002-027 Sec:2.2.4 & 2.2.5.
기계.설비 | 일반기계_고정.회전 | 미시공 | 자재 | 기타 | 폐기 | MIP6 | 현대건설 | NCR-OOK-MS015-001 | MS015 | MS | Vaccum Deaeration Package | Veolia Water solutions | - | 2024-08-22 | 2024-10-30 | 2024-11-07 | he scale provided on the level gauge is showing measurement units in "mm" which is SI unit. As per 34-SAMSS-831 requirements, all measurement shall be done in English Units (which is inches or feets for level).
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 품목의 결함, 손상 및 제작불량 | 재작업 | MIP6 | 현대건설 | NCR-OOK-MS008-003 | MS008 | MS | Electrical Heater | CHROMALOX | - | 2024-08-29 | 2024-10-29 | 2024-10-30 | It was observed that the TEE (TEE,BW,8"SCH80,SMLS,INC800H, 2PCS) which fabricated by IPP was identified as lnconel 800 I 330 stainless steel when evaluated via X-ray fluorescence (XRF) spectroscopy. In this case, the XRF identified the presence of silicon in the semi-quantitative results. When a ground portion of the TEE was evaluated via XRF, it identified the material as 'lnconel 800' / 330 stainless steel. TEE was observed to be in blasted condition upon inspection visit. The OD, ID, and Weld Prep areas are the affected areas noted to be blasted. Blast media was confirmed by IPP as it is Aluminum oxide with noted blast media residue on the ID of TEE in current condition. Weld prep areas noted to be blasted was found with rust contamination on and near weld prep areas
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 재작업 | MIP6 | 현대건설 | NCR-OOK-MS014-001 | MS014 | MS | Electrical Trim Heater | INOXCVA | CHROMALOX | 2024-08-29 | 2024-11-29 | 2024-10-30 | 1. Chamber (PIPE, 8"SCH40, 304H, SMLS): During machining process the inco『rect tool was used. This resulted in an additional feature around the OD of the intended hole. 2. Flange (FLANGE:8"-300# 304H RFWN): The flange serration face has been damaged with defect protruding into ID bore concern for leak pattern 3. Cap (8" SCH 40, SA403 304H): The requirement material is SCH 40 as per the DWG, but the actual material is SCH BOS. 4. Tee (8" x 8" x 6", RDC, SA403, WPS3): Noted for out of tolerance ovality on 8" side and high step in ID.
기계.설비 | 일반기계_고정.회전 | 미시공 | 자재 | 기타 | 재작업 | MIP6 | 현대건설 | NCR-OOK-MS016-001 | MS016 | MS | Flare Package_FFG & Propane Skid | JOHN ZINK COMPANY | KESME | 2024-11-01 | 2024-12-30 | 2024-12-11 | During Factory Acceptance Test, below punch lists are issued and rectification after site delivery. 1) It is observed that the height of the LCP is more than 2 meters, so, the LCP manually operable button cannot be accessed. It is against 16-SAMSS-512 clause 15.1 and SAES-B-054 requirements. 2) LCP Tag for 0270 is wrong on LCP. (M96-LCP-F-0270). The letter “F” is missing. 3) PCV fasteners were found non-fluoropolymer coated. (Non-fluoropolymer is acceptable. But SS316 bolts are required instead of SS304 bolts.) 4) Temperature rating of some internal parts of LCP are not meet the requirement
기계.설비 | 일반기계_고정.회전 | 손상 | 자재 | 품목의 결함, 손상 및 제작불량 | 수리 | MIP6 | 현대건설 | NCR-OOK-MS008-004 | MS008 | MS | Lean Fuel Gas Heater (M97-E-0602 A/B) - 18 inch / 2 set | Chromaolx | Chromalox | 2025-03-26 | 2025-07-29 | 2025-05-30 | It was observed that there are couple of linear indications on the pipe surface. (18” Pipe for Chamber) Update: During evaluation, total four linear indications were identified as critical by the inspectors.
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 수리 | MIP6 | 현대건설 | NCR-OOK-MS008-005 | MS008 | MS | Rich Fuel Gas Heater(M97-E-0601 A/B) - 8 inch / 2 set | Chromaolx | Chromalox | 2025-04-16 | 2025-07-29 | 2025-05-29 | It was observed that ‘Fly cut’ for both tube element and rod on wrong side (wet side) for 8” flanges.
기계.설비 | 일반기계_고정.회전 | 손상 | 자재 | 품목의 결함, 손상 및 제작불량 | 수리 | MIP6 | 현대건설 | NCR-OOK-MS008-006 | MS008 | MS | Rich Fuel Gas Heater(M97-E-0602 A/B) - 18 inch / 2 set | Chromaolx | Chromalox | 2026-01-16 | 2026-02-27 | 2026-02-24 | During the final inspection prior to bundle insertion and shipment, flange surface damage was observed on the Grayloc flange gasket/sealing surface of heater assemblies M97-E-0602A/B.
건축 | 철골 | 기타 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 재작업 | SM12 | 현대건설 | NCR-OOK-SC001-001 | SC001 | SC | Strucral Steel | International Building System Factory | - | 2020-09-24 | 2020-10-13 | 2020-10-13 | It was found during painting inspection that the bolt holes of structural steel main members were painted. This is a violation of 12-SAMSS-007 para 6.2.7.3 related to electrical continuity for non-conductive coating.
건축 | 철골 | 기타 | 설계 | 기타 | 재작업 | SM12 | 현대건설 | NCR-OOK-SC001-002 | SC001 | SC | Strucral Steel | International Building System Factory | - | 2020-11-06 | 2020-11-07 | 2020-11-12 | It was found that the HOLD member item list of Steel Structure issued by HDEC was not monitored correctly by IBSF. Therefore, there are two cases not follow as per HOLD item list issued: Case 1 : Two pieces of steel structure members was wrongly delivered to site after HOLD. Case 2 : One piece of steel structure member wrongly on-going fabrication after HOLD.
건축 | 철골 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 재작업 | SM12 | 현대건설 | NCR-OOK-SC001-003 | SC001 | SC | Strucral Steel | International Building System Factory | - | 2020-11-19 | 2020-11-21 | 2020-11-25 | During shop material inspection of Galvanizing, it was found out that below items has a low DFT of under 100microns as per minimum requirement of the procedures.
건축 | 철골 | 자재불량 | 자재 | 식별, 추적관리 미흡 | 재작업 | SM12 | 현대건설 | NCR-OOK-SC002-001 | SC002 | SC | Strucral Steel II | Astra Factory for Heavy Industries | - | 2020-12-03 | 2020-12-14 | 2020-12-23 | During surveillance inspection it was observed that AHI QC failed to control the Erection Part Marking. Hard punching of 3863-J01-01 PR-79-IC2-B4-G098 & 3863-J01-01 PR-79-IC2-B4-C025, is not matching with the stenciling and stickers provided. Stenciled Part Mark 3863-J01-01 PR79-IC2-B4-C027 and Part Mark on Stickers 3863-J01-01 PR-79-IC2-B4-G027 do not match with each other. Items : 3863-J01-01 PR-79-IC2-B4-G098, 3863-J01-01 PR-79-IC2-B4-G025 and 3863-J01-01 PR-79-IC2-B4-C027
기타 | 기타 | 기타 | 기타. | 기타 | 현상태사용 | SM12 | 현대건설 | NCR-OOK-GE-002 | N/A | Etc. | N/A | N/A | - | 2020-12-18 | 2021-02-26 | 2021-02-26 | For any CONTRACTOR/Subcontractor issued Purchase Order with a value exceeding Ten Thousand U.S. Dollars ($10,000), CONTRACTOR shall obtain COMPANY Approval prior to placing and revising the Purchase Order as per Schedule G Para. 11.2 and Schedule Q Attachment VI Para 1.3 & 1.4. However, CONTRACTOR/Subcontractor has issued Purchase Order without obtaining COMPANY’s NOL for following items as well as Non-Inspectable Item which exceed Ten Thousand U.S. Dollars ($10,000) 1. SM12-AR-MR-001 Epoxy Coated Rebar 2. SM12-AR-MR-002 Precast Concrete 3. SM12-HV-MR-002 PVC and CPVC Pipe, fittings and adhesives Moreover, CONTRACTOR revised steel structure P.O (SC-PO-001 Rev.1) without COMPANY’s approval.
전기 | 급.배전설비 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 재작업 | SM12 | 현대건설 | NCR-OOK-EL003-001 | EL003 | EL | Transformer (230/13.8kV) | SAUDI POWER TRANSFORMER COMPANY | - | 2021-06-28 | 2021-07-30 | 2021-07-15 | As per 14-SAMSS-531 Sec 5.1 “All wiring shall be a minimum of 2.5 mm² (14 AWG) 600-V stranded copper”. It was found that the cables provided to RPRR devices are 16AWG un-armored cables.
기계.설비 | 기타 | 기타 | 시험.검사 | 절차서, 지침서의 미준수 | 재작업 | SM12 | 현대건설 | NCR-OOK-PI016-001 | PI016 | PI | Forged Fitting | MEGA SPA | - | 2021-11-03 | 2022-01-31 | 2022-01-24 | Corrosion test of below listed items in A182 F44 has been performed with test duration. 24 which is in contrasr to applicable 02-SAMSS-013, paragraph 11 which stated that duration shall be of 48h. ITEM 209 (TAG I146333687) MEGALET Sch. 40S/10S A/SA182 F44 1x3 qty 1 ITEM 218 (TAG I149346060) MEGALET Sch. 10S/10S A/SA182 F44 3x8 qty 2
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 재작업 | SM12 | 현대건설 | NCR-OOK-MS001-001 | MS001 | MS | Dish Heads of Vessel I | AL Zamil Heavy Industries limited | Arabian Oasis Industries LLC | 2021-11-11 | 2022-01-14 | 2021-12-21 | Impact test of Dished Head (2:1 Ellipsoidal Dish Heads (Welded) Tag No # T74-D-0701A/B/C) weld production test coupon of was performed at -45⁰C after simulation heat treatment. Heat Treatment condition: Normalized + Stress Relieved@ 630⁰C +/-10⁰C for 140mts holding time. Impact test values were found not meeting the required impact value (Minimum Average - 34J and Minimum Individual –27J) at following specimen location per 32-SAMSS-004 Para. 12.3.3
전기 | 계기 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 폐기 | SM12 | 현대건설 | NCR-OOK-RM001-001 | RM001 | RM | Thermowell for Air Compressor | HANWHA POWER SYSTEMS CO LTD | WIKA ALEXANDER WIEGAND SE AND CO KG | 2021-11-23 | 2021-12-31 | 2021-12-23 | For the following thermowells the tip diameter is 0,625” instead of required 0.79”: T76-67-TW-0104, T76-67-TZW-0105, T76-67-TW-0107, T76-67-TW-0108, T76-67-TW-0146, T76-67-TZW-0147, T76-67-TW-0149, T76-67-TW-0150, T76-67-TW-0188, T76-67-TZW-0189, T76-67-TW-0191, T76-67-TW-0192, T76-67-TW-0230, T76-67-TZW-0231, T76-67-TW-0233, T76-67-TW-0234 For the following thermowells the tip diameter is 0,625” instead of required 1.024”: T76-67-TW-0100, T76-67-TW-0102, T76-67-TW-0101, T76-67-TW-0103, T76-67-TW-0106, T76-67-TW-0142, T76-67-TW-0144, T76-67-TW-0143, T76-67-TW-0145, T76-67-TW-0148, T76-67-TW-0184, T76-67-TW-0186, T76-67-TW-0185, T76-67-TW-0187, T76-67-TW-0190, T76-67-TW-0226, T76-67-TW-0228, T76-67-TW-0227, T76-67-TW-0229, T76-67-TW-0232
전기 | 급.배전설비 | 자재불량 | 자재 | 품목의 결함, 손상 및 제작불량 | 현상태사용 | SM12 | 현대건설 | NCR-OOK-EL004-001 | EL004 | EL | Transformer & NGR (13.8/4.16kV, 13.8/0.48kV) | WESCOSA | - | 2022-01-03 | 2022-01-30 | 2022-01-28 | Temperature raise test was started at 7.00Am as per NOI and around 9.00Am suddenly the transformer Pressure relief valve pop-upped and the transformer oil splashed from the PRD for the transformer tag # T76-022-XFR(T)-316, S.No. 2021W03646.
기계.설비 | 기타 | 기타 | 자재 | 미승인 자재 사용 | 현상태사용 | SM12 | 현대건설 | NCR-OOK-PI011-001 | PI011 | PI | HDPE Fittings | National Marketing EST.CO.LTD | Plastitalia SPA | 2022-02-08 | 2022-04-30 | 2022-04-13 | Plate LJ Flange / items 1, 2, 3, 5, 39 have been purchased by Plastitalia to other sub-supplier in RVL named AGRU, that is not mentioned in approved sub-vendor list.
기계.설비 | 일반기계_고정.회전 | 기타 | 시험.검사 | 절차서, 지침서의 미준수 | 재작업 | SM12 | 현대건설 | NCR-OOK-MS007-001 | MS007 | MS | Air Dryer Package | KAESER Kompressoren GMBH | Schwartz-Hautmont | 2022-03-15 | 2022-09-30 | 2022-09-07 | Hydrostatic test for T76-D-0721A/B (Dryer Vessel), T76-D-0722A/B (Pre-Filter), T76-D-0723A/B (After Filter) were performed without ‘Punch Close’ & In addition without contractor having cleared all the NDE report to ensure full compliance as well as having outstanding welding activities and no prior approval thereof.
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 재작업 | SM12 | 현대건설 | NCR-OOK-MS007-002 | MS007 | MS | Air Dryer Package | KAESER Kompressoren GMBH | Schwartz-Hautmont | 2022-03-15 | 2022-09-30 | 2022-09-15 | Skid welds joint are not fully seal welded as required by 12-SAMSS-007 Para 5.2.4.4 “The edges of tightly contacting surfaces shall be completely seal welded”. Floor plates against skid beams.
전기 | 기타 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 재작업 | SM12 | 현대건설 | NCR-OOK-RM002-001 | RM002 | RM | Motor for Centrifugal Pump, API 610 BB | ITT Saudi Company | TECO MIDDLE EAST ELECTRICAL AND MFR | 2022-03-25 | 2022-08-31 | 2022-08-31 | Stator Winding immersion test or Sealed Winding conformation test as per 17-SAMSS-502, sec.6.3.4.4 The Stator Insulation resistance value measured very low in water and not complying the NEMA-MG1- 2016 Part 12.62 & ITP sec.0020-0020 requirements. Hence the testing activity was failed. As per 17-SAMSS-502, sec.6.3.4.4, Vendor shall submit the report as below. Repairs to the stator winding system required to correct a failed test shall be documented and submitted within two weeks to the Saudi Aramco representative in coordination with the Coordinator, Electrical Systems Division, and Consulting Services Department. The report shall detail the repair, the life impact of the repair, and the design changes that may be required on identical machines.
기계.설비 | 기타 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 재작업 | SM12 | 현대건설 | NCR-OOK-MS006-001 | MS006 | MS | Ball Valve of WSF PKG | AES Arabia | BAC Valves | 2022-05-04 | 2022-10-07 | 2022-08-16 | Coating inspection as per Aramco painting system APCS 1B performed. As per Painting system DFT results shall be between 275-400 microns finding that average results were 550 microns on average – out of acceptance criteria. Coating inspection – 599 / 571 / 681 microns (shall be between 275-400 microns as per Specification).
전기 | 급.배전설비 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 재작업 | SM12 | 현대건설 | NCR-OOK-EL201-001 | EL201 | EL | 230kV GIS Assembly (Interconnection Elements) | HITACHI (ABB) | - | 2022-05-24 | 2022-09-29 | 2022-09-28 | In a reference to Non-conformance of length of interconnections issue, discovered during an ongoing installation in Marjan PKG6 project, and documented vis INCR NCR-OOK-EL001-002-GIS, the length of the interconnection Element was less than the length required for the end-to-end connection between the ES/DS. After an internal investigation, the same issue was confirmed for SM12 project, as this GIS was designed and delivered within the same timeframe. This NCR is issued for HITACHI to provide RCA & Corrective action.
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 품목의 결함, 손상 및 제작불량 | 재작업 | SM12 | 현대건설 | NCR-OOK-MS007-003 | MS007 | MS | Air Dryer Package (Dryer Vessels) | KAESER Kompressoren GMBH | Schwartz-Hautmont | 2022-07-18 | 2022-10-30 | 2022-11-29 | Prior to the hydrostatic test inspection, ARAMCO pointed out the followings 1) All welds must be dressed-up. - All welding of the Dryer vessels have the toes of the welds shall be dressed (smooth contour / fatigue finish) as it is noted that the vessels are in Cyclic service. 2) There are the misalignment on weld between head and shell for both top and bottom sides.
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 재작업 | SM12 | 현대건설 | NCR-OOK-MS007-004 | MS007 | MS | Air Dryer Package | KAESER Kompressoren GMBH | - | 2022-07-19 | 2023-04-28 | 2023-03-17 | During the painting inspection, it was observed High DFT on flange face and side. The detected DFT is often 600-1000µ, otherwise the acceptable value is 275-400µ (micrometers, min-max.)
기계.설비 | 일반기계_고정.회전 | 기타 | 자재 | 서류의 결함, 미비 | 현상태사용 | SM12 | 현대건설 | NCR-OOK-MS001-002 | MS001 | MS | LP Flare Header Drain Drum (T78-D-0802) of Vessel I (C.S) | Al-Zamil Company For Heavy Steel | - | 2022-08-12 | 2023-02-28 | 2023-01-12 | Welding is done for L-seams and C-seams of main shell with improper WPS/PQR (VD-MS001-COMMON-030 Rev.C) Despite MDMT was changed from 1.11℃ to - 44.44℃ in GAD (VD-MS001-T78D0802-005 Rev.C) on 3-Aug-2021, WPS/PQR (VD001-COMMON-030 Rev.C) was not revised to include a required impact testing on MDMT -44.44℃ and Welding has been conducted.
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 식별, 추적관리 미흡 | 재작업 | SM12 | 현대건설 | NCR-OOK-MS001-003 | MS001 | MS | 90° LR ELBOW 2, 1/2” STD ASME SA403 WP316 (QTY : 4 EA) | Al-Zamil Company For Heavy Steel | - | 2022-08-26 | 2022-11-26 | 2022-09-20 | During material receiving inspection of elbows by ZHI, it was found that wrong original marking in actual material engraved SA-234 instead SA-403 as violation of 02-SAMSS-013 Para.15. Material Descriptions: 1) 90° LR ELBOW 2, 1/2” STD ASME SA403 WP316 - QTY : 4 EA 2) MFR : PETROL RACCORD SPA / MFR ID 30003102 3) To be used for T74-D-0701C
기계.설비 | 일반기계_고정.회전 | 기타 | 설계 | 설계, 도면의 부정확 | 재작업 | SM12 | 현대건설 | NCR-OOK-MS007-005 | MS007 | MS | Piping Spools | KAESER Kompressoren GMBH | - | 2022-09-22 | 2023-03-31 | 2023-02-27 | Hydrostatic pressure test of Piping Spools has been carried out respectively at the followed pressure as per pressure test procedure No. VD-MS007-COMMON-040 Rev.0 Skids No. T76-U-0702A/B : 418.47 psig (432.97 psi) But it’s observed that test pressure was wrongly calculated and applied as per piping GA & ISO METRIC / VD-MS007-COMMON-091 Rev.1 and hydrostatic test pressure shall be 425 psig (439.5 psi) in accordance with 01-SAMSS-010 Para. 9.1.1
기계.설비 | 일반기계_고정.회전 | 기타 | 시험.검사 | 절차서, 지침서의 미준수 | 재작업 | SM12 | 현대건설 | NCR-OOK-MS001-004 | MS001 | MS | 4” SCH. STD ASME SA333-6 (QTY : 1 EA) | AL Zamil Heavy Industries limited | MFR : Ali N. AL Nassar and Partners | 2022-10-05 | 2022-10-25 | 2022-10-18 | 1. Impact testing for pipes ordered to ASTM A333 and A671 shall be carried out at -45°C or as required by the applicable ASTM standard, whichever is colder as per Para 9.2.1 of 01-SAMSS-043. 2. Where the largest possible test specimen has a width along the notch of less than 80% of the material nominal thickness shall be conducted at a temperature lower than the MDMT by an amount equal to the difference between the temperature reduction corresponding to the actual material thickness as per UG-84(c)(5)(-b) of ASME Sec.VIII Div.1. 3. Nominal thickness of 4” STD is 6mm and test specimen is 3.33mm which is less than 80% of the material nominal thickness shall be conducted impact test at -56􀈔 considering temperature reduction 11􀰁 from original MDMT(-45􀰁). 4. Impact test was conducted at -55􀈔􀀃􀁚􀁄􀁕􀁐􀁈􀁕􀀃􀁗􀁋􀁄􀁑􀀃􀀐􀀘􀀙􀈔 for stockiest 4” SCH.STD in SA333-6 after SPWHT(1cycle & 4cycle) by Saudi Aramco’s approval 3rd party laboratory (TCR Arabia). It is non-conformance for 32-SAMSS-043 & ASME Sec.VIII Div.1.
기계.설비 | 일반기계_고정.회전 | 기타 | 자재 | 미승인 자재 사용 | 폐기 | SM12 | 현대건설 | NCR-OOK-MS007-006 | MS007 | MS | Filters | KAESER Kompressoren GMBH | Schwartz-Hautmont | 2022-09-30 | 2023-03-31 | 2023-02-09 | MTC of Studs and bolts installed on assembled Filters was checked and following non-conformance found: Sub Vendor "LGC US Asset Holdings" of Stud bolts 1"8 UN-2A x 5-1/2" B7 FPC and HEX NUT 1"8UN-2B H2 FPC is not on Approved Vendor List - 9COM 60000000577/580.
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 재작업 | SM12 | 현대건설 | NCR-OOK-MS001-005 | MS001 | MS | Saddle Assembly & Embedded plates (T78-D-0801/0802/0805) | AL Zamil Heavy Industries limited | - | 2022-10-17 | 2022-12-31 | 2023-01-04 | Anchor bolt hole distance from center line for Fixed & Sliding Saddle, Sliding/Embedded Plate shall be 475mm and hole to hole distance shall be 950mm as per the approved GA drawing whereas actual distance found 380mm from saddle center to anchor bolt hole and 760mm from hole to hole center which is a violation of design requirement as per the GA drawing. Fixed & Sliding Saddles, Sliding/Embedded plates have been fabricated as per the detail drawing and discrepancy (dimension mismatch) noticed in both GA and detail drawings.
기계.설비 | 일반기계_고정.회전 | 기타 | 설계 | 도면, 기술시방서와 규격, 표준요건의 상이 | 재작업 | SM12 | 현대건설 | NCR-OOK-MS007-007 | MS007 | MS | Skid A/ B/ C | KAESER Kompressoren GMBH | Schwartz-Hautmont | 2022-10-25 | 2023-01-30 | 2023-01-18 | Painting system for Hand rail & Ladder are revised after painting from APCS-26 to APCS-26T as per Coating Map / T80-H-CE-034351 Rev.00F
기계.설비 | 일반기계_고정.회전 | 자재불량 | 설계 | 설계, 도면의 부정확 | 재작업 | SM12 | 현대건설 | NCR-OOK-MS007-008 | MS007 | MS | Skid A/ B/ C T76-U-0702A/B/C | KAESER Kompressoren GMBH | Schwartz-Hautmont | 2022-10-28 | 2023-04-28 | 2023-04-05 | During pre-assembly of checkered plate in the Skid frame, it’s observed that 1. Skid frame supporting dryer leg support is not aligned 2. Checkered plate couldn’t be installed in Skid frame.
기계.설비 | 기타 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 폐기 | SM12 | 현대건설 | NCR-OOK-PI003-001 | PI003 | PI | PIPE (SS SMLS) | Zhejiang Jiuli HI-TECH Metals | - | 2022-12-30 | 2023-09-09 | 2023-06-26 | During chemical composition analysis, the below item found the PREN was not qualified as per 01-SAMSS-046 30-Oct-2013 para.8.3 requirement. Detail result as per below: The required Pitting Resistance Equivalent (PREN) (%Cr+3.3(%Mo+0.5%W)+16%N) for the base material shall be greater than or equal to 24 as per 01-SAMSS-046 30-Oct-2013 para.8.3 requirement for material TP316/316L.
기계.설비 | 일반기계_고정.회전 | 자재불량 | 설계 | 기술검토 미비, 기술시방서의 부정확 | 재작업 | SM12 | 현대건설 | NCR-OOK-MS007-009 | MS007 | MS | Skid structure | KAESER Kompressoren GMBH | Schwartz-Hautmont | 2023-01-09 | 2023-08-10 | 2023-07-10 | Vendor has realized that SH(Manufacturer) made a mistake with the mechanical calculation of the skid structure. The weight value of Dryers used for the mechanical calculation was 2.548,42 kg(service empty), instead of 5.000 kg(service full).
기계.설비 | 일반기계_고정.회전 | 손상 | 자재 | 품목의 결함, 손상 및 제작불량 | 재작업 | SM12 | 현대건설 | NCR-OOK-MS001-006 | MS001 | MS | Davit arm & eye bolts damage during transportation (T74-D-0802) | AL Zamil Heavy Industries limited | - | 2023-01-17 | 2023-03-03 | 2023-02-01 | Item : CPI Slop Oil Tank (T74-D-0802) Davit arm & eye bolt of M1 manway were damaged during transportation due to inconsideration height of trailer.
기계.설비 | 일반기계_고정.회전 | 손상 | 자재 | 품목의 결함, 손상 및 제작불량 | 재작업 | SM12 | 현대건설 | NCR-OOK-MS003-001 | MS003 | MS | Flange to End Plate welds (T76-E-00501 A/B/C/D/E/F) | LHE Co., Ltd | - | 2023-01-27 | 2023-04-15 | 2023-04-21 | Welding defects(LF : Lack of Fusion) were found on all weld joints by UT before PWHT Weld Details : Double sided bevel weld / weld deposit : total 145mm (72.5mm per each side) Tag No # T76-E-00501 A/B/C/D/E/F Flange Detail : LWN 18” 150 RF SA105N (WELD OVERLAY) End Plate Detail : SA516-70N 145t Joint no : N1~N4 (X 6 items) Qty :24 Joints (4flanges/1item X 6items)
기계.설비 | 기타 | 누수 | 자재 | 품목의 결함, 손상 및 제작불량 | 폐기 | SM12 | 현대건설 | NCR-OOK-MS010-001 | MS010 | MS | Valve Assembly Hydro Test | Zeeco Middle East Limited | L&T Valves Limited | 2023-02-11 | 2023-08-30 | 2023-08-29 | During Valve Assembly Hydro Shell test, leakage was observed on Body Shell (Heat No. : GLBP / PT Report No. : D03 / Foundry : Amazon)
기계.설비 | 기타 | 기타 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 재작업 | SM12 | 현대건설 | NCR-OOK-MS007-010 | MS007 | MS | 18 Relief Valves | Kaeser Kompressoren GMBH | Emerson Automation Solutions | 2023-02-03 | 2023-05-30 | 2023-03-29 | Per ITP the valves shall be coted per SAES-H-001 and SAES-H-101V using the painting system APCS-1B. However, all valves were coted using the painting system APCS-1D.
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 현상태사용 | SM12 | 현대건설 | NCR-OOK-MS012-001 | MS012 | MS | Drinking Water Return Mixer (T76-K-0401) | Samwon Engineering Co., Ltd. | - | 2023-03-06 | 2023-04-07 | 2023-03-09 | It was observed that there was discrepancy on length of Drinking Water Return Mixer between DWG and Actual during final inspection. Please refer to the followed value in detail. - Drawing Length: 760±3.17 - Actual Length: 766 (+2.83mm)
기계.설비 | 일반기계_고정.회전 | 자재불량 | 설계 | 도면, 기술시방서와 규격, 표준요건의 상이 | 현상태사용 | SM12 | 현대건설 | NCR-OOK-MS006-002 | MS006 | MS | Walnut Shell Filtration Package (T78-U-0903) | AES Arabia LIMITED | - | 2023-03-08 | 2023-05-31 | 2023-04-11 | WALNUT SHELL FILTER AND FACE PIPING SKID ( T78-D-0932 A / B) AND GUARD FILTER PIPING SKID, (T78-D-0931 A/B) – Checkered floor plates used in the skid assembly is not meeting the minimum mandatory requirement of the 12-SAMSS-007 para 4.13 – ASTM A 786 pattern 4 or 5, instead the checkered floor plates used were not incompliance with this requirement.
기계.설비 | 일반기계_고정.회전 | 손상 | 자재 | 품목의 결함, 손상 및 제작불량 | 재작업 | SM12 | 현대건설 | NCR-OOK-MS018-001 | MS018 | MS | Sand Filters for Sand Filter PKG | Veolia Water solutions | Al-Zamil Metal Works Factory | 2023-03-18 | 2023-06-30 | 2023-05-24 | It’s noticed that ZMF failed to protect the flanges during fabrication stage and the flange faces have been observed some damages. - Total Flanges observed for investigation as per ZMF inspection report: 64 nos. - Flanges applied re-serration as per ZMF inspection report: 25 nos. - Flanges decided to use it as it is (without re-serration) as per ZMF inspection report: 39 nos. In addition, re-serration was applied without proper notice and inspection. - Evaluation has not been done as per applicable standard and it’s not offered for evaluation & Inspection - Re-serration procedure is not approved by HDEC - No approval record for re-serration company is shared - Post inspection after re-serration has not been done properly to verify required surface roughness (3.2-6.4 um Ra) & raised face height
전기 | 계기 | 기타 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 재작업 | SM12 | 현대건설 | NCR-OOK-MS018-002 | MS018 | MS | Cooling water Flow Transmitter | Veolia Water solutions | Krohne Altometer | 2023-03-07 | 2023-08-23 | 2023-06-07 | The painting system applied does not concur with the approved painting procedure. The coating on the flow meter had been performed as per KROHNE standards. APCS-1D shall be applied as per the approved procedure.
기계.설비 | 기타 | 자재불량 | 자재 | 품목의 결함, 손상 및 제작불량 | 재작업 | SM12 | 현대건설 | oms | IN009 | CI | Buckling Pin Relief Valve | BS and B Safety systems | - | 2023-05-02 | 2023-07-04 | 2023-06-20 | During surface preparation for valve external coating, open porosity or sand inclusions were found after grit blasting. During visual examination of the grit blasted surfaces, open porosity or sand inclusions became visible. Several isolated areas were noted as well as areas with clusters of porosity/sand inclusions. The applicable Tag are for three (3) 48’’ #150 Buckling Pin Relief Valves, Tagged: T78-58-PZV-0012, T78-58-PZV-0013 & T78-58-PZV-0010. Ref. Casting markings: GG46630-15 Heat K309, GG46630-14 Heat K306 and GG46630-16 Heat K309. Finally, the above valve’s final surfaces requirement is out of acceptance criteria as per MSS SP-55 Class ‘A’.
전기 | 제어설비 | 미시공 | 자재 | 기타 | 재작업 | SM12 | 현대건설 | NCR-OOK-EL203-001 | EL203 | EL | Control and Protective Relay Panel | Hitachi Energy Ltd. | - | 2023-05-25 | 2023-08-30 | 2023-08-01 | 1. FAT Punch listed that ; As per 16-SAMSS-514 Section 15.1.1 c) Lamp shall be field replaceable from the front. Presently the installed lamps are not replceable from front. (Common for all 79 tags). Metrosil and Stabilizing resistors were missing. (Two tags for T80-026-RP-049, T80-026-RP-050) Reger to the attached photos. 2. iFAT Punch listed that; I/O configuration comments to be rectified at site by Vendor during iSAT.
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 재작업 | SM12 | 현대건설 | NCR-OOK-MS010-002 | MS010 | MS | Water Pumps (Bare Pump) for Flare Gas Recovery Package | Zeeco Middle East Limited | Goulds Pumps Co. Ltd | 2023-06-26 | 2024-02-18 | 2024-01-15 | During performance test for T74-G-0711A, measured vibration value was exceed the requirement for performance test procedure. And performance test reports for other units (T74-G-0711B/C/D) were not prepared, because there was no successful internal testing due to same issue of high vibration as well.
전기 | 급.배전설비 | 미시공 | 자재 | 기타 | 재작업 | SM12 | 현대건설 | NCR-OOK-EL001-001 | EL001 | EL | 4.16 kV MCC | Wahah Electric Supply Company (WESCOSA) | - | 2023-05-20 | 2023-07-23 | 2023-07-27 | The materials are delivered to the site with an open punch list. Refer to the attached punch list no. SM12-EL001-WES-PL-009 for further details
기계.설비 | 일반기계_고정.회전 | 기타 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 재작업 | SM12 | 현대건설 | NCR-OOK-RM014-001 | RM014 | RM | Fabrication of skid structure frame | Veolia Water Solutions | Power Tech. For Metal Fabrications | 2023-07-11 | 2023-10-11 | 2023-08-21 | 1) PT STEEL carried out modification work on the released skid structure frame (after final inspection & IRC) without an approval from CONTRACTOR. The modification works were done without submission/approval of revised fabrication drawings. 2) Hot work (gas cutting) was carried out on the painted frame to make holes for pipe. Due to the hot work, the existing paint was damaged on many locations. 3) Welded CS plates were removed and re-welded with SS plates without submission/approval of revised drawings and approved WPS for SS materials (VD-RM014-COMMON-118 / WPS & PQR for Skids Structure). 4) As per 12-SAMSS-007, Para. 4.1.2, the minimum thickness of any part of a structural shape shall be 5 mm, but whereas drip plate is of 3 mm. Drip plate (SS Material) welding is ongoing without WPS approved by CONTRACTOR. On 3 mm thickness plate, SMAW is ongoing due to which the entire drip plate got distortion/bend.
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 폐기 | SM12 | 현대건설 | NCR-OOK-MS007-011 | MS007 | MS | T76-U-0702A/B/C (3 SKIDs) | Kaeser Kompressoren GMBH | - | 2023-07-19 | 2023-10-30 | 2023-09-19 | The stud bolts near all ball valves flanges connections are short. (threads are not exposed on above nuts) The followed bolts are need to be replaced.
기계.설비 | 일반기계_고정.회전 | 미시공 | 자재 | 기타 | 재작업 | SM12 | 현대건설 | NCR-OOK-MS018-003 | MS018 | MS | T76-U-0504 SKID - A,B,C,D (4 SKIDs) | Veolia Water Solutions | - | 2023-08-31 | 2023-12-30 | 2023-10-06 | Factory Acceptance Test (FAT) shall be performed at the skid-mounted unit manufacturer’s facility to ensure that the unit meets all functional and operational requirements as described in the project specifications. However, the following activities were not performed during FAT. 1. Instrument Tubing were not subjected to pneumatic leak tests in accordance with requirements of 34-SAMSS-831. 2. All flanged joints were not inspected by pneumatic test and soap solution. 3. Visual inspection for whole skid not completed. 4. Dimensional Inspection of Critical Points (TI-01D & TP-03D) for only Skid-D not done during FAT. 5. Lock nut for all Piping U Bolts not installed. 6. Flow Transmitter to be installed at site. (T76-65-FT-0101, 0102, 0103 & 0104) 7. Uninstalled AOV Tag# T76-65-AOV-0294 shall be installed and cable work to be done as per the approved drawing. 8. Skid-D- AOV-0294 & PI-0211 were not installed and Main Pipe spool (SHT-022 SPL-S3) is also uninstalled during FAT. Those shall be installed at site. 9. Name Plates for the Skids not installed. 10. Pipe supports (L-4045mm x W-800mm) are dismantled from skids for transportation to site.
전기 | 제어설비 | 미시공 | 자재 | 기타 | 재작업 | SM12 | 현대건설 | NCR-OOK-EL005-001 | EL005 | EL | Power System Automation | Schweitzer Engineering Laboratories, Saudi Ltd. | Rawabi Electirc | 2023-09-07 | 2023-12-10 | 2023-11-01 | 1. Punch list Issued during DAT - Total number of punches issued:146 (Inspector issued 59, PSED issued 87) 2. Punch Re-inspection conducted and resulted as follows. - Closed 115, Open 31 (Completed but Not Verified) > 31 out of 87 punch points issued by PSED will be still open and verified for closing at site during site testing.
전기 | 급.배전설비 | 미시공 | 자재 | 기타 | 재작업 | SM12 | 현대건설 | NCR-OOK-EL006-001 | EL006 | EL | DC System | AEG Power Solutions GmbH | - | 2023-10-04 | 2023-11-30 | 2023-10-27 | 14 open punch items out of 94 items issued during FAT will be implemented at site during site testing and pre-commissioning stage.
전기 | 제어설비 | 미시공 | 자재 | 기타 | 재작업 | SM12 | 현대건설 | NCR-OOK-EL203-002 | EL203 | EL | Control and Protective Relay Panel | Hitachi Energy Ltd. | - | 2023-10-19 | 2024-01-15 | 2023-11-01 | 1. Materials are delivered with conditional IRC due to seven(?) FAT punches and four(4) iFAT punches open; 2. FAT punch listed that; #1 : Protection settings changed is not in the 10list ,need to add check #2 : IED firmware changed is not in the 10 list ,need to add check #3 : Sag swell detection is not in the 10 list #4 : Markup in the 10 list need to update
전기 | 제어설비 | 기타 | 환경 | 기타 | 재작업 | SM12 | 현대건설 | NCR-OOK-IN001-001 | IN001 | CI | DCS MARSHALLING & FF MARSHALLING cabinets | Yokogawa Saudi Arabia (YKSA) | - | 2023-10-23 | 2023-12-31 | 2023-12-26 | The fire incident happened on 07th Oct 2023 at YKSA basement floor manufacturing area,( YKSA- DTV). During the time of fire incident PKG#12- Six (06) cabinets were placed for the MOD-PACK modification. The incident area and cabinet staqed area see the below photo. The following six cabinets for PKG#12 are staged T76-043-DCS-XMC-201, T76-043-DCS-XMC-202, T76-043-DCS-XMC-204, T76-043-DCS-XMC-203, T76-043-DCS-FMC-201 & T76-043-DCS-FMC-202. The cabinet (T76-043-DCS-XMC-201) front door was fully opened during the water sprinklers activated. While doing the visually verification water dried mark found on the side punched rails, some of the mounting plate location also (see the below photo's). The other five(5) cabinets ( T76-043-DCS-XMC-202, T76-043-DCS-XMC-204, T76-043-DCS-XMC-203, T76- 043-DCS-FMC-201 & T76-043-DCS-FMC-202 ) between the edges of the cabinets and GASKET the dust water stained found (see the below photo)
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 재작업 | SM12 | 현대건설 | NCR-OOK-MS001-007 | MS001 | MS | Direct Contact After Cooler | Air Product and Chemicals Inc | Munters | 2023-10-06 | 2024-01-31 | 2024-02-01 | The mis-arrangement of bolting between N3/N4 permanent internal nozzle flange and removal internal distribution nozzle plate flange due to mismatch of flange rating - N3/N4 permanent internal nozzle flange: #300 - Removal internal distribution nozzle plate flange: #150 The elevation and orientation each nozzle is as below. (Refer to Att. #1) - N3 Nozzle (4”): Orientation 234 deg. / Elevation 18,029mm from reference tangent line. - N4 Nozzle (10”): Orientation 305 deg. / Elevation 10,285mm from reference tangent line.
전기 | 급.배전설비 | 미시공 | 자재 | 기타 | 재작업 | SM12 | 현대건설 | NCR-OOK-EL006-002 | EL006 | EL | DC / AC UPS System | AEG Power Solutions GmbH | - | 2023-11-12 | 2024-02-11 | 2024-02-15 | 1. Tewnty six (26) open punch items our of 100 items issued during FAT will be implimented at site during site testing and pre-commissioning stage.
기계.설비 | 일반기계_고정.회전 | 누수 | 자재 | 품목의 결함, 손상 및 제작불량 | 재작업 | SM12 | 현대건설 | NCR-OOK-MS005-001 | MS005 | MS | DEMINERALIZED WATER TANK | Amiantit Fiberglass Industries | - | 2023-11-08 | 2024-01-31 | 2024-01-17 | It’s observed some leakage on the flange connection and passing through the shell of tank (T76-D-0401B) during 24 Hrs. leak test. The location of leakage is on bottom of flange and near to shell.
전기 | 제어설비 | 미시공 | 자재 | 기타 | 재작업 | SM12 | 현대건설 | NCR-OOK-EL005-002 | EL005 | EL | Power System Automation | Schweitzer Engineering Laboratories, Saudi Ltd. | Rawabi Electirc | 2023-11-05 | 2024-02-28 | 2023-12-08 | 1. Punch list Issued during DAT - Total number of punches issued:118 (Inspector issued 61, PSED issued 57) 2. Punch Re-inspection conducted and resulted as follows. - Closed 46, Open 5 (by TPI) - Closed 51, Open 5 (by PSED) Ten (10) Open punch points will be rectified and verified for closing at site during pre-commissioning.
전기 | 기타 | 미시공 | 자재 | 기타 | 재작업 | SM12 | 현대건설 | NCR-OOK-EL007-001 | EL007 | EL | Emergency Diesel Generator | Saudi Disel Equipment Company | - | 2024-02-08 | 2024-08-06 | 2024-07-24 | One(1) open punch items out of 35 items issued during FAT will be implemented at site during site testing and pre-commissioning stage. - SM12-EL007-SDEC-PL-003 : Total 35 issued, 34 items closed, 1 items open Refer to the attached punch list
전기 | 제어설비 | 미시공 | 자재 | 기타 | 재작업 | SM12 | 현대건설 | NCR-OOK-EL005-003 | EL005 | EL | Power System Automation | Schweitzer Engineering Laboratories, Saudi Ltd. | Rawabi Electirc | 2024-02-14 | 2024-05-13 | 2024-05-08 | FAT Punch list listed that; 1. Historians are not configured. Vendor to confirm and ensure thath Historians are configured in all panels. 2. Vendor to ensure the buffer ports are configured for all the panels. 3. In the HMI, the statgus of each device to be displayed correctly. Vendor to fix. 4. Vendor to ensure SLD/Network Drawing is correct in HMI before SAT. As per SEL's response these comments will be closed at site during SAT.
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 폐기 | SM12 | 현대건설 | NCR-OOK-MS017-001 | MS017 | MS | Disposal Vaporizer | Al-Zamil Heavy Industries Ltd. | - | 2024-02-05 | 2024-04-30 | 2024-03-23 | ZHI used SA193 B8M stud bolts and SA194 8M nuts which is not coated, for girth flange connection. - as per detail drawing No. VD-MS017-T76E08080908-004 Sheet No.002 and Coating Map CE-034351, material piece mark E0808-212, 212A, 213 and 213A are required to use ceramic fluoropolymer coated bolts and nuts.
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 재작업 | SM12 | 현대건설 | NCR-OOK-MS009-001 | MS009 | MS | Non-Standard forging of Pressure Vessel for Flare & Burn Pit Package | Zeeco Middle East Limited | Maritime Industrial Services (MISA) | 2024-02-07 | 2024-05-30 | 2024-05-21 | 1. Applicable Item: LLP LSD/KO DRUM (T78-D-0822A/B) Non-Conformance Component: 1) N2 (30”) 2EA (Non-Standard Forging (Shape Machining Error) 2) N6A/B (4”) 4EA (Non-Standard Forging (Shape Machining Error) 2. Description 1) TPI found during material receiving inspection that N2 Nozzle is installed on Top Head, so it is required to be Spherical in Shape on forged lip. But materials (N2 Flange) were machined to Cylindrical Radius on forged lip as photos below.
기계.설비 | 일반기계_고정.회전 | 기타 | 자재 | 미승인 자재 사용 | 현상태사용 | SM12 | 현대건설 | NCR-OOK-MS015-001 | MS015 | MS | TSA ReactivationH eater (T76-E-0801/0901) | Chromalox, Inc. | - | 2024-03-15 | 2024-09-27 | 2024-08-29 | It is noted that the rolled and welded plate for Heater Chamber has been purchased through “Mach Industrial Group.” which is not in RVL (Regulated Vendor List) and not approved by sub-vendor List / VD-MS015-COMMON-003 DWG No. : VD-MS015-T76E080109 01-003 rev.0 Tag No.. : T76-E-0801/09 01 (2ea) Rolled and Welded Plate Quantities: 4pcs (2pcs for 1 heater)
기계.설비 | 일반기계_고정.회전 | 미시공 | 자재 | 기타 | 재작업 | SM12 | 현대건설 | NCR-OOK-MS020-001 | MS020 | MS | Odor Abatement Package | Veolia Water solutions | - | 2024-06-04 | 2024-08-30 | 2024-07-17 | Final inspection including pneumatic test for all flanged joints shall be performed at the skid-mounted unit manufacturer’s facility to ensure that the unit meets requirements as described in the project specifications. However, the following activity won’t be completed during the final inspection due to the below: 1. The final visual inspection & Pneumatic test couldn’t be completed because the 3” Gate Valves (10ea) need to be delivered as loose supplied items due to the delay in production and shall be installed at site.
기계.설비 | 일반기계_고정.회전 | 미시공 | 자재 | 기타 | 재작업 | SM12 | 현대건설 | NCR-OOK-RM011-001 | RM011 | RM | Chemical Injection Package | Zeeco Middle East Limited | - | 2024-08-13 | 2024-10-13 | 2024-09-04 | During final & packing inspection for T76-U-0001, we found punches as per the attachments #1, 2. Open punches were closed at vendor shop. But, some of punches were still open during final inspection. All open outstanding / punch lists (Mech. & E&I) as below to be closed at job site. 1. Paint touch-up to be done at site by Zeeco workers. 2. Motor & Pump earthing to be done at site by HDEC. Loose grounding cables for this Sodium Hypochlorite will be provided by Zeeco. 3. Related VDs such as GA drawing to be revised. 4. Missing test reports for Junction Box and Motor to be provided.
기계.설비 | 일반기계_고정.회전 | 미시공 | 자재 | 기타 | 재작업 | SM12 | 현대건설 | NCR-OOK-RM011-002 | RM011 | RM | Chemical Injection Package | Zeeco Middle East Limited | - | 2024-09-08 | 2024-09-30 | 2024-09-20 | During final & packing inspection for Corrosion Inhibitor Skid of T76-U-0505, we found punch as per the attachments #1. One punch was open during final & packing inspection. All open outstanding / punch list as below to be closed after deliver to site. 1. The 3/4” PTFE Lined Blind Flange shall be installed on the topside of LG0032.
기계.설비 | 소화설비공사 | 미시공 | 자재 | 기타 | 재작업 | SM12 | 현대건설 | NCR-OOK-SE001-001 | SE001 | Etc. | Deluge Valve Skid for Fire and Safety Equipment | REDA TRADING AND DEVELOPMENT CO. FO | - | 2024-09-10 | 2024-10-10 | 2024-10-07 | During final & packing inspection for deluge valve skid (T76-U-0502 #1~#7), there are some open points as per the attachment #1. REDA will close out all the open points at site. Open Points #6. Air inlet (TP-3) and air outlet (TP-4) spools missing from assembly. #8. After assembly of spools mentioned in point #6, full skid pneumatic test shall be performed to ensure the integrity of joint tightness. #14. As per datasheet CE-033885-001 Rev.00, Item #24, S.No #12 – There shall be placard for deluge valve but no such placard found on skid. #15. As per datasheet CE-033885-001 Rev.00, Item #24, S.No #14 – All letters shall be written in both English & Arabic on skid. There is no Arabic written on skid. Also to clarify which contents to be written on skid in both English & Arabic. #16. As per datasheet CE-033885-001 Rev.00, Item #24, S.No #16 – Requirements mentioned in this point was not found on skid. REDA to provide. Attachment #1. Punch List Requirements/
기계.설비 | 일반기계_고정.회전 | 미시공 | 자재 | 기타 | 재작업 | SM12 | 현대건설 | NCR-OOK-RM011-003 | RM011 | RM | Chemical Injection Package | Zeeco Middle East Limited | - | 2024-09-30 | 2024-10-31 | 2024-10-11 | During final & packing inspection for Sulphuric Acid Skid of T76-U-0505, we found punches as per the attachments #1. Four punches were open during final & packing inspection. All open outstanding / punch list as below to be closed after deliver to site. 1. There is No enough space to assemble Stud bolt/Nut on the 1” - 45° Elbow PTFE Lined spool between two flanges. 2. Two SPECIAL 40º ELBOWs NPS1'' 150# A536 SCH80 were not assembled to the strainer drain lines. 3. The only PTFE(Teflon) piece (70mm) instead of PTFE lined pipe spool has been installed on the LG-0044 drain line. 4. Upper vent valve of LG-0044 is not closed with PTFE lined blind flange.
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 품목의 결함, 손상 및 제작불량 | 수리 | SM12 | 현대건설 | NCR-OOK-MS010-003 | MS010 | MS | 12” Ball Valve (SN 2201300010001 / TAG No. T74-47-ZV-0244) | Zeeco Middle East Limited | LCM ITALIA SPA | 2024-10-30 | 2024-12-30 | 2024-11-28 | During draining check as part of final inspection, it was noted that drain valve (gate type) of TAG T74-47-ZV-0244, was found blocked and valve wheel is not working for open / close.
기계.설비 | 일반기계_고정.회전 | 기타 | 시험.검사 | 절차서, 지침서의 미준수 | 현상태사용 | SM12 | 현대건설 | NCR-OOK-MS009-002 | MS009 | MS | T78-D-0821A | Zeeco Middle East Limited | Maritime Industrial Services (MISA) | 2024-12-14 | 2025-01-15 | 2025-01-15 | During surveillance inspection, it was noticed that vendor was performed the repair work on nozzle N4 J1 of vessl no-T78-D-0821A after completion of post weld heat treatment without intimating of any inspection authority, it is the vilation of 32-SAMSS-04 clause 16.4.2 and SAES-W-10 clause 13.11
기계.설비 | 일반기계_고정.회전 | 기타 | 자재 | 미승인 자재 사용 | 폐기 | SM12 | 현대건설 | NCR-OOK-MS015-002 | MS015 | MS | TSA Reactivation Heater | Chromalox, Inc. | - | 2025-01-13 | 2025-03-30 | 2025-04-03 | 1.5” pipe with heat number A231216 was utilized in the fabrication of nozzles 3 and 4. This pipe was sourced from a non-approved vendor and is not listed on the ARAMCO Regulated Vendor List (RVL).
기계.설비 | 일반기계_고정.회전 | 기타 | 시험.검사 | 검사, 시험의 미시행 또는 미흡 | 재작업 | SM12 | 현대건설 | NCR-OOK-MS010-004 | MS010 | MS | EIV valve (Tag No. T74-47-ZV-0250) | Zeeco Middle East Limited | Valmet Flow Control Industrial LLC | 2025-02-07 | 2025-05-30 | 2025-03-28 | The testing for 1 EIV valve was not completed due to some issues with the Solenoid Valve.
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 폐기 | SM12 | 현대건설 | NCR-OOK-MS015-003 | MS015 | MS | TSA Reactivation Heater | Chromalox, Inc. | - | 2025-02-19 | 2025-05-30 | 2025-03-11 | The followings were observed during the material receiving inspection. 1. The bore size on the 1.5” RFWN was in compliance with the drawing 121-307180-407, but not in compliance to the drawing note 2 and not in compliance with ASME B16.50. 2. With regard to tube MTC, the requirements of 01-SAMSS-047 concerning the Corrosion Testing, Section 10, Table 4, ASTM G28, Steel Grade UNS NO8825 was not reported as being performed on the first shipment of tubes or the current tubes set for this inspection. 3. Replacement 1.5” pipe receiving inspection was conducted with non-conforming findings. Inside of the 1.5 pipe, with heat number 126118, has a non-round interior on all three pipes presented.
전기 | 계기 | 미시공 | 자재 | 기타 | 재작업 | SM12 | 현대건설 | NCR-OOK-IN002-001 | IN002 | CI | Analyzer System for ASU (+MPS Shelter) | Yokogawa Saudi Arabia Company | - | 2025-03-11 | 2025-06-07 | 2025-04-07 | 1. Seven (7) open punch items out of Eighty nine(89) issued during FAT will be implemented at site during site testing and pre-commissioning stage. - Refer to the attached six punchlists (SM12-IN002-YKSA-PL-001)
전기 | 계기 | 미시공 | 자재 | 기타 | 재작업 | SM12 | 현대건설 | NCR-OOK-IN002-2-001 | IN002-2 | CI | Analyzer System for ASU (T76-AH-0006) | Yokogawa Saudi Arabia Company | - | 2025-03-27 | 2025-06-27 | 2025-05-07 | During the FAT Inspection TPI noticed that for the Analyzer shelter T76-AH-0006 the 3-Phase step down transformer (480VAC/400/230VAC) is missing as per the drawing and BOM, refer the punch point #194. As per section 9.8 of SAEP-1151 requirement, contractor shall not release material with punch list items unless approval is obtained from company representative. Hence it was agreed with the company representative to issue INCR for outstanding point along with conditional release.
전기 | 계기 | 미시공 | 자재 | 기타 | 재작업 | SM12 | 현대건설 | NCR-OOK-IN002-2-002 | IN002-2 | CI | Analyzer System for ASU (T76-AH-0006) | Yokogawa Saudi Arabia Company | - | 2025-04-30 | 2025-07-30 | 2025-10-29 | MPS shelter (housing) was shipped to project site under the following incomplete conditions; 1) Incomplete installation and integration work (like electrical cable, enclosure, instrument, duct etc.) 2) No factory inspection and testing conducted 3) No inspection release certificate issued
기계.설비 | 일반기계_고정.회전 | 기타 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 재작업 | SM12 | 현대건설 | NCR-OOK-MS015-004 | MS015 | MS | TSA Reactivation Heater | Chromalox, Inc. | - | 2025-06-05 | 2025-07-30 | 2025-07-14 | During inspection, it was found that the Inconel 800 heating elements 1.125 OD X 1.031/1.047 ID 800 SMLS tubes had been subjected to abrasive blasting and it has raised concerns regarding the performance of the elements. Also, the Gasket Seal Serration Surface are blasted too. Lastly, VENDOR failed to comply with ITP witness step. (Pre-blast preparation and etc.) This step was not performed and notified to the inspector.
기계.설비 | 기타 | 미시공 | 자재 | 기타 | 재작업 | SM12 | 현대건설 | NCR-OOK-PI064-001 | PI064 | PI | ASU Oxygen General Valve | Herose Gmbh Arnaturen UND Metalle | - | 2025-06-24 | 2025-07-30 | 2025-07-31 | 1. One (1) open action required item issued during inspection will be closed at site. - Action required Item Description Following information are missed on nameplates as per MSS-SP-25 (mandated by 04-SAMSS-035 and MR §10.7).  Body Material Designation  Rating Class  Service limitation
전기 | 계기 | 미시공 | 자재 | 기타 | 재작업 | SM12 | 현대건설 | NCR-OOK-IN012-001 | IN012 | CI | Air Quality Monitoring Station (AQMS) | Yusuf Bin Ahmed Kanoo Company Limited | - | 2025-07-27 | 2025-10-26 | 2025-08-19 | During the FAT inspection TPI noticed that for the QMS Shelter T80-AH-001 at Sub-supplier, some punch points were not rectified by main supplier and sub-supplier. As agreed by all parties (PMT, EPD and Proponent), CAT b & C punch points are moved to site. As per section 9.8 of SAPE-1151 requirement, contractor shall not release material with punch list items unless approval is obtained from company. Hence it was agreed with company to issue INCR for outstanding point along with conditional release. The punch list is attached along with this INCR.
기계.설비 | 일반기계_고정.회전 | 기타 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 현상태사용 | SM12 | 현대건설 | NCR-OOK-MS015-005 | MS015 | MS | TSA Reactivation Heater | Chromalox, Inc. | - | 2025-08-11 | 2025-08-31 | 2025-08-22 | During routine inspection surveillance on 23 July 2025, it was identified that multiple heater units supplied by CHX contain cancelled heating elements that were not replaced, documented, or authorized in accordance with project quality procedures. Although the governing datasheet does not require spare heating elements, CHX elected to install additional elements in each bundle to serve as built-in spares in the event of failures. This provision was an internal CHX decision. However, the handling of failed elements within these spares has raised significant quality and traceability concerns.
기계.설비 | 기타 | 미시공 | 자재 | 기타 | 폐기 | SM12 | 현대건설 | NCR-OOK-MS014-001 | MS014 | MS | Control Valve (Butterfly) for ASU | Air Product and Chemicals Inc | Valmet | 2025-11-13 | 2026-01-30 | 2026-01-20 | 1. One (1) open action required item issued during inspection will be closed at site. - Action required Item Description The Tag # T76-60-ZV-0111 has a galvanized Carbon Steel ASTM A732 Fr 1A coupling on the shaft. This item is not found on the Materials List provided by HDEC. Also, ASTM T732 Fr 1A is not equivalent material of Shaft (ASTM A564 gr. 630 H1150M).
기타 | 기타 | 기타 | 기타. | 기타 | 현상태사용 | SM12 | 발주처 | 500015424 | RM001 | RM | Air Compressor Package | Hanwha Power Systems | Boldrocchi | 2020-09-11 | 2020-10-16 | 2020-10-06 | During Sub-POs review for Instrument Air Compressor, Company has noticed that the Main manufacturer (HANWHA POWER SYSTEMS,ID#30006086) has placed their Sub PO (order# P20BD09002 dated Apr,20 2020) for the (Inlet Air Filter) with on-hold manufacturer (BOLDROCCHI, Italy ID# 30004546). Moreover, the Sub PO placed prior to obtain the Company review of the sub vendor list which is in violation to SAEP-1151, Para. 6.3 that stated "When requested, after P.O. award and prior to sub-P.O placements contractor shall submit sub-vendor list for company review that shall include as a minimum the following: material description, 9COM, approved sub-vendor (Name and ID), inspection level and material specification". In addition to the above, the Contractor did not Document/Report the Nonconformity as Contractor NCR (INCR) which is a violation to SchQ Para 7.5.2. Contractor is requested to provide Root Cause, Corrective action and Preventive action to eliminate reoccurrence of similar issues.
전기 | 기타 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 폐기 | SM12 | 발주처 | 500017991 | RM002 | RM | Motor for Centrifugal Pump, API 610 BB | ITT Saudi Company | TECO Middle East | 2022-08-09 | 2022-10-04 | 2022-09-09 | NCR has been issued to document the repeated failure of stator sealed Winding conformance test for the Closed Loop Cooling Water Pump “T76-GM-0503A” manufactured by TECO middle east (MFR ID#30006593). The previously failed motor has been Re-tested on July, 3rd 2022 where the values of IR(Immersed in water condition after High Potential Test) was 10.7KΩ against the acceptance -criteria of 25MΩ per 17-SAMSS-502/6.3.4.4 and NEMA-MT1. The Manufacturer “TECO” failed to identify the proper RCA which caused a repeated failure for the same motor three times.
기계.설비 | 기타 | 기타 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 재작업 | SM12 | 발주처 | 500018751 | PI002 | PI | PIPE (CS WELD) | Hyundai Steel | - | 2023-03-21 | 2023-06-26 | 2023-07-13 | Hyundai Steel Company (HSC) ID#30008916 neither use pyrometers equipped heat treatment furnace nor attach thermocouples to the pipe which deviates from the heat treatment requirement in 01-SAMSS-043 para. 7.2. The thermocouples in HSC have been located on the upper side of the furnace wall which is not directly attached on the pipe. CONTRACTOR shall conduct full investigation, provide RCA and Corrective Actions to ensure meetings Company standards as well as ensuring the integrity of supplied materials. Contractor PO# 4600061069 IL# 107000205868 Material: CS WELD PIPE / ASTM A671 CC60 CL22. Quantities involved in violation: approximately 1,455 M out of 13,781 M
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 재작업 | SM12 | 발주처 | 500019612 | MS010 | MS | Water Pump | ZEECO MIDDLE EAST LTD | GOULDS PUMPS | 2023-12-06 | 2024-02-18 | 2024-01-15 | NCR has been issued to document the repeated failure of vibration test of the Water Pump “T74-G-0711A” for Flare Gas Recovery PKG manufactured by GOULDS PUMPS/Korea (MFR ID# 30006824). The high vibration issue has been initially observed on June, 2023 during the performance test where the Contractor documented the failure through INCR “NCR-OOK-MS010-002”. After implementing the corrective actions which include the replacement of 3rd stage impeller and other course of actions, the Pump has been Re-tested on Nov, 15 2023 where the high vibration issue was observed again which exceeded the acceptance tolerance (Max. 3.0 mm/sec) as per 31-SAMSS-004 Para 6.9.3 and API-610 table 8. The Manufacturer “GOULDS PUMPS” failed to identify the proper root causes which caused a repeated failure for the same Pump. # Measured vibration value during the initial testing (First Failure): DE _ Horizontal: 8.57 mm/sec / Vertical: 3.11 mm/sec NDE _ Horizontal: 10.17 mm/sec # Measured vibration value during the second Failure: DE – 6.002 mm/sec (Min. Continuous flow) / Vertical DE – 3.975 mm/sec (Mid. Flow) / Vertical Contractor Shall conduct full investigation, provide RCA and Corrective Actions to ensure the quality of supplied equipment. The ACD is Feb-18-2024.
기타 | 기타 | 기타 | 기타. | 기타 | 현상태사용 | SM12 | 발주처 | 500020202 | RM014 | RM | Water Recovery Package | VEOLIA WATER SOLUTIONS | - | 2024-08-14 | 2024-08-19 | 2024-08-19 | Description of Deficiency: Schedule Q Violation Hyundai violated the following: 1. Short notice for inspection (it was sent on Wednesday to conduct inspection on the next day), please find attached the notification. 2. Even though Hyundai received rejection for the notification, they proceed with the activities. 3. The inspection took place on Thursday and Friday (out working days). The inspection level is 3 and the material is chemical skid IL# 107000217826.
기타 | 기타 | 기타 | 기타. | 기타 | 현상태사용 | SM12 | 발주처 | 500020364 | PI008 | PI | PTFE Lined Piping | ELEMENTOS FLEXIBLES ARCONI SA | - | 2024-09-30 | 2024-10-08 | 2024-10-08 | CONTRACTOR have had an incompliance of SVL requirements. CONTRACTOR violated the following: 1. The SVL was submitted with incorrect material requested by the manufacturer. 2. Hyundai did not issue INCR for incorrect material requested in the SVL by the manufacturer. 3. Hyundai submitted the new SVL with the new material after receiving the materials 4. Hyundai did not implement the review comments on the SVL. [SM12] PI008 / PTFE Lined Piping IL107000223155
기계.설비 | 일반기계_고정.회전 | 기타 | 기타. | 기타 | 현상태사용 | STA4 | 현대건설 | STA4-MS003-ZAH-NCR-001 |  | MS | Pressure Vessel |  |  | 2024-08-07 | 2024-09-06 | 2024-08-30 | Vendor placed order for dish head to “Arabian Oasis” prior to get approval from COMPANY. It is violation comparing to MR requirement
기계.설비 | 기타 | 기타 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 재작업 | STA4 | 현대건설 | STA4-PI003-HYS-NCR-001 |  | PI | CARBON STEEL SMLS PIPE |  |  | 2024-09-06 | 2024-09-12 | 2024-09-13 | During marking inspection of pipe, the contract number displayed on the pipes is STA-PI-PO-003-4600066444, it is the same as the contract number shown on the cover of the contract. However, the contract number shown on all vendor documents and ITP is STA4-PI-PO-003-4600066444. The involved pipes refer to attachment-the item list of pipes involved PO number issue.
기계.설비 | 기타 | 기타 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 폐기 | STA4 | 현대건설 | STA4-PI004-PCK-NCR-001 |  | PI | CARBON STEEL WELDED PIPE |  |  | 2024-10-25 | 2024-12-25 | 2024-12-18 | the welding control for production line of 508*9.52, founded incorrect weld wire (ESAB weld EH14) to be used in pipe with 508*9.52(pipe No: 12411266,12411272) due to WPS240610 by welder (Jin long, welder No: PW02208)
기계.설비 | 일반기계_고정.회전 | 기타 | 설계 | 설계, 도면의 부정확 | 현상태사용 | STA4 | 현대건설 | STA4-MS004-XIN-NCR-001 |  | MS | Filter |  |  | 2025-03-28 | 2025-05-30 | 2025-04-01 | Longitudinal weld on Skirt and circumferential weld on Tag No. 404-S-3002 skirt were not identified weld number in the weld map (No. SA-AMI-000-4XIN-102005, Rev.0). The weld number for longitudinal weld of skirt of Tag No. 420-S-0008 (Seam No. A12) was not identified in the weld map (No. A-AMI-000-4XIN-102005, Rev.0.).
기계.설비 | 일반기계_고정.회전 | 기타 | 시험.검사 | 절차서, 지침서의 미준수 | 재작업 | STA4 | 현대건설 | STA4-MS016-STK-NCR-001 |  | MS | Deaerator |  |  | 2025-01-29 | 2025-03-30 | 2025-02-19 | It was observed that the specimen of plates for SPWHT to meet AMIMS-D-3204 requirement are taken from longitudinal instead of Transvers to the rolling direction.
기계.설비 | 일반기계_고정.회전 | 기타 | 설계 | 기술검토 미비, 기술시방서의 부정확 | 재작업 | STA4 | 현대건설 | STA4-MS018-INX-NCR-001 |  | MS | LIN STORAGE & VAPORIZATION SYSTEM |  |  | 2025-02-17 | 2025-05-30 | 2025-05-06 | The longitudinal welds of two adjacent shell rings offset kept by 30° instead of 60° on the following joints
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 재작업 | STA4 | 현대건설 | STA4-MR005-FLW-NCR-001 |  | MR | SALINE COOLING WATER PUMP (LOOP 1) 404-G-3001 A |  |  | 2025-02-27 | 2025-05-30 | 2025-03-21 | 404-G-3001A, Saline Cooling Water Pump(LOOP 1). Flatness on pump pads is out of tolerance according to construction drawing and Flowserve procedure SQ 53 rev.2: required is 0.05 mm/mt while measured values are above 0.25 mm/mt.
전기 | 급.배전설비 | 기타 | 시험.검사 | 검사, 시험의 미시행 또는 미흡 | 현상태사용 | STA4 | 현대건설 | STA4-EL001-HIT-NCR-001 |  | EL | 230kv GIS Drives |  |  | 2025-03-10 | 2025-03-29 | 2025-03-31 | According to SA-AMI-451-4HIT-402107_1, 230kV GIS: INSPECTION AND TEST PLAN-GIS, the highlighted inspection requires Contractor’s (HDEC) witness at Hitachi Energy Bulgaria. However, the Drives (Operating Mechanism for CB) were tested without Contractor’s (HDEC) witness and subsequently delivered to Hitachi Energy in KSA.
전기 | 급.배전설비 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 재작업 | STA4 | 현대건설 | STA4-EL002-HYO-NCR-001 |  | EL | 230kv Power Transformer |  |  | 2025-03-15 | 2025-03-21 | 2025-03-21 | During the Lightning Impulse Test on Phase H2 on 13th.Mar.2025, per SA-AMI-451-4HYO-402002_0_230kV Power TR - FACTORY INSPECTION & TEST PLAN, the result of sequence 7(LI 100%) was failed with the abnormal traces, when performed seventh full wave impulse on H2 terminal,
전기 | 급.배전설비 | 기타 | 자재 | 서류의 결함, 미비 | 현상태사용 | STA4 | 현대건설 | STA4-EL002-HYO-NCR-002 |  | EL | 230kv Power Transformer |  |  | 2025-03-21 | 2025-03-31 | 2025-03-31 | According to SA-AMI-000-HDAI-510003_2 (Vendor Inspection Procedure), all punch list items must be cleared before the inspection release. Additionally, as per SA-AMI-451-HDAI-414002_0 (Unpriced Purchase Order for 230/34.5kV Power Transformer), delivery cannot proceed without the inspection release certificate (IRC) from the purchaser (HDEC). However, considering the site erection situation, HDEC has agreed to issue the IRC with outstanding punch list items (1ea / No .19), as noted in the NCR with the attached punch list. This NCR will be used to track the resolution of the punch list items and will be closed upon HDEC’s agreement.
전기 | 기타 | 손상 | 시험.검사 | 절차서, 지침서의 미준수 | 폐기 | STA4 | 현대건설 | STA4-MR001-HTC-ABB-NCR-001 |  | MR | Main Motor for Centrifugal Compressor (API617) |  |  | 2025-03-27 | 2025-10-18 | 2025-07-30 | During the Final test of the motor, the forced oil lubrication system for the sleeve bearings was not activated, and the oil sumps were apparently dry. As a result, the bearings operated without proper lubrication, leading to excessive friction, heat generation, and severe damage to the bearing components and shaft journal. - Inspection Findings: Following the disassembly of the motor, the following damages were observed. However, please note that this is not the full information of the issues. A. DE and NDE bearing liners (white metal) completely destroyed B. Outer labyrinth seals (DE and NDE) damaged C. Inner labyrinth seals showed discoloration due to excessive heat D. Shaft journal damaged
전기 | 기타 | 기타 | 자재 | 서류의 결함, 미비 | 현상태사용 | STA4 | 현대건설 | STA4-MR005-FLW-NID-NCR-001 |  | MR | SOFT COOLING WATER PUMP DRIVING MOTORS |  |  | 2025-03-27 | 2025-11-11 | 2025-11-05 | According to SA-AMI-000-HDAI-510003_2 (Vendor Inspection Procedure), all punch list items must be cleared before the inspection release. Additionally, as per SA-AMI-000-HDAI-412005_0 / UNPRICED PO FOR COOLING WATER PUMP (API 610 BB), delivery cannot proceed without the inspection release certificate (IRC) from the purchaser (HDEC). However, considering the characteristic of punch, HDEC has agreed to issue the IRC with 1 outstanding punch list item, as noted in the NCR with the attached punch list. This NCR will be used to track the resolution of the punch list items and will be closed upon HDEC’s agreement. - Note: The IECEx CES 25.0003X certification for the soft cooling pump (Type ET 1000) is nearing completion, with the hard copy expected soon. The draft copy currently shared confirms that this motor meets the certification requirements for hazardous area installations as specified by the project. Since the third-party certification body (CESI) is a government institution, the process of issuing the final copy is taking considerable time. The final copy will be verified during the review of the final dossier."
기계.설비 | 기타 | 기타 | 자재 | 미승인 자재 사용 | 현상태사용 | STA4 | 현대건설 | STA4-PI003-HYS-NCR-002 |  | PI | Carbon Seamless Pipes (NPS 1.5 and below) |  |  | 2025-03-31 | 2025-06-21 | 2025-06-22 | - During TBE stage and PIM held on June 25th 2024, HYST has confirmed that Sub-Vendor is not applicable. - For the small pipes (NPS 1.5 and below), HYST outsourced them to Hongda Precision manufacturing Co., Ltd; HYST provided the mother pipes, sub-vendor (Hongda Precision manufacturing Co., Ltd) executed the cold-drawing, HT, ECT whereas the Sch.Q mandate that manufacturing shall be conducted by the sub-vendor which is approved by HDEC and COMPANY.
전기 | 급.배전설비 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 폐기 | STA4 | 현대건설 | STA4-EL006-SCH-NCR-001 |  | EL | Voltage Transformer (VT) |  |  | 2025-04-17 | 2025-12-01 | 2025-09-17 | According to AMIMS-P-6504, para 15.3.4(Indoor Metal-Clad Switchgear: 1 to 40 kV), voltage transformers (VTs) shall be of the withdrawable type. However, the VT installed on the incomer panels is of the fixed type, whereas the VTs on the Bus VT and VT Riser panels are of the withdrawable type
전기 | 기타 | 기타 | 시험.검사 | 기타 | 현상태사용 | STA4 | 현대건설 | STA4-MR012-NIJ-WEE-NCR-001 |  | MR | HV Motor 1 set |  |  | 2025-05-09 | 2025-10-31 | 2025-09-09 | The HV Motor (403-GM-0001-C / 1 out 3ea) has been shipped to Main vendor (Nijhuis Pompen BV / Netherlands) without the required approval of the ITP/Test procedure which is a clear violation of project quality requirements. As per the Vendor Inspection Procedure, all ITPs must be submitted and approved by both CONTRACTOR and COMPANY prior to the commencement of any inspection, testing, or the start of fabrication. Fabrication, inspection, or testing activities shall not begin until the ITP and procedures have received formal approval from both CONTRACTOR and COMPANY, in accordance with project requirements
전기 | 급.배전설비 | 기타 | 시험.검사 | 시험, 검사 주기의 부적절 | 재작업 | STA4 | 현대건설 | STA4-EL001-HIT-NCR-003 |  | EL | 230kV GIS ( 9 bays) |  |  | 2025-05-07 | 2025-06-30 | 2025-07-07 | The 230kV GIS has been delivered to the site without meeting the following contractual quality requirements: 1. SA-AMI-451-HDAI-340700_3(MATERIAL REQUISITION FOR 230kV GIS (Gas Insulated Switchgear)),  Final inspection shall be performed prior to delivery. Equipment/material shall be delivered only after Final Inspection had been performed and Release Note Issued.  Equipment/material shall not be released with punch list items unless approval is obtained from COMPANY Representative. ▶ The final inspection(C4) was applied to only 3 bays and the GIS was shipped without IRC. 2. SA-AMI-000-HDAI-510003 (Vendor Inspection Procedure)  Agreed Exceptions List shall be prepared by Vendor, reviewed and approved by the CONTRACTOR and COMPANY to accompany the material and / or equipment to site. ▶ The punch lists from the FAT and final inspection have not been closed, nor have they been agreed upon as an exception list. 3. Additional issue ▶ According to the approved ITP (SA-AMI-451-4HIT-402107 Rev.2), the final inspection (C4) and Release Note(C5 / Hold point) shall be applied to all bays. This requirement was clarified, agreed upon, and recorded as a punch during the FAT. However, despite HDEC's request to update the applicable quantity on the inspection notification, the final inspection was only applied to 3 bays.
전기 | 급.배전설비 | 미시공 | 자재 | 기타 | 재작업 | STA4 | 현대건설 | STA4-EL006-SCH-NCR-002 |  | EL | 34.5kv SWGR 1st batch |  |  | 2025-05-14 | 2025-12-15 | 2025-12-15 | According to SA-AMI-000-HDAI-510003_2 (Vendor Inspection Procedure), all punch list items must be cleared before the inspection release. Additionally, as per SA-AMI-000-HDAI-340705 (MATERIAL REQUISITION FOR 34.5kV Switchgear), Equipment/material shall not be released with punch list items unless approval is obtained from COMPANY Representative. However, considering the site erection situation, HDEC has agreed to issue the IRC with outstanding punch list items as attached. This release is also aligned with CPY PMT as the outstanding punch lists are from CPY proponents. This NCR will be used to track the resolution of the punch list items and will be closed upon HDEC’s agreement.
전기 | 급.배전설비 | 미시공 | 자재 | 기타 | 재작업 | STA4 | 현대건설 | STA4-EL001-HIT-NCR-004 |  | EL | 230kV GIS ( 5 bays) |  |  | 2025-05-14 | 2026-01-30 | 2026-01-30 | According to SA-AMI-000-HDAI-510003_2, Vendor Inspection Procedure, all punch list items must be cleared before the inspection release. Additionally, as per SA-AMI-451-HDAI-340700_3, MATERIAL REQUISITION FOR 230kV GIS (Gas Insulated Switchgear), Equipment/material shall not be released with punch list items unless approval is obtained from COMPANY Representative. However, considering the site erection situation, HDEC has agreed to issue the IRC with outstanding punch list items as attached. This NCR will be used to track the resolution of the punch list items and will be closed upon HDEC’s agreement.
기계.설비 | 일반기계_고정.회전 | 자재불량 | 설계 | 도면, 기술시방서와 규격, 표준요건의 상이 | 재작업 | STA4 | 현대건설 | STA4-MS011-MHS-NCR-001 |  | MS | Shell plate with Nozzle |  |  | 2025-05-15 | 2025-06-15 | 2025-06-12 | During final inspection of shell plates with nozzle, the minimum shell horizontal butt weld toe to toe distance is not meeting the code requirement as follows, Dwg No: SA-AMI-420-4MHS-101009 Sheet 02 of 09 Rev.00 Tag No: 420-T-0002 (TK-491) Shell Plate: SP2-01C Nozzle No: B3 44" Ø 1. The distance between the bottom shell weld toe and the R.F. pad weld toe is 45 mm. 2. The distance between the R.F. pad weld toe and the top shell weld toe is 60 mm
전기 | 급.배전설비 | 미시공 | 자재 | 기타 | 재작업 | STA4 | 현대건설 | STA-EL011-CEG-NCR-001 |  | EL | AC UPS & DC SYSTEM(3rd batch) |  |  | 2025-05-23 | 2025-11-30 | 2025-12-08 | According to Vendor Inspection Procedure, all punch list items must be cleared before the inspection release. Additionally, as per MATERIAL REQUISITION FOR AC UPS & DC SYSTEM, Equipment/material shall not be released with punch list items unless approval is obtained from COMPANY Representative. However, considering the site erection situation and punch categories, HDEC has agreed to issue the IRC with outstanding punch list items as attached. This NCR will be used to track the resolution of the punch list items and will be closed upon HDEC’s agreement.
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 재작업 | STA4 | 현대건설 | STA4-MS021-ZE2-FMC-NCR-001 |  | MS | DERRICK STRUCTURE |  |  | 2025-04-17 | 2025-05-30 | 2025-05-13 | During the inspection visit to the subcontractor responsible for the galvanizing process, conducted to verify compliance with the approved procedure, it was observed that some flanges exhibited evidence of being manufactured from multiple pieces after galvanizing. As a result, this report has been issued due to the following: - • Zeeco's drawings do not indicate any welded splices, specifying that each flange should be fabricated from a single piece. • The segmented flanges were assembled, welded, and potentially subjected to NOT (Non-Destructive Testing) without prior notification for witness inspection at these critical points. • Since these joints are not specified in the approved drawings, they are classified as shop splices and require formal written approval prior to fabrication.
전기 | 급.배전설비 | 미시공 | 자재 | 기타 | 폐기 | STA4 | 현대건설 | STA4-EL001-HIT-NCR-002 |  | EL | LCC |  |  | 2025-04-13 | 2026-01-25 | 2026-01-09 | According to SA-AMI-000-HDAI-510003_2 (Vendor Inspection Procedure), all punch list items must be cleared before the inspection release. Additionally, as per STA4-EL-PO-001-4600066433 (Purchase Order for 230KV GIS), delivery cannot proceed without the inspection release certificate (IRC) from the purchaser (HDEC). However, considering the characteristic of punch, HDEC has agreed to issue the IRC with outstanding punch list item, as noted in the NCR with the attached punch list. This NCR will be used to track the resolution of the punch list items and will be closed upon HDEC’s agreement
기계.설비 | 일반기계_고정.회전 | 기타 | 시험.검사 | 절차서, 지침서의 미준수 | 재작업 | STA4 | 현대건설 | STA4-MS016-STK-NCR-002 |  | MS | Stockiest Pipe |  |  | 2025-05-09 | 2025-08-31 | 2025-08-18 | CPY inspector observed that the SA106-B 8” SCH.100 pipe purchased from Van Leewen stockiest should not followed AMIMS-L-1043 requirements as below. - 8’’ Sh100 Pipe is only examined according ISO 10893-3 and only in transverse direction. ASTM testing to be Performed - Pipe is only non-destructive examined with Magnetic flux in accordance with ISO 10893-3 and not with the mentioned ASTM standards. - Hydrotest pressure to be at 90% of yield = 388barg - Marking does not comply with AMIMS L 1043. The marking shall include the specification number AMIMS-L- 1043 along with date of issue. - Pipes shall be supplied with bevelled ends in accordance with Figure 4 of ASME B16.25 irrespective of wall thickness, unless otherwise specified in the Purchase Order. Weld bevels must be NDE MPI tested - Certificate does not mention a radiation level. This to be verified. It shall be certified that the radiation level of the pipes is less than 100 beckerel /gram.
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 현상태사용 | STA4 | 현대건설 | STA4-MS018-INX-NCR-002 |  | MS | Dish Head |  |  | 2025-04-23 | 2025-07-30 | 2025-06-05 | Required minimum thickness as mentioned in the drawing : 15.00 mm The lowest actual thickness: Outer Vessel Tag: 408-D-2001-A: 14.70 mm Outer Vessel Tag: 408-D-2001-D: 14.90 mm Outer Vessel Tag: 408-D-2001-F: 14.68 mm Location Pattern: Lowest thickness noticed all the formed dish head with in Crown Area at radius around 1400mm. Dish Head ID 5000mm. The 14.70, 14.90 and 14.68mm are in isolated spots at the radius of around 1400mm. Thickness check by D-Meter. Calibration ok. Inspection Date : 18 & 19.April.2025 Offered Items: Bottom Dish Head, Outer Vessel Outer Vessel Tag: 408-D-2001-A Outer Vessel Tag: 408-D-2001-B: Ok [ 15.64 mm ] Outer Vessel Tag: 408-D-2001-D Outer Vessel Tag: 408-D-2001-F
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 폐기 | STA4 | 현대건설 | STA4-MS016-STK-NCR-003 |  | MS | Stockiest Flange |  |  | 2025-06-23 | 2025-09-23 | 2025-08-04 | For the following flanges, the tensile tests carried out are slightly below the minimum required tensile values as required by the SA 105: N10 - BFW Pumps Recycle WNRF 4" 600# SCH.160 SA105 (Heat 23-39573) N05 - BFW Pumps suction WNRF 8" 300# SCH.80 SA105 (Heat BK1427) N6 Steam Inlet WNRF 16" 150# SCH30 SA105 (Heat J6AV22)
기계.설비 | 일반기계_고정.회전 | 자재불량 | 시험.검사 | 절차서, 지침서의 미준수 | 현상태사용 | STA4 | 현대건설 | STA4-MR003-HHI-NCR-001 |  | MR | impeller |  |  | 2025-06-26 | 2025-09-15 | 2025-07-21 | Dimensional changes following overspeed test were out with the allowed limit - 1st stage impeller of compressor tag 407-K-0001-B & C - Allowed limit: 0.038mm 407-K-0001-2 : Before - 382.826 / After - 382.875 / Deformation - 0.049mm 407-K-1001-3 : Before - 382.819 / After - 382.866 / Deformation - 0.047mm
전기 | 급.배전설비 | 미시공 | 자재 | 기타 | 재작업 | STA4 | 현대건설 | STA4-EL001-HIT-NCR-005 |  | EL | 9 bays |  |  | 2025-07-08 | 2026-01-04 | 2026-01-30 | conditional IRC with NCR (open punch items)
전기 | 기타 | 미시공 | 자재 | 기타 | 재작업 | STA4 | 현대건설 | STA4-MR001-HTC-ABB-NCR-002 |  | MR | Main Motor for Centrifugal Compressor (API617) |  |  | 2025-08-26 | 2025-11-30 | 2025-11-11 | Two open punches are open till final completion of factory inspection at the manufacturer’s factory. Those will be closed at Main-Vendor’s factory prior to final shipment of Main pump to site.
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 폐기 | STA4 | 현대건설 | STA4-CI005-VAL-NCR-001 |  | CI | On-Off Valve (Ball) |  |  | 2025-09-01 | 2025-10-30 | 2025-10-23 | The body joint nuts are of wrong size, not M20 Hexnuts for tag 404-ZV-10001 but apparently ¾ UNC. These must be replaced and tested.
기계.설비 | 일반기계_고정.회전 | 손상 | 자재 | 품목의 결함, 손상 및 제작불량 | 수리 | STA4 | 현대건설 | STA4-MS004-XIN-NCR-002 |  | MS | Filter |  |  | 2025-08-28 | 2025-09-30 | 2025-09-22 | During the inspection stage, a dent was identified on the shell as per the below picture. The dent has dimensions of approximately 160 mm in length, 130 mm in width, and a maximum depth of 5 mm. This defect was found after the hydrostatic test and before the blasting operation.
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 현상태사용 | STA4 | 현대건설 | STA4-MR010-OPT-NCR-001 |  | MR | Spent Caustic Transfer Pump 420-G-0044-A/B |  |  | 2025-08-29 | 2026-03-31 |  | Performance test was carried out as per STA4-MR010-OPT-IN-004 rev01, tag 420-G-0044-A, Spent Caustic Transfer Pump. After review performance test reports, it was found that power consumption was higher that required value.
전기 | 제어설비 | 미시공 | 자재 | 기타 | 재작업 | STA4 | 현대건설 | STA4-EL012-SEL2-NCR-001 |  | EL | PMS |  |  | 2025-10-15 | 2026-04-16 | 2026-02-12 | With Company approval, a conditional IRC with NCR has been issued for the item described herein. Refer to the punch List_ STA4-EL-012-SEL-PMS-PL-001 (PMS) dated 05 OCT 2025. This NCR will be used to track the resolution of punch list item at site till final closure. (punch item #4)
기계.설비 | 기타 | 손상 | 자재 | 품목의 결함, 손상 및 제작불량 | 재작업 | STA4 | 현대건설 | STA4-PI016-AMP-NCR-001 |  | PI | VALVE; GATE; WEDGE; 26 INCH AND UP; FLANGED |  |  | 2025-10-18 | 2025-10-31 | 2025-12-01 | Damages/ defects in RF detected. As general comment: roughness not uniform: 1) Isolated mechanical damages have been by grinding/ sand papering, resulting in a smooth/flat surface 2) Localized areas showing not uniform shape (to correspond with roughness 3,2-6,3 Ra)
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 현상태사용 | STA4 | 현대건설 | STA4-MS016-STK-NCR-004 |  | MS | Deaerator |  |  | 2025-10-27 | 2025-12-31 | 2025-12-23 | During dimensional examination it was observed that N18 showed a deviation nozzle location 15mm where a tolerance of ±3 mm is allowed and deviation 1° from parallel plane where a tolerance of ±0.5° The stand-off of this nozzle is 600 mm. This nozzle will be used to install a pressure transmitter
전기 | 제어설비 | 미시공 | 자재 | 기타 | 재작업 | STA4 | 현대건설 | STA4-EL012-SEL2-NCR-002 |  | EL | PMS |  |  | 2025-11-04 | 2026-05-04 | 2026-03-06 | With Company approval, a conditional IRC with NCR has been issued for the item described herein. Refer to the punch List_ STA4-EL-012-SEL-PMS-PL-001 (PMS) dated 05 OCT 2025. This NCR will be used to track the resolution of punch list item at site till final closure. (punch item #4)
기계.설비 | 기타 | 기타 | 시험.검사 | 점검, 및 시험자의 과실 | 재작업 | STA4 | 현대건설 | STA4-PI038-DON-NCR-001 |  | PI | Knife Gate Valve |  |  | 2025-10-13 | 2025-10-31 | 2025-10-30 | During the pressure test, test pressure did not hold, due to leakages on test jig connections.
전기 | 급.배전설비 | 미시공 | 자재 | 기타 | 재작업 | STA4 | 현대건설 | STA4-EL008-AFN-NCR-001 |  | EL | LV SWGR |  |  | 2025-10-22 | 2026-04-20 | 2026-04-16 | According to SA-AMI-000-HDAI-510003_2 (Vendor Inspection Procedure), all punch list items must be cleared before the inspection release. Additionally, as per the Sec. 5.9 of SA-AMI-000-HDAI-340707 (MATERIAL REQUISITION FOR LV SWGR) , Equipment/material shall not be released with punch list items unless approval is obtained from COMPANY Representative. However, considering the site erection situation and punch categories, HDEC has agreed to issue the IRC with outstanding punch list items as attached. This NCR will be used to track the resolution of the punch list items and will be closed upon HDEC’s agreement. 1. A 'partially closed sample & Partially Closed (SITE)' indicates that a full inspection and verification must be carried out upon installation at the site under supervision of ALFANAR. 2. Partially Closed (Documentation)’ refers to closure achieved through documentation updates All as-built documents must reflect the relevant punch items and obtain approval from our design team 3. As the IFAT punch items require SEL's involvement, they will be closed during the SAT stage All aforementioned site activity shall be supported by ALFANAR under get complete close. Attachment 1 : Final punch list - STA4-EL008-AF2-PL-001 (SSG) - STA4-EL008-AF2-PL-002 (SG,ESG) - STA4-EL008-AF2-PL-003 (IFAT with SEL) Attachment 2 : IRC (with condition) , STA4-EL008-AF2-IRC-001
전기 | 급.배전설비 | 미시공 | 자재 | 기타 | 재작업 | STA4 | 현대건설 | STA4-EL009-AFN-NCR-001 |  | EL | LV Controlgear |  |  | 2025-11-02 | 2026-05-01 | 2026-04-30 | According to SA-AMI-000-HDAI-510003_2 (Vendor Inspection Procedure), all punch list items must be cleared before the inspection release. Additionally, as per SA-AMI-000-HDAI-340708, MATERIAL REQUISITION FOR LV Controlgear(MCC), equipment shall not be released with punch list items unless approval is obtained from COMPANY Representative. With Company approval considering the site urgency and punch categories, a conditional IRC with NCR has been issued for the item described herein. Please refer to the following three categories. 1. ”Partially Closed (SAMPLE)” indicates that a full inspection and verification must be carried out upon installation at the site under supervision of ALFANAR. 2. “Partially Closed (SITE)” indicates that a full inspection and verification must be carried out upon installation at the site under supervision of ALFANAR. 3. “Partially Closed (Documentation)”’ indicates that drawing and documentation must be updated as asbuilt. 4. As the IFAT punch items require SEL's involvement and SEL proposed to update and rectify them at site during the SAT stage This NCR will be used to track the resolution of the punch list items at site till final closure. Attachment; - Att.1 STA4-EL009-AF3-PL-001 FAT Punch list - Att.2 STA4-EL008-AF2-PL-003 IFAT Punch (Conducted together with LV SWGR)According to SA-AMI-000-HDAI-510003_2 (Vendor Inspection Procedure), all punch list items must be cleared before the inspection release. Additionally, as per SA-AMI-000-HDAI-340708, MATERIAL REQUISITION FOR LV Controlgear(MCC), equipment shall not be released with punch list items unless approval is obtained from COMPANY Representative. With Company approval considering the site urgency and punch categories, a conditional IRC with NCR has been issued for the item described herein. Please refer to the following three categories. 1. ”Partially Closed (SAMPLE)” indicates that a full inspection and verification must be carried out upon installation at the site under supervision of ALFANAR. 2. “Partially Closed (SITE)” indicates that a full inspection and verification must be carried out upon installation at the site under supervision of ALFANAR. 3. “Partially Closed (Documentation)”’ indicates that drawing and documentation must be updated as asbuilt. 4. As the IFAT punch items require SEL's involvement and SEL proposed to update and rectify them at site during the SAT stage This NCR will be used to track the resolution of the punch list items at site till final closure. Attachment; - Att.1 STA4-EL009-AF3-PL-001 FAT Punch list - Att.2 STA4-EL008-AF2-PL-003 IFAT Punch (Conducted together with LV SWGR)
기계.설비 | 일반기계_고정.회전 | 미시공 | 자재 | 기타 | 재작업 | STA4 | 현대건설 | STA4-MS017-SYC-NCR-001 |  | MS | Air Dryer Package (407-X-2001) |  |  | 2025-11-07 | 2026-04-30 |  | Factory Acceptance Test (FAT) had been done at the skid-mounted unit manufacturer’s facility to ensure that the unit meets all functional and operational requirements as described in the project specifications. However, the following punch couldn’t be closed due to material issue. 1. Punch No. 38-2 from PL (STA4-MS017-SYC-PL-002) -. 4 leak points were founded (407-PG-05015, 05018, 05025, 05028 drain valve 1/2”) 2. Punch No. 15 from PL (STA4-MS017-SYC-PL-003) -. Twenty percent (20%) spare take off fittings and block valves shall be installed on the branch header and provided with low point drain valve. Currently, there were no drain valve and spare valves.
전기 | 제어설비 | 미시공 | 자재 | 기타 | 재작업 | STA4 | 현대건설 | STA4-EL012-SEL1-NCR-001 |  | EL | SS2, SS21, SS22 |  |  | 2025-11-11 | 2026-02-10 | 2026-03-09 | With Company approval considering the site urgency and punch categories, a conditional IRC with NCR has been issued for open punch points as attached. This NCR will be used to track the resolution of the punch list items at site till final closure. Attachment; STA4-EL012-SEL1-PL-001 FAT Punch list
전기 | 급.배전설비 | 미시공 | 자재 | 기타 | 재작업 | STA4 | 현대건설 | STA4-EL007-AFN-NCR-001 |  | EL | HV Switchgear |  |  | 2025-12-19 | 2026-06-17 |  | Description (with Nature of Non-Conformance / Attach sketch and Photograph if applicable) According to SA-AMI-000-HDAI-510003_2 (Vendor Inspection Procedure), all punch list items must be cleared before the inspection release. Additionally, as per the Sec. 5.9 of SA-AMI-000-HDAI-340706 (MATERIAL REQUISITION FOR HV SWGR) , Equipment/material shall not be released with punch list items unless approval is obtained from COMPANY Representative. However, considering the site erection situation and punch categories, HDEC has agreed to issue the IRC with outstanding punch list items as attached. This NCR will be used to track the resolution of the punch list items and will be closed upon HDEC’s agreement. 1. Partially Closed (SITE)' indicates that a full inspection and verification must be carried out upon installation at the site under supervision of ALFANAR. 2. Partially Closed (Documentation)’ indicates that document review for test report, certificate etc. Also, All as-built documents must reflect the relevant punch items and obtain approval from HDEC design team 3. CPY review’ It is under Company review, thus any necessary corrections will be implemented later on site. Based on the results of the CPY review, ALFANAR’s additional actions will be determined. All aforementioned site activity shall be supported by ALFANAR under get complete close. Attachment 1 : Final punch list - STA4-EL007-AF1-PL-001 (Open Punch) - STA4-EL007-AF1-PL-001 (Total) Attachment 2 : IRC (with condition) - STA4-EL007-AF1-IRC-001
기계.설비 | 저장탱크 | 기타 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 수리 | STA4 | 현대건설 | STA4-MS011-MHS-NCR-002 |  | MS | Shell plate |  |  | 2025-11-11 | 2025-11-30 | 2025-12-18 | During surveillance on 11th Oct 2025, it was observed that the welder for part mark SP1-02A TK488 (405-T-0003) was welding over a pitted area without any approved procedure or prior approval. Dwg Ref: SA-AMl-405-4MHS-101037 Sheet 03 of 06 Rev.02 & Refer attached Annexure-1
기계.설비 | 저장탱크 | 기타 | 시험.검사 | 검사, 시험의 미시행 또는 미흡 | 재작업 | STA4 | 현대건설 | STA4-MS011-MHS-NCR-003 |  | MS | Aluminum dome roof |  |  | 2025-12-18 | 2026-03-15 | 2026-03-04 | For the aluminum dome roof (Inspection Level-3), the material was dispatched to site without prior submission and approval of the applicable ITP and required inspection documents, which is non-compliant with the project quality requirements.
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 현상태사용 | STA4 | 현대건설 | STA4-MR010-OPT-NCR-002 |  | MR | Spent Caustic Transfer Pump 420-G-0044-A/B |  |  | 2025-12-04 | 2026-04-30 |  | For high power consumption, waiver request was submitted for CPY approval. CTR would like to deliver sealless pumps to site conditionally with this open punch.
전기 | 제어설비 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 현상태사용 | STA4 | 현대건설 | STA4-CI001-EME-NCR-001 |  | CI | PDC(Power Dst.) |  |  | 2026-01-20 | 2026-07-19 |  | According to SA-AMI-000-HDAI-510003_2 (Vendor Inspection Procedure), all punch list items must be cleared before the inspection release. Additionally, as per SA-AMI-000-HDAI-353101, MATERIAL REQUISITION FOR PCS equipment shall not be released with punch list items unless approval is obtained from COMPANY Representative. A conditional IRC has been issued for the 7(seven) open punch items which require to be as built. Drawing update can be finalized at the time of final shipment of the rest batches.
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 서류의 결함, 미비 | 현상태사용 | STA4 | 현대건설 | STA4-MS020-ZE1-MO-NCR-001 |  | MS | Incinerator Chamber & Stack |  |  | 2026-01-14 | 2026-04-12 | 2026-01-29 | Before issuance IRC, pending drawing which are not approved by CPY were found. These drawings were approved by CTR only. CTR would like to deliver incinerator chamber & stack to site conditionally with this open punch.
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 현상태사용 | STA4 | 현대건설 | STA4-MS016-STK-NCR-005 |  | MS | Saddle of Deaerator |  |  | 2026-01-22 | 2026-04-22 | 2026-02-28 | During final painting inspection, inspector found non-conformance final coating color for saddle between approved procedure (RAL 7042) and actual (RAL 7032).
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 재작업 | STA4 | 현대건설 | STA4-MS023-KES-SMF-NCR-001 |  | MS | Separator vessel for flare gas recovery package (430-D-0102) |  |  | 2026-02-19 | 2026-04-30 | 2026-04-21 | During the Final Visual and Dimensional Inspection (FVDI) of the Separator Vessel, Equipment Tag No. 430-D-0102, carried out in accordance with the approved ITP Stage No. 20, both the internal and external areas of the vessel were inspected. It was observed that the external dish head nozzles, Item Nos. L3A, L3B, L5A, and L5B, do not conform to the requirements specified in the approved detailed fabrication drawing No. SA-AMI-430-4KES-101007_F. As per the approved drawing, the required dimension from the dish center to each nozzle is 610 mm. But the actual measured dimension is 605 mm, resulting in a deviation of 5 mm. This deviation exceeds the specified tolerance and requires root cause and corrective action.
전기 | 제어설비 | 미시공 | 자재 | 기타 | 재작업 | STA4 | 현대건설 | STA4-EL012-SEL1-NCR-002 |  | EL | SS2, SS21, SS22 |  |  | 2026-03-26 | 2026-06-24 |  | With Company approval considering the site urgency and punch categories, a conditional IRC with NCR has been issued for open punch points as attached. This NCR will be used to track the resolution of the punch list items at site till final closure. Attachment; STA4-EL012-SEL1-PL-002 FAT Punch list
전기 | 계장제어 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 현상태사용 | STA4 | 현대건설 | STA4-CI001-EME-NCR-002 |  | CI | PCS overall |  |  | 2026-03-06 | 2026-06-05 |  | According to SA-AMI-000-HDAI-510003_2 (Vendor Inspection Procedure), all punch list items must be cleared before the inspection release. Additionally, as per SA-AMI-000-HDAI-353101, MATERIAL REQUISITION FOR PCS equipment shall not be released with punch list items unless approval is obtained from COMPANY Representative. This NCR is issued based on the punch list items identified during the Final Wrap-Up Meeting held on February 9. 2026 All punch items will be managed through Test Studio (Emerson’s system) A final wrap-up will be again conducted at the time of SAT completion, and any remaining follow-up items will be transferred to ICAPS for further tracking and closure.
기계.설비 | 기타 | 기타 | 시험.검사 | 검사, 시험의 미시행 또는 미흡 | 기타 | STA4 | 현대건설 | STA4-CI005-VAL-NCR-002 |  | CI | On-Off Valve (Ball) |  |  | 2026-04-08 | 2026-05-31 |  | According to the TBE and the valve datasheet (instrument specification sheets), the standard code for all Trunnion Ball Valves shall be API 6D. However, the vendor has not inspected the valves in accordance with API 6D. Eleven of these valves require re-testing because the high-pressure seat test / DBB test was omitted. Total Q’ty: Trunnion Type Ball Valve (27 pcs)
기타 | 기타 | 기타 | 기타. | 기타 | 현상태사용 | STA4 | 발주처 | AMIRAL-P4-NCR-0376 |  | 공통 |  |  |  | 2026-01-13 | 2026-04-13 | 2026-03-29 | CTR-INCR for Procurement (STA4-NCR-OOK-QM-006) is escalated to company (AMIRAL) NCR, for not completing the proposed corrective action (CA) within the specified ECD (in line with "NON-CONFORMANCE MANAGEMENT PROCEDURE" (SA-AMl-OOO-EQAC-000003) STA4-NCR-OOK-QM-006: It is observed that 257 VENDOR documents have not been submitted for over 45 days since they were received from the company. This is clear violation of SA-AMI-OOO-HDAI-110002, para 5.9.1. Delayed document submission will have a considerable impact in the manufacturing, inspection and testing activities at vendor shops and subsequent delivery impact. Contractor to comply with the requirements and implement both corrective and preventive measures. A root cause analysis should also be conducted to prevent the recurrence of such non-compliance in future projects.
전기 | 기타 | 기타 | 설계 | 기술검토 미비, 기술시방서의 부정확 | 현상태사용 | STA4 | 발주처 | AMIRAL-P4-NCR-0391 |  | CI |  |  |  | 2026-02-05 | 2026-05-05 |  | This Company NCR is issued to Contractor HYUNDAI (PKG-4) for Fiber Optic (F.O.) cables for the AMIRAL Project supplied by the approved vendor MIDDLE EAST FIBER CABLE MANUFACTURING COMPANY (MEFC), due to failure to comply with the contractual and technical requirements of AMIMS-J-4913, Clause 6.1.3, and AMIITP-J-347600 which mandates the Oil-resistant test for F.O. cables. MEFC is obligated to conduct the Oil-resistant test on the final F.O. cable and invite Company for test witnessing (Inspection Level 2), and provide a valid, project-specific test certificate. However, to date, Contractor/MEFC failed to perform the required oil test and has only submitted an outdated certificate from a sub-supplier (SHAKUN Polymers) applicable solely to sheath material, which is not acceptable and does not demonstrate compliance with AMIRAL requirements. The Contractor/Vendor is therefore required to immediately conduct the oil test in accordance with the applicable specifications and approved waivers, arrange Company witnessing. Contractor Hyundai, through the Project Management Team (PMT), is hereby instructed to investigate and determine the root cause of this nonconformity and to develop, submit, and implement effective corrective and preventive actions.
기타 | 기타 | 기타 | 기타. | 기타 | 현상태사용 | SAC2 | 현대건설 | NCR-OOK-PI-0001 |  | PI |  |  |  | 2024-11-01 | 2024-12-13 | 2024-11-14 | Contractor found that piping PO for Flange-3 from ULMA under MR No. JUS&ICS2-PI-MR-0031 has singed on July 2, 2024 before obtaining the No Objection Letter from Company as approval was given in July 8, 2024.
기타 | 기타 | 기타 | 기타. | 기타 | 현상태사용 | SAC2 | 현대건설 | NCR-OOK-PI-0002 |  | PI |  |  |  | 2024-12-24 | 2025-02-07 | 2025-02-13 | Contractor found that 'Change Order(P.O Addendum)' for Piping Materials were submitted to company later than the Contractural Due date (10 Working days)
기타 | 기타 | 기타 | 기타. | 기타 | 현상태사용 | SAC2 | 현대건설 | NCR-OOK-PI-0003 |  | PI |  |  |  | 2025-01-06 | 2025-01-24 | 2025-01-24 | Regarding the process of bid equalization for pipe support, IK Manufacturer obtained confidential bid equalization documents which the information should not be shared with the bidders.
기타 | 기타 | 기타 | 기타. | 기타 | 현상태사용 | SAC2 | 현대건설 | NCR-OOK-CI-0001 |  | CI |  |  |  | 2025-01-08 | 2025-03-14 | 2025-03-13 | Contractor found that Instrumentation PO Addendum No.1 was issued without Technical Bid Evalluation revision. 1. Item : Control Valve (General & Non-General) 2. Original PO No. : JUS&ICS2-CI-PO-0015 & 0016 (Signed on 5th Sep, 2024) 3. PO Addendum No.1 Issue Date : 12th Dec, 2024 (for Oxygen service) 4. Technical Bid Evalluation No. : JUS&ICS2-CI-TBE-0015 & 0016 (Issued on 12th Nov, 2024) 5. TBE Rev.00 was issued with the ARAMCO's comments on the Oxygen Valve still pending resolution
기계.설비 | 기타 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 현상태사용 | SAC2 | 현대건설 | JUS&ICS2-PI-PO-0022-1-NCR-001 |  | PI |  |  |  | 2025-01-17 | 2025-03-31 | 2025-02-13 | Contractor found that The raw material used to Manufacture the wrought fitting exceeded the sulfur content limit specified in the project requirements. 1. Vendor Name : ERNE Fitting (MFR # 30005383) 2. Violation Details for Sulfur Contents (%) * Requirement in 02-SAMSS-005 : Shall not exceed 0.003% * Actual Contents in MTC : Below table
기타 | 기타 | 기타 | 기타. | 기타 | 재작업 | SAC2 | 현대건설 | JUS&ICS2-CI-PO-0007-NCR-001 |  | CI |  |  |  | 2025-09-04 | 2025-12-02 | 2025-11-12 | Tag no. : 861-B-6106, 862-B-6206A, 869-400-B-6906, 869-500-B-6906 (Analyzer Shelter) It was submitted that In-Process inspection would be carried out at an unapproved location. 1. Notified location : No. 282, Qingwei Road, Qingcun Town, Fengxian District, Shanghai (Shanghai Qianyi Industrial Co., Ltd) 2. Approved location : No. 4528, Kangxin Road, Shanghai (ABB ENGINEERING (SHANGHAI) LTD - MFR no_30005668)
기계.설비 | 기타 | 기타 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 수리 | SAC2 | 현대건설 | JUS&ICS2-PI-PO-0007-NCR-001 |  | PI |  |  |  | 2025-09-25 | 2025-12-23 | 2025-12-15 | IL No. : 107000292139, Cladtek Arabia KSA, Item: Clad Piping, Item No.: Line Item No. 390 (Ident Code: M361761213 / Vendor Internal Code : CA98-WO-039-00004 ), Item Description: CS API-5L-BM-PSL2 SAWL w/100% RT BE B36.10M N06625 CLADDING Sour 68 inch, 1.125". During witnessing of repair welding after CRA at Cladtek, using Approved WPS CA098-WPS-001I, the following observations/non-conformities were noted: 1. Discrepancy with the WPS (1) Welding Position (QW-405): The WPS specifies that repair welding shall be performed in the flat (1G) position by rotating the pipe. However, the welder performed welding in a fixed 5G position, carrying out repairs from inside the pipe in multiple orientations (overhead, vertical, and horizontal). (2) Amperage Range (QW-409): The WPS specifies a maximum of 140 Amps, whereas the welder used 151 Amps. 2. CRA Weld Defects: On the same pipe (CA98-WO-039-00004), after completion of CRA welding, several unusual visual defects/Pin holes and uncladded areas were observed (see the attached images).
기타 | 기타 | 기타 | 기타. | 기타 | 현상태사용 | SAC2 | 발주처 | 500021221 |  | CI |  |  |  | 2025-09-16 | 2025-12-15 | 2025-12-11 | It has been identified that instrument cable tray clamps supplied by ABAHSAIN COPE (ID 30005833) under PO JUS-ICS2-CI-PO-0042 do not comply with the approved project specifications, NEMA VE 1 and 2, and design drawings (VD-CI0042-102 Rev. C). The clamps were suppl ied with a welded construction, whereas a one-piece design was specified. In addition, Contractor did not provide cable tray’s inst a llation and erection instruction by manufacturer which is key deliverable part of NMR-603. The contractor failed to report these d is crepancies through INCRs and accepted the release of material despite non-conformities, which violates Schedule Q para. 7.5.3, S A E P-1151 10.2, and the contractor’s Quality Plan 8.7.3 (JUS-ICS2-PM-PD-6001 Rev.00). As per SAEP-381 5.2, these are classified a s a m oderate violations and therefore Company NCR has been issued to investigate the root causes and implement corrective actions t o prev ent recurrence.
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 재작업 | SHN1 | 현대건설 | SHN1-2110-2001-002-KHA-NCR-0001 | MS-2110-2001-002 | MS | Radiant Module (Steel structure) | JNK Heaters | KHAN Plant (KIC) | 2023-11-20 | 2024-02-29 | 2024-04-02 | It’s observed that painting color for steel structure is wrongly applied with Blue gray instead of gray (Munsell No. N-6) and mosf of them have been installed for back to back module (H-211103 & 04) at KHAN Plant
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 현상태사용 | SHN1 | 현대건설 | SHN1-2110-2001-001-ARV-NCR-0001 | MS-2110-2001-001 | MS | Transfer Line Exchanger | Lummus | Arvos | 2023-12-01 | 2024-02-29 | 2024-04-04 | During inspection before PWHT, the dimension “F” as per dimensional check found out of tolearance by 2mm
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 폐기 | SHN1 | 현대건설 | SHN1-2110-2001-001-ENG-NCR-0001 | MS-2110-2001-001 | MS | Radiant Coil (Gas Heater) | Lummus | Engemasa | 2023-12-20 | 2024-03-05 | 2024-03-07 | It was found that items 222014 and 222015, SMLs Pipe OD 60.3 x 3.9 x 604 & 814 mm, were thicker than specified, revealing to be schedule 80 instead of schedule 40 as requested on material list of S-Oil Shaheen Project. 222014 (ASTM A312 TP347H) : 204 pcs - 192 + 12 (spares) pcs 222015 (ASTM A312 TP347H) : 204 pcs - 192 + 12 (spares) pcs
기계.설비 | 일반기계_고정.회전 | 기타 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 재작업 | SHN1 | 현대건설 | SHN1-2110-2001-002-IPL-NCR-0001 | MS-2110-2001-002 | MS | Convection Module & GTE Duct | JNK Heaters | I-Plant | 2024-01-08 | 2024-02-29 | 2024-05-09 | It’s observed that Intermediate heat treatment have not been applied on weld joint between manifold pipe (SA335 P91) to weldolet (SA335 F91) as per ASME SEC.I PW 38.8 - Item : H211101 ~ H211104 / USSH Outlet Pipe
기계.설비 | 일반기계_고정.회전 | 자재불량 | 설계 | 설계, 도면의 부정확 | 재작업 | SHN1 | 현대건설 | SHN1-2110-2001-002-IPL-NCR-0002 | MS-2110-2001-002 | MS | Convection Module & GTE Duct | JNK Heaters | I-Plant | 2024-03-15 | 2024-06-12 | 2024-05-31 | During material receiving inspection and pre-assembly, it’s observed that the strainer on cross over can’t be assembled because thickness of intermediate wall on concentric reducer (Item No. 123506 & 223506 / O.D 273.1 x 15.08 & O.D 219.1 x 8.18) where strainer support (Item No. 123508 & 223508) to be inserted is thick and various. - Reducer - Q’ty : 80 ea (8 x 10 Heaters) / Heat No. : I69722 - Strainer - Q’ty : 80 ea (8 x 10 Heaters) / Heat No. : E71K
기계.설비 | 일반기계_고정.회전 | 기타 | 시험.검사 | 절차서, 지침서의 미준수 | 현상태사용 | SHN1 | 현대건설 | SHN1-2110-2001-002-KHA-NCR-0002 | MS-2110-2001-002 | MS | Radiant Module | JNK Heaters | KHAN Plant | 2024-03-22 | 2024-06-21 | 2024-03-27 | During document review on refractory lining (castable) for peep door for H-211104, it’s observed that water and casing temperature were lower than spec. requirement (SHAHEEN-COM-ML-SPC-0010 Para. 5.3.10) as following;
기계.설비 | 일반기계_고정.회전 | 균열 | 자재 | 품목의 결함, 손상 및 제작불량 | 재작업 | SHN1 | 현대건설 | SHN1-2110-2001-002-IPL-NCR-0003 | MS-2110-2001-002 | MS | Convection Module & GTE Duct | JNK Heaters | I-Plant | 2024-05-23 | 2024-12-27 | 2024-11-21 | During material receiving inspection and pre-assembly for convection module (CM-01 for 8 Liquid Heaters), it’s observed that 1. the clearance between ITS (Part No. 131002) and support guide is not designed so that it can’t be assembled 2. the clearance between ITS (Part No. 131002) and support bracket (Part No. 123006) spacing between was designed with 1mm gap. In addition, the cast support brackets were fabricated smaller than the drawing so that ITS can’t be installed. For the detail, please find attached investigation reports describing measuring result.
기계.설비 | 일반기계_고정.회전 | 기타 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 재작업 | SHN1 | 현대건설 | SHN1-2110-2001-002-IPL-NCR-0004 | MS-2110-2001-002 | MS | Convection Module & GTE Duct | JNK Heaters | I-Plant | 2024-05-23 | 2024-12-27 | 2024-12-24 | During material receiving inspection and pre-assembly for convection module (CM-01 for 8 Liquid Heaters), it’s observed that Interference between upper ITS (Part No. 131002) and lower ITS (Part No. 131001) is made against design value with 11mm, because the supplied ITS is thicker than drawing, also surface condition is irregular and bent outward. For the detail, please find attached investigation reports describing measuring result.
기타 | 기타 | 기타 | 자재 | 미승인 자재 사용 | 현상태사용 | SHN1 | 현대건설 | SHN1-2110-2001-001-JZH-NCR-0001 | MS-2110-2001-001 | MS | Burners | Lummus | John Zink | 2024-07-22 | 2024-11-22 | 2024-11-22 | During receiving inspection, it was found that two(2ea) burners for H-211107 are wrongly fabricated and delivered. 1) External : Lighting port/Pilot/Sight port locations are rotated about 45 degree from the drawing. 2) Internal : Turning vane angle is rotated about 45 degree from the drawing.
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 현상태사용 | SHN1 | 현대건설 | SHN1-2110-2001-002-IPL-NCR-0005 | MS-2110-2001-002 | MS | Convection Module & GTE Duct | JNK Heaters | I-Plant | 2024-10-23 | 2024-11-22 | 2024-11-19 | During castable lining inspection after dry out (visual & hammering inspection), cracks which is out of tolerance are observed at 2 (two) different location as following;
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 현상태사용 | SHN1 | 현대건설 | SHN1-2110-2001-002-IPL-NCR-0006 | MS-2110-2001-002 | MS | Convection Module & GTE Duct | JNK Heaters | I-Plant | 2025-01-08 | 2025-04-06 | 2025-02-21 | It was found that the welder used an tungsten electrode type that is not conformed to the WPS for RT repair works. -WPS : Tungsten Electrode Type - EWTh-2 -Actual use : EWTh-2 + Non identified steel + EWTh-2 -Applicable repair joint no.: H211106 CM-01, LMP #1-C1, #4-C2, Defect is Incomplete Penetration
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 현상태사용 | SHN1 | 현대건설 | SHN1-2000-3012-001-EUR-NCR-0001 | MR-SH1-2000-3012-001 | EL | AD / DC UPS with Battery | Europower | GUTOR | 2025-02-11 | 2025-04-21 | 2025-04-17 | 1. Compared to the quantity of MCCB or other components (TB.Bus-bar, etc…) the PANEL size has been designed too small and component are congested due to the space limit inside the panel. →It causes the limitation of access to each component or major Maintenance part of the Panel. 2. Two Terminal blocks are installed too close to the bottom entrance with no enough clearance secured and it is deemed to causes the limit of access during the site termination and Maintenance
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 현상태사용 | SHN1 | 현대건설 | SHN1-2000-4001-001-YKO-NCR-0001 | MR-SH1-2000-4001-001 | IC | PCS (Process Control System) | Yokogawa Electric Korea | N/A | 2025-01-14 | 2025-05-16 | 2025-04-17 | Fabrication of the Process Control System (PCS) began on August 6, 2024, before the Pre-Inspection Meeting (PIM), which was conducted on December 2, 2024, contrary to project requirements.
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 현상태사용 | SHN1 | 현대건설 | SHN1-2000-3201-001-KDA-NCR-0001 | MR-SH1-2000-3201-001 | EL | Communication System | Kukdong Automation | N/A | 2025-08-01 | 2025-10-31 | 2025-09-30 | The components installed in the listed cabinets for Communication System have been procured from the restricted country; China.
기계.설비 | 일반기계_고정.회전 | 자재불량 | 자재 | 도면, 기술시방서 요건과 상이한 제작 | 현상태사용 | SHN1 | 현대건설 | SHN1-2135-1003-001-DIQ-NCR-0001 | MR-SH1-2135-1003-001 | MR | Cooling Tower | Daeil Aqua | N/A | 2025-08-26 | 2025-11-20 | 2025-09-11 | Fast Ball Oil Pump(Supplied by Graco) / Part No. : BST-77900903 / Tag No. : P-213511(Air operated pump) It was observed that the fast ball oil pump was assembled in a Graco factory in China with global component. Vendor is not possible to present original material mill certificate.

## PQAN
순번 | PQAN No. | PQAN 배포일자 | 연 | 월 | Feedback | 작성자 | 검토자 | 공종 | 프로젝트 | PO No. | NCR No. | Transmittal No. | 제목 | 품목 | 공급업체 | 국가 | 지역 | 발견 시기 | 발견 장소 | 개요 | 원인 | 후속/예방 조치 (권고) | 이미지 URL (Teams)
1 | PQAN-2025-001 | 2025-03-11 | 2025 | 3 | 0 | 장동철 | 유요석 | 배관 | SM12 | PI016 | - | - | 대구경 Lateral Tee 수압 시험 후 변형 | Fabricated Lateral Tee | GAS METAL TECH | 사우디아라비아 | DAMMAM | Hydrostatic Test | Vendor | 대구경 Lateral Tee (84” x 80”, 68” x 54”, 48” x 30” 등)에 대한 수압 시험 후 Heel Side Notch 부분 변형 (Bulging) 발생 | Header – Branch 연결부에 국부적인 과부하 (압력) 발생 (타 구역 대비 수압시험 압력 ↑) 사업주 요건에 따른 수압시험 압력 계산식은 실제 재료의 강도 검증 목적으로 (실제 재료 두께 적용) 90% SMYS (Specified Material Yield Strength)을 고려한 Barlow’s Formula를 적용하기 때문에 계산된 수압시험 압력이 일반적인 계산 방식 (ASME B31.3 / 설계 압력 & 온도에 따른 두께 적용) 대비 높음 |  | https://teams.microsoft.com/l/message/19:KlEVjYWGS-QmxCKqE5H4Ofn-AvSWTK6hz_ErP7aUdvg1@thread.tacv2/1770610954279?tenantId=5fcb0def-a698-40ce-a73a-ea61130c13c6&groupId=80bfa3ae-81fa-4e4e-ba65-7b9c876b82d8&parentMessageId=1770610954279&teamName=P-Quality%20Alert%20Notice%20(PQAN)&channelName=PQAN%20Library&createdTime=1770610954279
2 | PQAN-2025-002 | 2025-04-18 | 2025 | 4 | 0 | 서민 | 유요석 | 회전 | STA4 | MR001 | NCR-STA4-MR001-HTC-ABB-001 | - | Centrifugal Compressor의 Main Motor FAT 중 Trip 발생 | Main Motor for Centrifugal Compressor | ABB Finland | 핀란드 | HELSINKI | Factory Acceptance Test | Sub-Vendor | Motor FAT (Routine & Type Test)를 위한 기동 후 Rated Speed에서 고 진동 및 급격한 Voltage 저하 발생하였고 Load Generator에 의해 Motor 가동 중지됨. 분해 점검 결과, Rotor / Bearing / Labyrinth Seal 손상 확인되어 납기 지연 (재 제작) 발생 | 해당 Motor는 Forced Lubrication System을 통해 Lube Oil이 공급되는 Type으로 Motor 기동 시 Oil Pump 가동이 우선 요구되나 Vendor 시험 운전원의 실수로 Oil Pump 미 가동 상태에서 Motor 기동하였음 (FAT 절차 미준수) |  | https://teams.microsoft.com/l/message/19:KlEVjYWGS-QmxCKqE5H4Ofn-AvSWTK6hz_ErP7aUdvg1@thread.tacv2/1770611042032?tenantId=5fcb0def-a698-40ce-a73a-ea61130c13c6&groupId=80bfa3ae-81fa-4e4e-ba65-7b9c876b82d8&parentMessageId=1770611042032&teamName=P-Quality%20Alert%20Notice%20(PQAN)&channelName=PQAN%20Library&createdTime=1770611042032
3 | PQAN-2025-003 | 2025-05-22 | 2025 | 5 | 0 | 장동철 | 유요석 | 장치 |  |  |  |  | Refractory Lining 균열 | Refractory Lining (Castable) in Fired Equipment | 아이플랜트 | 한국 |  | Final Inspection | Vendor | Fired Heater의 Refractory Lining (Castable) 시공 & Pre-Dry out 후 균열 발생 Incinerator의 현장 설치 후 내부 확인 시 균열 발견 | 제작 ① 내화물의 배합 조건 (대기 / 물 / Mixing 온도, Dry Mixing, 배합 비율 등) 미 준수 ② 내화물 시공 후 잔존 수분 제거 시 (Pre-Dry out) 열팽창/수축 (Heating/Cooling Rate) 관리 미흡 ③ 내화물 작업 후 Full Curing 전, 후속작업을 위한 Lifting에 따른 충격과 Pre-Dry out 시 Castable 타설 부위의 국부하중-처짐 (임시 지지대 수량 및 위치) 관리 미흡 운송 및 설치 (시간이 지남에 따라 미세 균열이 Crack으로 성장) ① 운송 과정의 진동과 하역 시 발생하는 충격, 설치과정에서의 미세한 뒤틀림 (구조적 응력) |  | https://teams.microsoft.com/l/message/19:KlEVjYWGS-QmxCKqE5H4Ofn-AvSWTK6hz_ErP7aUdvg1@thread.tacv2/1770611127739?tenantId=5fcb0def-a698-40ce-a73a-ea61130c13c6&groupId=80bfa3ae-81fa-4e4e-ba65-7b9c876b82d8&parentMessageId=1770611127739&teamName=P-Quality%20Alert%20Notice%20(PQAN)&channelName=PQAN%20Library&createdTime=1770611127739
4 | PQAN-2025-004 | 2025-06-27 | 2025 | 6 | 0 | 서민 | 유요석 | 배관 |  |  |  |  | Coating film 균열/박리 (Cracking/Flaking) | Seal Drum & PTFE Lining Piping spools | Arconi Misa | 스페인 사우디아라비아 |  | After delivery (Site) | Site | Seal Drum 현장 설치 후 Internal Painting의 Flaking 발견됨 PTFE Lined Piping 현장 설치 후 External Painting의 Flaking 발생함 | Surface preparation 불량 ① 기기 Internal 설치 상태에서 (탈착 불가) 도장 작업 수행으로, 표면 처리 (Surface preparation) 위한 Access 확보 애로 (표면 조도 불량) ② 도장작업 前, 표면 cleaning 작업 미흡 (이물질 잔존) Painting Control 미흡 ① Excessive coating film 적용에 따른 도막 Internal stress 증가  크랙 유발 ② 도장 작업 관리 부족 (전체 Spool Inspection Report에 표면처리, 1st, 2nd, 3rd Coat 치수 동일) |  | https://teams.microsoft.com/l/message/19:KlEVjYWGS-QmxCKqE5H4Ofn-AvSWTK6hz_ErP7aUdvg1@thread.tacv2/1770611363619?tenantId=5fcb0def-a698-40ce-a73a-ea61130c13c6&groupId=80bfa3ae-81fa-4e4e-ba65-7b9c876b82d8&parentMessageId=1770611363619&teamName=P-Quality%20Alert%20Notice%20(PQAN)&channelName=PQAN%20Library&createdTime=1770611363619
5 | PQAN-2025-005 | 2025-07-30 | 2025 | 7 | 0 | 이해석 | 유요석 | 장치 |  |  |  |  | Cracking Heater용 Burner 제작/조립 불량 | Hearth Burner (Cracking Heater) | John Zink | 미국 | TULSA | After delivery (Site) | Site | Hearth Burner 내부 S/S Liner Plate 마감 불량으로 Gap 발생 및 내부 보온재 돌출 Hearth Burner와 Burner Tile 조립 시 Burner 상단의 Primary Riser Tip 과 Tile Hole의 Alignment가 허용 공차 (±3mm) 벗어남 | - By Vendor ① 작업자 기량 & 제작 관리 수준 미흡 (균일 하지 않은 제품 품질) : 현장 입고된 480개 Hearth Burner 중 436개 불량판정 & 수리, Primary Riser Tip 1440ea (버너당 3개) 중 297개 불량 & 재 제작 ② 공장 품질 관리 절차 미흡 : 합/부 기준 및 Internal 검사 절차 부재 (Random Sample 검사 Only) - By Contractor ① Trial Fit 수량 불충분 : (Primary Riser Tip과 tile Hole간) alignment 검사 수량 선정 미흡으로 전반적인 품질 수준 판단 기회 상실 → Spec. 요건 (One per each type) 적용 시, 전체 수량 및 검사 중요도 고려 미흡 ② Licensor(Proprietary) 품목에 대한 품질 관리 방안 개선 요구 및 적용 애로 (검사 빈도, 수량 등) |  | https://teams.microsoft.com/l/message/19:KlEVjYWGS-QmxCKqE5H4Ofn-AvSWTK6hz_ErP7aUdvg1@thread.tacv2/1770611467271?tenantId=5fcb0def-a698-40ce-a73a-ea61130c13c6&groupId=80bfa3ae-81fa-4e4e-ba65-7b9c876b82d8&parentMessageId=1770611467271&teamName=P-Quality%20Alert%20Notice%20(PQAN)&channelName=PQAN%20Library&createdTime=1770611467271
6 | PQAN-2025-006 | 2025-08-29 | 2025 | 8 | 0 | 장동철 | 유요석 | 배관 |  |  |  |  | Pipe Inside Surface Imperfection | Carbon Steel Seamless Pipe | Tenaris | 이탈리아 | DALMINE | After delivery (Site) | Site | 현장 입고 후 Pipe 외관 검사 중 내부 표면에서 Expanding Mark, Pit, Heavy Mill scale 등이 발견됨 | Rotary expansion 공정 중 노후화로 마모된 Expanding Mandrel의 형상이 PIPE 내면에 전사되어 자국 형성 Pipe 생산 중 생성된 Mill scale 제거부위에 (후처리 공정) Pit 형상의 고르지 못한 Surface Imperfection 발생 수압 시험 중 떨어진 Scale이 완전 제거되지 않고 Pipe 벽면에 재 부착 & 두꺼운 Scale층 형성 Pipe 생산 중 열처리 (Normalizing, Quenching & Tempering 등)에 사용되는 연소 gas의 Oxygen content, Temperature 범위 & Holding Time 관리 불량 Pipe 생산 후처리 공정 중 내면 Blowing & Grinding 작업 미흡 |  | https://teams.microsoft.com/l/message/19:KlEVjYWGS-QmxCKqE5H4Ofn-AvSWTK6hz_ErP7aUdvg1@thread.tacv2/1770611919162?tenantId=5fcb0def-a698-40ce-a73a-ea61130c13c6&groupId=80bfa3ae-81fa-4e4e-ba65-7b9c876b82d8&parentMessageId=1770611919162&teamName=P-Quality%20Alert%20Notice%20(PQAN)&channelName=PQAN%20Library&createdTime=1770611919162
7 | PQAN-2025-007 | 2025-09-30 | 2025 | 9 | 0 | 장동철 | 유요석 | 전기 |  |  |  |  | 변압기 탱크의 누유 | Power Transformer | 현대일렉트릭 | 한국 |  | After delivery (Site) | Site | 현장 입고 된 변압기의 외부에서 Oil Leak 흔적이 발견됨 | 공장 압력시험 (0.35kgf/㎠, 24시간 Holding) 중에는 Oil Leak 확인되지 않았으나 현장 인도/설치 이후 모래먼지 포집 흔적 등으로 Oil Leak가 발견되었고, 세부 조사 결과 변압기 Tank 제작 시 다수의 용접 결함이 발생한 것으로 확인됨 변압기 탱크 구조 및 형상 제한에 따른 용접 작업 애로 → 결함 발생 형식적인 용접부 외관 검사 및 비파괴 (PT) 수행으로 표면 용접결함 확인 실패 |  | https://teams.microsoft.com/l/message/19:KlEVjYWGS-QmxCKqE5H4Ofn-AvSWTK6hz_ErP7aUdvg1@thread.tacv2/1770612108827?tenantId=5fcb0def-a698-40ce-a73a-ea61130c13c6&groupId=80bfa3ae-81fa-4e4e-ba65-7b9c876b82d8&parentMessageId=1770612108827&teamName=P-Quality%20Alert%20Notice%20(PQAN)&channelName=PQAN%20Library&createdTime=1770612108827
8 | PQAN-2025-008 | 2025-10-28 | 2025 | 10 | 0 | 강태준 | 유요석 | 배관 |  |  |  |  | Casting Valve - Stem Packing 누설 | Casting Valve | Neway | 중국 |  | After delivery (Site) | Site | 모듈샵 수압시험 중 Casting Valve의 Stem Packing 부위에서 지속적으로 누설 발생함 | 프로젝트 Piping Material Spec.은 451℃ ~ 800℃ 고온 조건만 고려하여 Packing 재질 (MICA or Equivalent)을 규정하고 있음 (압력 미 고려) Packing 재질로써 MICA만 적용할 경우, 재질 특성상 고온에는 강하지만 고압에서는 Sealing 성능이 저하될 수 있음 TBE 시 타 업체는 대안으로 MICA + α (적층구조)를 제시하였으나, 본 공급업체는 프로젝트 요구사항에 따른 MICA 단일 재질을 적용하였음 고압 (Class 2500) Valve에서 집중적으로 누설 발생  MICA + Graphite로 설계 변경 추진 |  | https://teams.microsoft.com/l/message/19:KlEVjYWGS-QmxCKqE5H4Ofn-AvSWTK6hz_ErP7aUdvg1@thread.tacv2/1770612202349?tenantId=5fcb0def-a698-40ce-a73a-ea61130c13c6&groupId=80bfa3ae-81fa-4e4e-ba65-7b9c876b82d8&parentMessageId=1770612202349&teamName=P-Quality%20Alert%20Notice%20(PQAN)&channelName=PQAN%20Library&createdTime=1770612202349
9 | PQAN-2025-009 | 2025-11-28 | 2025 | 11 | 0 | 이해석 | 유요석 | 전기 |  |  |  |  | 애관 외관 결함 Bushing Surface Defect | Bushing Insulator (Ceramic Type) | 메인: 삼화컨덴서 제작: 태성 세라믹 조립: 남도전기 | 한국 |  | After delivery (Site) | Site | -Power Capacitor의 현장 자재 인수 검사 중, 애관 표면에 Hole 형태의 외관 결함 발견됨 -Power Transformer의 현장 자재 인수 검사 중, 애관 표면에 Crack 발견됨 | -Ceramic 애관 제작은 수작업으로 이뤄지며 (도자기 제작과 유사), 작업자 숙련도에 따라 제품 품질 상이 -애관 제작 관련 PJT Spec. / Code 요건이 계약에 반영되어 있지 않고 Vendor 자체 육안 검사(형식적) 외에 품질관리 요건 미적용 (KS 3801 / 3802, IEC 60137 등 관련 Code 있으나 전기 Item의 Sub-sub component로 품질 관리 대상에서 제외됨) -애관 설치 시, Over torque 적용 / Bolt 체결 순서 미 준수 / Clamp 모서리 Notch에 애관이 눌리며 Crack 발생 |  | https://teams.microsoft.com/l/message/19:KlEVjYWGS-QmxCKqE5H4Ofn-AvSWTK6hz_ErP7aUdvg1@thread.tacv2/1770612284366?tenantId=5fcb0def-a698-40ce-a73a-ea61130c13c6&groupId=80bfa3ae-81fa-4e4e-ba65-7b9c876b82d8&parentMessageId=1770612284366&teamName=P-Quality%20Alert%20Notice%20(PQAN)&channelName=PQAN%20Library&createdTime=1770612284366
10 | PQAN-2025-010 | 2025-12-30 | 2025 | 12 | 1 | 나광조 | 유요석 | 장치 |  |  |  |  | 열교환기 내부의 수압시험 잔류수/응축수 | 열교환기 | 중국: Dongfang 미국: Chromalox 한국: | 한국/중국/미국 |  | After delivery (Site) | Site | -열교환기의 현장 자재 인수 검사 중, 기기 내부에서 수압시험 잔류수 또는 부적절한 N2 Purging에 따른 응축수 발견됨 -수압시험 잔류수 / 응축수의 장기 노출에 따른 Shell / Tube side에 Rust contamination 발생함 | -기기 configuration을 고려한 Drain 절차 미수립으로 (Floating Head 하단과 tubesheet의 높이차 미고려) 수압시험 잔류수 잔존 -Drain & Dry out 후 부적절한 검사 수행 (Borescope 등을 활용한 기기 내부 잔류수 확인 절차 미적용) -수압시험 시 녹 발생 방지용 Inhibitor 미적용 -부적절한 N2 Purging 수행 (N2 Purging 반복 : Air → N2 치환) 및 기기 내부 이슬점 온도 미확인 |  | https://teams.microsoft.com/l/message/19:KlEVjYWGS-QmxCKqE5H4Ofn-AvSWTK6hz_ErP7aUdvg1@thread.tacv2/1770612400616?tenantId=5fcb0def-a698-40ce-a73a-ea61130c13c6&groupId=80bfa3ae-81fa-4e4e-ba65-7b9c876b82d8&parentMessageId=1770612400616&teamName=P-Quality%20Alert%20Notice%20(PQAN)&channelName=PQAN%20Library&createdTime=1770612400616
11 | PQAN-2026-001 | 2026-01-28 | 2026 | 1 | 0 | 정진우 | 유요석 | 장치 |  |  |  |  | 도장 색상 불일치 | Deaerator | Stork | 네덜란드 |  | Painting Inspection | Vendor | 도장 검사 중 일부 기자재의 Final 도장 색상이 요구 사항과 상이함이 발견됨 Deaerator Saddle Part (요구사항: RAL 7042 / 실제적용: RAL 7032) Power Distribution Board (요구사항: RAL 7042 / 실제적용: RAL 7035) | -도장 제조사 / International의 Silicone Acrylic 계열 도장재의 가용 색상(RAL 7042) 확인 없이 절차서 작성, 유사 색상(RAL7032) 임의 적용 -도장 사양 및 도장절차서 상에 명기되어 있는 색상 확인 절차 누락 | -도장절차서 제출 시, 제조사 Datasheet + 색상 가용 확인 Letter 검토 -검사 시, RAL-Munsell Code 활용 의무화 (MR 반영) | https://teams.microsoft.com/l/message/19:KlEVjYWGS-QmxCKqE5H4Ofn-AvSWTK6hz_ErP7aUdvg1@thread.tacv2/1770612649076?tenantId=5fcb0def-a698-40ce-a73a-ea61130c13c6&groupId=80bfa3ae-81fa-4e4e-ba65-7b9c876b82d8&parentMessageId=1770612649076&teamName=P-Quality%20Alert%20Notice%20(PQAN)&channelName=PQAN%20Library&createdTime=1770612649076
12 | PQAN-2026-001 | 2026-01-28 | 2026 | 1 | 0 | 강인묵 | 유요석 | 전기 |  |  |  |  | 도장 색상 불일치 | Power Distribution Board | Al-Fanar | 사우디아라비아 |  | Painting Inspection | Vendor | 도장 검사 중 일부 기자재의 Final 도장 색상이 요구 사항과 상이함이 발견됨 Deaerator Saddle Part (요구사항: RAL 7042 / 실제적용: RAL 7032) Power Distribution Board (요구사항: RAL 7042 / 실제적용: RAL 7035) | -도장 제조사 / International의 Silicone Acrylic 계열 도장재의 가용 색상(RAL 7042) 확인 없이 절차서 작성, 유사 색상(RAL7032) 임의 적용 -도장 사양 및 도장절차서 상에 명기되어 있는 색상 확인 절차 누락 | -도장절차서 제출 시, 제조사 Datasheet + 색상 가용 확인 Letter 검토 -검사 시, RAL-Munsell Code 활용 의무화 (MR 반영) | https://teams.microsoft.com/l/message/19:KlEVjYWGS-QmxCKqE5H4Ofn-AvSWTK6hz_ErP7aUdvg1@thread.tacv2/1770612649076?tenantId=5fcb0def-a698-40ce-a73a-ea61130c13c6&groupId=80bfa3ae-81fa-4e4e-ba65-7b9c876b82d8&parentMessageId=1770612649076&teamName=P-Quality%20Alert%20Notice%20(PQAN)&channelName=PQAN%20Library&createdTime=1770612649076
13 | PQAN-2026-002 | 2026-02-25 | 2026 | 2 | 0 | 서민 | 유요석 | 회전 |  |  |  |  | Pump Casing 주조결함 (1. Pump Casing Casting 결함) | Centrifugal Pump | Flowserve / Peekay Steel | 인도 |  | Visual Inspection | Vendor | Super Duplex Stainless Steel (SDSS)로 제작된 Pump Casing의 Casting 결함에 따른 Pump 제작 지연 및 시운전 중 Leak 발생 | -Casting 결함 – Porosity, Shrinkage, Crack 등 - Casting 전, Pump Model별 Pattern 및 주조 관리 역량 검증 미흡 | -NORSOK M-650 Certificate 등 Casting Foundry 제조 역량 사전 검증 -신규 Pattern에 대해 주물 유동, 응고 해석 등 주조 관리 방안 시뮬레이션 검증 -SDSS 용접 보수 시, Post-Weld Heat Treatment 적용 | https://teams.microsoft.com/l/message/19:KlEVjYWGS-QmxCKqE5H4Ofn-AvSWTK6hz_ErP7aUdvg1@thread.tacv2/1771985386124?tenantId=5fcb0def-a698-40ce-a73a-ea61130c13c6&groupId=80bfa3ae-81fa-4e4e-ba65-7b9c876b82d8&parentMessageId=1771985386124&teamName=P-Quality%20Alert%20Notice%20(PQAN)&channelName=PQAN%20Library&createdTime=1771985386124
14 | PQAN-2026-002 | 2026-02-25 | 2026 | 2 | 0 | 서민 | 유요석 | 회전 |  |  |  |  | Pump Casing 주조결함 (2. Casting Cleaning window 관리) | Centrifugal Pump | Sulzer Saudi / Ultimate Alloy | 사우디아라비아 |  | After delivery (Site) | Site | Super Duplex Stainless Steel (SDSS)로 제작된 Pump Casing의 Casting 결함에 따른 Pump 제작 지연 및 시운전 중 Leak 발생 | -Cleaning Window 임의 적용 - Casting 단계에서 Cleaning Window 적용 여부 미확인 | -제작 전, Casing에 Cleaning Window 적용 여부 확인 -Cleaning Window 적용 시, Window Closing을 위한 WPS/PQR, Welding Map 검토 및 용접부 건전성 확인 (UT / RT) | https://teams.microsoft.com/l/message/19:KlEVjYWGS-QmxCKqE5H4Ofn-AvSWTK6hz_ErP7aUdvg1@thread.tacv2/1771985386124?tenantId=5fcb0def-a698-40ce-a73a-ea61130c13c6&groupId=80bfa3ae-81fa-4e4e-ba65-7b9c876b82d8&parentMessageId=1771985386124&teamName=P-Quality%20Alert%20Notice%20(PQAN)&channelName=PQAN%20Library&createdTime=1771985386124
15 | PQAN-2026-003 | 2026-03-23 | 2026 | 3 | 0 | 강태준 | 유요석 | 배관 |  |  |  |  | Oxygen Service Valve의 Cleanliness 요건 불만족(EIGA 33) - 포장손상 | Forged Valve (Oxygen Servie) | OMB | 이탈리아 |  | After delivery (Site) | Site | Oxygen Valve에 대한 현장 자재인수검사 중 포장 손상, 밀봉 손상, 표면 오염이 발견되었고, 이는 EIGA Doc 33/18에 따라 확보한 Cleanliness의 훼손을 의미함 ※ EIGA Doc 33/18, Para. 10: Clean Room에서 Cleanliness 검사 완료 직후 오염 방지를 위한 밀봉 작업이 이루어져야 함 | Cleanliness Requirements를 고려하지 않은 Packing Method 적용 - 개별 Seal Packing 손상 방지를 위한 Wooden Box – Valve 간 보호조치 미흡 - Valve 간 충돌 방지를 위한 보호조치 및 충분한 이격거리 미확보 (밀집 포장) Valve 외부 표면 오염 - Seal Packing 손상 또는 Seal Packing 작업 미흡으로 인해 산소 유입 - Valve 표면에 흡착된 철가루가 산화하여 녹 발생 추정 | 개별 Seal Packing 등 내부 손상 방지를 위한 Packing Procedure 수립 및 이행 - Valve – Valve, Wooden Box – Valve 간 Protection 방안 (Ex. Seal Packing - Bubble Wrap 이중포장) - Nail이 아닌 Screw를 사용한 Boxing 작업 수행 Vendor 반송 (Vendor Guarantee) & 하기 검사항목 100% 입회검사 진행 (by TPI) - Cleaning & Cleanliness Inspection / Seal Packing Process (at Clean Room) - Packing (Wooden Box Closing) Inspection | https://teams.microsoft.com/l/message/19:KlEVjYWGS-QmxCKqE5H4Ofn-AvSWTK6hz_ErP7aUdvg1@thread.tacv2/1774231397159?tenantId=5fcb0def-a698-40ce-a73a-ea61130c13c6&groupId=80bfa3ae-81fa-4e4e-ba65-7b9c876b82d8&parentMessageId=1774231397159&teamName=P-Quality%20Alert%20Notice%20(PQAN)&channelName=PQAN%20Library&createdTime=1774231397159
16 | PQAN-2026-004 | 2026-04-20 | 2026 | 4 | 0 | 나광조 | 유요석 | 철골 |  |  |  |  | Steel Structure 도장 박리 | Steel Structure | KIC | 한국 |  | After delivery (Site) | Site | 배관 Spool & 철골 도장 후 자재 인수검사 / 현장설치 후 도장박리 발생으로 Bare Steel 노출 | 일반 Inorganic Zinc 도료는 상대적으로 높은 온도와 습도 조건에서 경화 성능 발현 - 동절기 저온/저습 환경에서 경화 지연 및 경화 시간 불충분으로 불완전 경화 Inorganic Zinc Primer Coat의 불완전 경화 (Curing)로 인한 Substrate와의 계면 접착력 저하 Intermediate Coat의 경화 (Curing) 과정에서 발생한 수축 응력이 불완전 경화된 Primer Coat에 인장 응력으로 작용하여 계면 박리 발생 (철골) | Paint Maker의 Technical Data Sheet (TDS) 및 Application Guide의 도장 요건 준수 계절별 충분한 온도/습도 및 경화시간 확보 Inorganic Zinc의 불완전 경화가 의심되는 경우 MEK Test 실시 Substrate 표면처리 적합성 확인 검사 수행 - Press O Film Test, Dust Test, Salt Contamination Test Production Paint 수행 전 Paint Panel Test (Mock-up Test) 수행 | https://teams.microsoft.com/l/message/19:KlEVjYWGS-QmxCKqE5H4Ofn-AvSWTK6hz_ErP7aUdvg1@thread.tacv2/1776662000956?tenantId=5fcb0def-a698-40ce-a73a-ea61130c13c6&groupId=80bfa3ae-81fa-4e4e-ba65-7b9c876b82d8&parentMessageId=1776662000956&teamName=P-Quality%20Alert%20Notice%20(PQAN)&channelName=PQAN%20Library&createdTime=1776662000956

## TPA_목록
순번 | TPA | 등록평가 | 정기평가 (2023) | 정기평가 (2024) | 정기평가 (2025) | 정기평가 (2026)
1 | 3P | 71 | 65 | 80 | N/A (2025 실적 없음) | 68
2 | A&A | 85 | 96 | 100 | 93.3 | 92
3 | ACES | 100 | 61 | 89 | 80.8 | 93
4 | APAVE | 93.5 | 89 | 65 | 90.7 | 60
5 | APPLUS | 94 | 67 | 93 | 92.3 | 74
6 | BROOKE | 74 | 62 | 74 | N/A (2025 실적 없음) | 97
7 | BV | 91 | 98 | 79 | 88.4 | 85
8 | DNV | 91 | 98 | 89 | 91.7 | 68
9 | ERAM | 100 | 75 | 65 | 93.1 | 80
10 | FE | 74 | 94 | 74 | 76.3 | 87
11 | GISCO | 89 | 71 | 83 | 84.3 | 96
12 | GOODIN | 98 | 89 | 72 | 85.2 | 61
13 | INTERTEK | 100 | 81 | 80 | 92.4 | 79
14 | KOTEC | 95.5 | 91 | 70 | 82.1 | 90
15 | PETRO-Q | 74 | 96 | 80 | 71.4 | 64
16 | PETROZONE | 80 | 60 | 85 | 81.9 | 85
17 | RINA | 98 | 70 | 88 | 79.3 | 82
18 | SGS | 98 | 62 | 71 | 81.9 | 82
19 | TEXIN | 100 | 80 | 93 | N/A (2025 실적 없음) | 95
20 | TQ CERT | 85 | 73 | 69 | N/A (2025 실적 없음) | 98
21 | TECHNOCRAT | 83 | 93 | 85 | 75.2 | 98
22 | TUV NORD | 100 | 70 | 88 | N/A (2025 실적 없음) | 63
23 | TUV RHEINLAND | 94 | 67 | 94 | N/A (2025 실적 없음) | 74
24 | ACE PLANTECH | 96.5 | 93 | 72 | N/A (2025 실적 없음) | 77
25 | AMO | 89 | 73 | 91 | N/A (2025 실적 없음) | 92
26 | HEBO | 80 | 89 | 98 | N/A (2025 실적 없음) | 84
27 | SITCO | 94 | 60 | 87 | N/A (2025 실적 없음) | 94

## TPA_집행현황
프로젝트 | 단계 | TPA 예산 (USD) | TPA 계약고 (USD) | 집행비용 (USD) | TPA 예산 (KRW) | TPA 계약고 (KRW) | 집행비용 (KRW) | 예산 소진율 | 現 계약고 소진율
MIP6 | Mechanical Completion | 12511157 | 12511157 | 12499872.15 |  |  |  | 99.91% | 99.91%
SM12 | Active | 9017286 | 9017286 | 8978506.17 |  |  |  | 99.57% | 99.57%
IBRU | Mechanical Completion | 4024396 | 2886653.24 | 2588452.45 |  |  |  | 64.32% | 89.67%
SHN1 | Active |  |  |  | 3442862995 | 3384427737 | 2646671496.1739 | 76.87% | 78.2%
ALOM | Active | 766265 | 766265 | 410205.2 |  |  |  | 53.53% | 53.53%
VEQU | Active | 375828 | 228937 | 203612.28 |  |  |  | 54.18% | 88.94%
STA4 | Active | 8945512 | 7462653 | 6714860.05 |  |  |  | 75.06% | 89.98%
SAC2 | Active | 4791851 | 3650000 | 2747125.66 |  |  |  | 57.33% | 75.26%
CSSP | Active | 5960701 | 미정 |  |  |  |  | 0% | N/A
PNG1 | Active | 1875089 | 미정 |  |  |  |  | 0% | N/A
ALSM | Bid | 미정 | 미정 |  |  |  |  | N/A | N/A

## TPA_월별대금청구현황
순번 | 프로젝트 | TPA | 청구연월 | 지급대금 | 단위
1
2
3 | ALOM | DNV | 2026-04-01 | 36355 | USD
4 | VEQU | APPLUS | 2026-04-01 | 188 | USD
5 | SHN1 | GOODIN | 2026-04-01 | 237000 | KRW
6 | SHN1 | A&A | 2026-04-01 | 12694676 | KRW
7 | SHN1 | DNV | 2026-04-01 | 129437262 | KRW
8 | STA4 | DNV | 2026-04-01 | 49502.3 | USD
9 | STA4 | RINA | 2026-04-01 | 111120.56 | USD
10 | STA4 | INTERTEK | 2026-04-01 | 22723.67 | USD
11 | STA4 | ERAM | 2026-04-01 | 83403.18 | USD
12 | STA4 | PETROZONE | 2026-04-01 | 59880 | USD
13 | STA4 | FE | 2026-04-01 | 45544.28 | USD
14 | STA4 | ACES | 2026-04-01 | 30876.25 | USD
15 | SM12 | INTERTEK | 2026-04-01 | 7511.24 | USD
16 | SM12 | ERAM | 2026-04-01 | 7767.86 | USD
17 | SAC2 | APAVE | 2026-04-01 | 5444 | USD
18 | SAC2 | ERAM | 2026-04-01 | 139313.12 | USD
19 | SAC2 | DNV | 2026-04-01 | 87235.7 | USD
20 | SAC2 | RINA | 2026-04-01 | 28492 | USD
21 | SAC2 | PETROZONE | 2026-04-01 | 150956 | USD
22 | SAC2 | TECHNOCRAT | 2026-04-01 | 58370 | USD
23 | SAC2 | ACES | 2026-04-01 | 772 | USD
24 | IBRU | GISCO | 2026-04-01 | 172 | USD
25 | SAC2 | APAVE | 2026-03-31 | 840 | USD
26 | SAC2 | ERAM | 2026-03-31 | 111446 | USD
27 | SAC2 | DNV | 2026-03-31 | 155310.96 | USD
28 | SAC2 | INTERTEK | 2026-03-31 | 3760 | USD
29 | SAC2 | TECHNOCRAT | 2026-03-31 | 46262.5 | USD
30 | ALOM | DNV | 2026-03-02 | 33400 | USD
31 | MIP6 | APAVE | 2026-03-01 | 18660 | USD
32 | SM12 | ERAM | 2026-03-01 | 1588.8 | USD
33 | STA4 | DNV | 2026-03-01 | 81830.1 | USD
34 | STA4 | RINA | 2026-03-01 | 467149.15 | USD
35 | STA4 | INTERTEK | 2026-03-01 | 79318.27 | USD
36 | STA4 | ERAM | 2026-03-01 | 101419.19 | USD
37 | STA4 | PETROZONE | 2026-03-01 | 59012 | USD
38 | STA4 | FE | 2026-03-01 | 39306 | USD
39 | STA4 | ACES | 2026-03-01 | 21403.5 | USD
40 | IBRU | GISCO | 2026-03-01 | 172 | USD
41 | SHN1 | GOODIN | 2026-03-01 | 948000 | KRW
42 | SHN1 | A&A | 2026-03-01 | 38117976.4706 | KRW
43 | SHN1 | DNV | 2026-03-01 | 97481029.4118 | KRW
44 | ALOM | DNV | 2026-02-02 | 7770 | USD
45 | MIP6 | APAVE | 2026-02-01 | 36836.85 | USD
46 | SM12 | APAVE | 2026-02-01 | 466.5 | USD
47 | SM12 | RINA | 2026-02-01 | 816 | USD
48 | SM12 | PETROZONE | 2026-02-01 | 12164 | USD
49 | STA4 | DNV | 2026-02-01 | 36961 | USD
50 | STA4 | RINA | 2026-02-01 | 277489.47 | USD
51 | STA4 | INTERTEK | 2026-02-01 | 30463.94 | USD
52 | STA4 | ERAM | 2026-02-01 | 179930.55 | USD
53 | STA4 | PETROZONE | 2026-02-01 | 64952 | USD
54 | STA4 | SGS | 2026-02-01 | 1459.74 | USD
55 | STA4 | FE | 2026-02-01 | 56878 | USD
56 | STA4 | ACES | 2026-02-01 | 30420.4 | USD
57 | SAC2 | APAVE | 2026-02-01 | 17589 | USD
58 | SAC2 | ERAM | 2026-02-01 | 107143.22 | USD
59 | SAC2 | DNV | 2026-02-01 | 84873.94 | USD
60 | SAC2 | INTERTEK | 2026-02-01 | 5786.83 | USD
61 | SAC2 | RINA | 2026-02-01 | 2554.8 | USD
62 | SAC2 | TECHNOCRAT | 2026-02-01 | 70860 | USD
63 | IBRU | GISCO | 2026-02-01 | 975 | USD
64 | IBRU | BV | 2026-02-01 | 978 | USD
65 | SHN1 | GOODIN | 2026-02-01 | 14023571.4286 | KRW
66 | SHN1 | A&A | 2026-02-01 | 47164076.1905 | KRW
67 | SHN1 | DNV | 2026-02-01 | 82184523.8095 | KRW
68 | VEQU | APPLUS | 2026-01-02 | 188 | USD
69 | ALOM | DNV | 2026-01-02 | 2200 | USD
70 | MIP6 | APAVE | 2026-01-01 | 16857.02 | USD
71 | SM12 | INTERTEK | 2026-01-01 | 2984.82 | USD
72 | SM12 | DNV | 2026-01-01 | 545 | USD
73 | SM12 | RINA | 2026-01-01 | 2838 | USD
74 | SM12 | ERAM | 2026-01-01 | 2757 | USD
75 | STA4 | DNV | 2026-01-01 | 56627.7 | USD
76 | STA4 | RINA | 2026-01-01 | 78834.65 | USD
77 | STA4 | INTERTEK | 2026-01-01 | 12499.8 | USD
78 | STA4 | ERAM | 2026-01-01 | 158336.32 | USD
79 | STA4 | PETROZONE | 2026-01-01 | 126540 | USD
80 | STA4 | FE | 2026-01-01 | 70682 | USD
81 | STA4 | ACES | 2026-01-01 | 51115.65 | USD
82 | SAC2 | ERAM | 2026-01-01 | 43161 | USD
83 | SAC2 | DNV | 2026-01-01 | 28610.8 | USD
84 | SAC2 | PETROZONE | 2026-01-01 | 5408 | USD
85 | SAC2 | TECHNOCRAT | 2026-01-01 | 50757.5 | USD
86 | SHN1 | GOODIN | 2026-01-01 | 22752000 | KRW
87 | SHN1 | A&A | 2026-01-01 | 49672127.2727 | KRW
88 | SHN1 | DNV | 2026-01-01 | 63178636.3636 | KRW
89 | VEQU | APPLUS | 2025-12-02 | 690 | USD
90 | ALOM | DNV | 2025-12-02 | 2140 | USD
91 | MIP6 | APAVE | 2025-12-01 | 25819.12 | USD
92 | SM12 | ERAM | 2025-12-01 | 7008 | USD
93 | SM12 | PETROZONE | 2025-12-01 | 7484 | USD
94 | STA4 | DNV | 2025-12-01 | 74622.32 | USD
95 | STA4 | RINA | 2025-12-01 | 14040.56 | USD
96 | STA4 | INTERTEK | 2025-12-01 | 12326.2 | USD
97 | STA4 | ERAM | 2025-12-01 | 67955.61 | USD
98 | STA4 | PETROZONE | 2025-12-01 | 34136 | USD
99 | STA4 | SGS | 2025-12-01 | 8139.59 | USD
100 | STA4 | FE | 2025-12-01 | 47456 | USD
101 | STA4 | ACES | 2025-12-01 | 32592.5 | USD
102 | SAC2 | APAVE | 2025-12-01 | 1932 | USD
103 | SAC2 | ERAM | 2025-12-01 | 22435.95 | USD
104 | SAC2 | DNV | 2025-12-01 | 71011.1 | USD
105 | SAC2 | INTERTEK | 2025-12-01 | 608 | USD
106 | SAC2 | RINA | 2025-12-01 | 26386 | USD
107 | SHN1 | GOODIN | 2025-12-01 | 29003000 | KRW
108 | SHN1 | A&A | 2025-12-01 | 60475400 | KRW
109 | SHN1 | DNV | 2025-12-01 | 41405000 | KRW
110 | VEQU | APPLUS | 2025-11-02 | 776 | USD
111 | ALOM | DNV | 2025-11-02 | 6238 | USD
112 | MIP6 | APAVE | 2025-11-01 | 31732.66 | USD
113 | SM12 | INTERTEK | 2025-11-01 | 3043.78 | USD
114 | SM12 | APAVE | 2025-11-01 | 3409.06 | USD
115 | SM12 | ERAM | 2025-11-01 | 2832.58 | USD
116 | STA4 | DNV | 2025-11-01 | 54251.96 | USD
117 | STA4 | RINA | 2025-11-01 | 49687.85 | USD
118 | STA4 | INTERTEK | 2025-11-01 | 21691.64 | USD
119 | STA4 | ERAM | 2025-11-01 | 213129.05 | USD
120 | STA4 | PETROZONE | 2025-11-01 | 113436 | USD
121 | STA4 | SGS | 2025-11-01 | 6468.24 | USD
122 | STA4 | FE | 2025-11-01 | 38608 | USD
123 | STA4 | ACES | 2025-11-01 | 28264.65 | USD
124 | SAC2 | APAVE | 2025-11-01 | 2912 | USD
125 | SAC2 | ERAM | 2025-11-01 | 14470.62 | USD
126 | SAC2 | DNV | 2025-11-01 | 47334.52 | USD
127 | IBRU | GISCO | 2025-11-01 | 344 | USD
128 | SHN1 | GOODIN | 2025-11-01 | 22262333.3333 | KRW
129 | SHN1 | A&A | 2025-11-01 | 55842111.1111 | KRW
130 | SHN1 | DNV | 2025-11-01 | 41901666.6667 | KRW
131 | ALOM | DNV | 2025-10-02 | 1815 | USD
132 | MIP6 | APAVE | 2025-10-01 | 25175.71 | USD
133 | SM12 | BV | 2025-10-01 | 5437.8 | USD
134 | SM12 | APAVE | 2025-10-01 | 15999.29 | USD
135 | SM12 | RINA | 2025-10-01 | 360 | USD
136 | SM12 | ERAM | 2025-10-01 | 31532.09 | USD
137 | SM12 | PETROZONE | 2025-10-01 | 18728 | USD
138 | STA4 | DNV | 2025-10-01 | 73161 | USD
139 | STA4 | RINA | 2025-10-01 | 71357.71 | USD
140 | STA4 | INTERTEK | 2025-10-01 | 18643.38 | USD
141 | STA4 | ERAM | 2025-10-01 | 153105.51 | USD
142 | STA4 | PETROZONE | 2025-10-01 | 231340 | USD
143 | STA4 | SGS | 2025-10-01 | 3272 | USD
144 | STA4 | FE | 2025-10-01 | 47106 | USD
145 | STA4 | ACES | 2025-10-01 | 11637.2 | USD
146 | SAC2 | APAVE | 2025-10-01 | 2702 | USD
147 | SAC2 | ERAM | 2025-10-01 | 42020.18 | USD
148 | SAC2 | DNV | 2025-10-01 | 45456.04 | USD
149 | SAC2 | INTERTEK | 2025-10-01 | 5776 | USD
150 | SAC2 | RINA | 2025-10-01 | 18837.4 | USD
151 | SAC2 | TECHNOCRAT | 2025-10-01 | 119110 | USD
152 | SHN1 | GOODIN | 2025-10-01 | 19363000 | KRW
153 | SHN1 | A&A | 2025-10-01 | 87235165 | KRW
154 | SHN1 | DNV | 2025-10-01 | 36265000 | KRW
155 | VEQU | APPLUS | 2025-10-01 | 564 | USD
156 | MIP6 | APAVE | 2025-09-01 | 15680.85 | USD
157 | SM12 | BV | 2025-09-01 | 4176.4 | USD
158 | SM12 | APAVE | 2025-09-01 | 30093.52 | USD
159 | SM12 | ERAM | 2025-09-01 | 20852.6 | USD
160 | SM12 | PETROZONE | 2025-09-01 | 36840 | USD
161 | SM12 | TECHNOCRAT | 2025-09-01 | 6026 | USD
162 | STA4 | DNV | 2025-09-01 | 69729.98 | USD
163 | STA4 | INTERTEK | 2025-09-01 | 36154.29 | USD
164 | STA4 | ERAM | 2025-09-01 | 162243.14 | USD
165 | STA4 | SGS | 2025-09-01 | 8076.2 | USD
166 | STA4 | FE | 2025-09-01 | 15178 | USD
167 | STA4 | ACES | 2025-09-01 | 14301.8 | USD
168 | SAC2 | APAVE | 2025-09-01 | 4592 | USD
169 | SAC2 | ERAM | 2025-09-01 | 43525.5 | USD
170 | SAC2 | DNV | 2025-09-01 | 30998.78 | USD
171 | SAC2 | RINA | 2025-09-01 | 22194.25 | USD
172 | SHN1 | GOODIN | 2025-09-01 | 20074000 | KRW
173 | SHN1 | A&A | 2025-09-01 | 55536555 | KRW
174 | SHN1 | DNV | 2025-09-01 | 28190000 | KRW
175 | VEQU | APPLUS | 2025-09-01 | 1540 | USD
176 | ALOM | DNV | 2025-09-01 | 1120 | USD
177 | MIP6 | APAVE | 2025-08-01 | 17595.52 | USD
178 | SM12 | BV | 2025-08-01 | 1696 | USD
179 | SM12 | APAVE | 2025-08-01 | 660.5 | USD
180 | SM12 | ERAM | 2025-08-01 | 52674.76 | USD
181 | SM12 | PETROZONE | 2025-08-01 | 21664 | USD
182 | STA4 | DNV | 2025-08-01 | 28944.77 | USD
183 | STA4 | INTERTEK | 2025-08-01 | 29279.42 | USD
184 | STA4 | ERAM | 2025-08-01 | 85594.08 | USD
185 | STA4 | PETROZONE | 2025-08-01 | 54452 | USD
186 | STA4 | SGS | 2025-08-01 | 36063.8 | USD
187 | STA4 | FE | 2025-08-01 | 34304 | USD
188 | SAC2 | APAVE | 2025-08-01 | 7168 | USD
189 | SAC2 | ERAM | 2025-08-01 | 39956.5 | USD
190 | SAC2 | DNV | 2025-08-01 | 74288.46 | USD
191 | SAC2 | INTERTEK | 2025-08-01 | 5347.06 | USD
192 | SAC2 | PETROZONE | 2025-08-01 | 3824 | USD
193 | SAC2 | TECHNOCRAT | 2025-08-01 | 3112.5 | USD
194 | SHN1 | GOODIN | 2025-08-01 | 29098304 | KRW
195 | SHN1 | A&A | 2025-08-01 | 63664536.9565 | KRW
196 | SHN1 | DNV | 2025-08-01 | 29485434.7826 | KRW
197 | VEQU | APPLUS | 2025-08-01 | 1270 | USD
198 | ALOM | DNV | 2025-08-01 | 2850 | USD
199 | MIP6 | APAVE | 2025-07-01 | 15482.2 | USD
200 | SM12 | BV | 2025-07-01 | 7363.6 | USD
201 | SM12 | APAVE | 2025-07-01 | 30822.82 | USD
202 | SM12 | ERAM | 2025-07-01 | 31744.46 | USD
203 | STA4 | DNV | 2025-07-01 | 73123.01 | USD
204 | STA4 | RINA | 2025-07-01 | 30080.93 | USD
205 | STA4 | INTERTEK | 2025-07-01 | 74142.6 | USD
206 | STA4 | ERAM | 2025-07-01 | 199819.41 | USD
207 | STA4 | PETROZONE | 2025-07-01 | 67064 | USD
208 | SAC2 | APAVE | 2025-07-01 | 5544 | USD
209 | SAC2 | ERAM | 2025-07-01 | 38552 | USD
210 | SAC2 | DNV | 2025-07-01 | 54230.46 | USD
211 | SAC2 | INTERTEK | 2025-07-01 | 3177.63 | USD
212 | SAC2 | RINA | 2025-07-01 | 5150.4 | USD
213 | SHN1 | GOODIN | 2025-07-01 | 29075947 | KRW
214 | SHN1 | A&A | 2025-07-01 | 63232088.2105 | KRW
215 | SHN1 | DNV | 2025-07-01 | 30565000 | KRW
216 | SHN1 | KOTEC | 2025-07-01 | 1380000 | KRW
217 | VEQU | APPLUS | 2025-07-01 | 1684 | USD
218 | ALOM | DNV | 2025-07-01 | 1320 | USD
219 | MIP6 | INTERTEK | 2025-06-01 | 920.8 | USD
220 | MIP6 | APAVE | 2025-06-01 | 17557.62 | USD
221 | SM12 | BV | 2025-06-01 | 3523.6 | USD
222 | SM12 | ERAM | 2025-06-01 | 44626.08 | USD
223 | SM12 | PETROZONE | 2025-06-01 | 640 | USD
224 | SM12 | TECHNOCRAT | 2025-06-01 | 4140 | USD
225 | STA4 | DNV | 2025-06-01 | 58182.33 | USD
226 | STA4 | RINA | 2025-06-01 | 75111.54 | USD
227 | STA4 | INTERTEK | 2025-06-01 | 45719.06 | USD
228 | STA4 | ERAM | 2025-06-01 | 106009.25 | USD
229 | STA4 | PETROZONE | 2025-06-01 | 53912 | USD
230 | SAC2 | APAVE | 2025-06-01 | 6583.5 | USD
231 | SAC2 | ERAM | 2025-06-01 | 29938.5 | USD
232 | SAC2 | DNV | 2025-06-01 | 49547.88 | USD
233 | SAC2 | INTERTEK | 2025-06-01 | 2960.24 | USD
234 | SAC2 | RINA | 2025-06-01 | 18803.2 | USD
235 | IBRU | GISCO | 2025-06-01 | 459 | USD
236 | SHN1 | GOODIN | 2025-06-01 | 25658736 | KRW
237 | SHN1 | A&A | 2025-06-01 | 53933379 | KRW
238 | SHN1 | DNV | 2025-06-01 | 24286842.1053 | KRW
239 | SHN1 | KOTEC | 2025-06-01 | 3450000 | KRW
240 | VEQU | APPLUS | 2025-06-01 | 490 | USD
241 | ALOM | DNV | 2025-06-01 | 1320 | USD
242 | MIP6 | DNV | 2025-05-01 | 46098.59 | USD
243 | MIP6 | APAVE | 2025-05-01 | 14797.12 | USD
244 | SM12 | DNV | 2025-05-01 | 6968 | USD
245 | SM12 | BV | 2025-05-01 | 7327.78 | USD
246 | SM12 | APAVE | 2025-05-01 | 10420.12 | USD
247 | SM12 | ERAM | 2025-05-01 | 64994.48 | USD
248 | SM12 | PETROZONE | 2025-05-01 | 34912 | USD
249 | SM12 | TECHNOCRAT | 2025-05-01 | 10580 | USD
250 | STA4 | DNV | 2025-05-01 | 34051.66 | USD
251 | STA4 | RINA | 2025-05-01 | 14331.45 | USD
252 | STA4 | INTERTEK | 2025-05-01 | 77770.25 | USD
253 | STA4 | ERAM | 2025-05-01 | 82548.18 | USD
254 | STA4 | PETROZONE | 2025-05-01 | 24536 | USD
255 | SAC2 | APAVE | 2025-05-01 | 3542 | USD
256 | SAC2 | ERAM | 2025-05-01 | 37710.27 | USD
257 | SAC2 | DNV | 2025-05-01 | 153551.26 | USD
258 | SAC2 | INTERTEK | 2025-05-01 | 6514.31 | USD
259 | SAC2 | RINA | 2025-05-01 | 9462.8 | USD
260 | SHN1 | GOODIN | 2025-05-01 | 24534000 | KRW
261 | SHN1 | A&A | 2025-05-01 | 56605893 | KRW
262 | SHN1 | DNV | 2025-05-01 | 16627272.7273 | KRW
263 | SHN1 | KOTEC | 2025-05-01 | 8285713 | KRW
264 | VEQU | APPLUS | 2025-05-01 | 5283 | USD
265 | MIP6 | APAVE | 2025-04-01 | 8588.71 | USD
266 | MIP6 | ERAM | 2025-04-01 | 1753.38 | USD
267 | SM12 | DNV | 2025-04-01 | 1683.45 | USD
268 | SM12 | BV | 2025-04-01 | 1696 | USD
269 | SM12 | APAVE | 2025-04-01 | 14986.71 | USD
270 | SM12 | RINA | 2025-04-01 | 3930.1 | USD
271 | SM12 | ERAM | 2025-04-01 | 40859.64 | USD
272 | SM12 | PETROZONE | 2025-04-01 | 17532 | USD
273 | SM12 | SGS | 2025-04-01 | 9300.1 | USD
274 | STA4 | DNV | 2025-04-01 | 54222.96 | USD
275 | STA4 | RINA | 2025-04-01 | 31956.27 | USD
276 | STA4 | INTERTEK | 2025-04-01 | 26322.38 | USD
277 | STA4 | ERAM | 2025-04-01 | 114979.11 | USD
278 | STA4 | PETROZONE | 2025-04-01 | 35584 | USD
279 | STA4 | SGS | 2025-04-01 | 3106 | USD
280 | SAC2 | APAVE | 2025-04-01 | 6860 | USD
281 | SAC2 | ERAM | 2025-04-01 | 31955.2 | USD
282 | SAC2 | DNV | 2025-04-01 | 61184.98 | USD
283 | SAC2 | INTERTEK | 2025-04-01 | 5545.46 | USD
284 | SAC2 | RINA | 2025-04-01 | 15356.85 | USD
285 | SAC2 | PETROZONE | 2025-04-01 | 8360 | USD
286 | IBRU | GISCO | 2025-04-01 | 1416 | USD
287 | SHN1 | GOODIN | 2025-04-01 | 25468000 | KRW
288 | SHN1 | A&A | 2025-04-01 | 42693865 | KRW
289 | SHN1 | DNV | 2025-04-01 | 10000000 | KRW
290 | SHN1 | KOTEC | 2025-04-01 | 27568571 | KRW
291 | VEQU | APPLUS | 2025-04-01 | 6235 | USD
292 | MIP6 | APAVE | 2025-03-01 | 7752 | USD
293 | MIP6 | ERAM | 2025-03-01 | 1290.69 | USD
294 | SM12 | INTERTEK | 2025-03-01 | 664 | USD
295 | SM12 | DNV | 2025-03-01 | 13618.11 | USD
296 | SM12 | BV | 2025-03-01 | 6884.86 | USD
297 | SM12 | APAVE | 2025-03-01 | 15628.28 | USD
298 | SM12 | RINA | 2025-03-01 | 7339.6 | USD
299 | SM12 | ERAM | 2025-03-01 | 83634.91 | USD
300 | SM12 | PETROZONE | 2025-03-01 | 30768 | USD
301 | SM12 | SGS | 2025-03-01 | 2508 | USD
302 | STA4 | DNV | 2025-03-01 | 65294.26 | USD
303 | STA4 | RINA | 2025-03-01 | 21557.95 | USD
304 | STA4 | INTERTEK | 2025-03-01 | 7582 | USD
305 | STA4 | ERAM | 2025-03-01 | 76191.6 | USD
306 | STA4 | PETROZONE | 2025-03-01 | 46784 | USD
307 | STA4 | SGS | 2025-03-01 | 2256 | USD
308 | SAC2 | APAVE | 2025-03-01 | 3125 | USD
309 | SAC2 | ERAM | 2025-03-01 | 42195.5 | USD
310 | SAC2 | DNV | 2025-03-01 | 51987.32 | USD
311 | SAC2 | INTERTEK | 2025-03-01 | 6602.51 | USD
312 | SAC2 | RINA | 2025-03-01 | 5569.4 | USD
313 | IBRU | GISCO | 2025-03-01 | 395 | USD
314 | SHN1 | GOODIN | 2025-03-01 | 33318000 | KRW
315 | SHN1 | A&A | 2025-03-01 | 32312000 | KRW
316 | SHN1 | DNV | 2025-03-01 | 10220000 | KRW
317 | SHN1 | KOTEC | 2025-03-01 | 11565000 | KRW
318 | VEQU | APPLUS | 2025-03-01 | 6122.5 | USD
319 | ALOM | DNV | 2025-03-01 | 2000 | USD
320 | VEQU | APPLUS | 2025-02-02 | 10874.5 | USD
321 | MIP6 | APAVE | 2025-02-01 | 6079.28 | USD
322 | SM12 | INTERTEK | 2025-02-01 | 920.8 | USD
323 | SM12 | DNV | 2025-02-01 | 1474 | USD
324 | SM12 | BV | 2025-02-01 | 3009.5 | USD
325 | SM12 | APAVE | 2025-02-01 | 2786.5 | USD
326 | SM12 | RINA | 2025-02-01 | 563 | USD
327 | SM12 | ERAM | 2025-02-01 | 15775.18 | USD
328 | SM12 | PETROZONE | 2025-02-01 | 34792 | USD
329 | SM12 | TECHNOCRAT | 2025-02-01 | 460 | USD
330 | STA4 | DNV | 2025-02-01 | 46826.6 | USD
331 | STA4 | RINA | 2025-02-01 | 13399.71 | USD
332 | STA4 | INTERTEK | 2025-02-01 | 27811.14 | USD
333 | STA4 | ERAM | 2025-02-01 | 38298.4 | USD
334 | STA4 | PETROZONE | 2025-02-01 | 7088 | USD
335 | SAC2 | APAVE | 2025-02-01 | 13104 | USD
336 | SAC2 | ERAM | 2025-02-01 | 66897.4 | USD
337 | SAC2 | DNV | 2025-02-01 | 115039.56 | USD
338 | SAC2 | INTERTEK | 2025-02-01 | 1120 | USD
339 | SAC2 | RINA | 2025-02-01 | 26007.8 | USD
340 | IBRU | GISCO | 2025-02-01 | 631 | USD
341 | SHN1 | GOODIN | 2025-02-01 | 32509555 | KRW
342 | SHN1 | A&A | 2025-02-01 | 28269260 | KRW
343 | SHN1 | DNV | 2025-02-01 | 10220000 | KRW
344 | SHN1 | KOTEC | 2025-02-01 | 15870000 | KRW
345 | ALOM | DNV | 2025-02-01 | 1600 | USD
346 | VEQU | APPLUS | 2025-01-01 | 9429 | USD
347 | MIP6 | DNV | 2025-01-01 | 31133 | USD
348 | MIP6 | APAVE | 2025-01-01 | 9455.63 | USD
349 | MIP6 | RINA | 2025-01-01 | 675 | USD
350 | MIP6 | ERAM | 2025-01-01 | 2999.72 | USD
351 | MIP6 | PETROZONE | 2025-01-01 | 69170 | USD
352 | MIP6 | TEXIN | 2025-01-01 | 6224.8 | USD
353 | MIP6 | TECHNOCRAT | 2025-01-01 | 9269 | USD
354 | MIP6 | PETRO-Q | 2025-01-01 | 6360 | USD
355 | SM12 | INTERTEK | 2025-01-01 | 1200.8 | USD
356 | SM12 | BV | 2025-01-01 | 8041.5 | USD
357 | SM12 | APAVE | 2025-01-01 | 19170.82 | USD
358 | SM12 | APPLUS | 2025-01-01 | 4574.16 | USD
359 | SM12 | RINA | 2025-01-01 | 3429.9 | USD
360 | SM12 | ERAM | 2025-01-01 | 77949.27 | USD
361 | SM12 | PETROZONE | 2025-01-01 | 27328 | USD
362 | SM12 | TQ CERT | 2025-01-01 | 18285.3 | USD
363 | SM12 | TECHNOCRAT | 2025-01-01 | 460 | USD
364 | SM12 | SGS | 2025-01-01 | 14478.45 | USD
365 | SM12 | PETRO-Q | 2025-01-01 | 344 | USD
366 | STA4 | DNV | 2025-01-01 | 75578.66 | USD
367 | STA4 | RINA | 2025-01-01 | 12680.51 | USD
368 | STA4 | INTERTEK | 2025-01-01 | 8174.11 | USD
369 | STA4 | ERAM | 2025-01-01 | 52391.1 | USD
370 | STA4 | PETROZONE | 2025-01-01 | 15896 | USD
371 | IBRU | GISCO | 2025-01-01 | 3142 | USD
372 | SHN1 | GOODIN | 2025-01-01 | 31226380.9524 | KRW
373 | SHN1 | A&A | 2025-01-01 | 26225055 | KRW
374 | SHN1 | DNV | 2025-01-01 | 10000000 | KRW
375 | SHN1 | KOTEC | 2025-01-01 | 10350000 | KRW
376 | ALOM | DNV | 2025-01-01 | 1400 | USD
377 | VEQU | APPLUS | 2024-12-01 | 21952.5 | USD
378 | MIP6 | INTERTEK | 2024-12-01 | 2333.78 | USD
379 | MIP6 | DNV | 2024-12-01 | 28285 | USD
380 | MIP6 | APAVE | 2024-12-01 | 39847.57 | USD
381 | MIP6 | RINA | 2024-12-01 | 1499.2 | USD
382 | MIP6 | ERAM | 2024-12-01 | 15182.05 | USD
383 | MIP6 | PETROZONE | 2024-12-01 | 68744 | USD
384 | MIP6 | TECHNOCRAT | 2024-12-01 | 460 | USD
385 | MIP6 | PETRO-Q | 2024-12-01 | 5936 | USD
386 | SM12 | INTERTEK | 2024-12-01 | 2569.6 | USD
387 | SM12 | BV | 2024-12-01 | 4051.3 | USD
388 | SM12 | APAVE | 2024-12-01 | 2993 | USD
389 | SM12 | RINA | 2024-12-01 | 4560.36 | USD
390 | SM12 | ERAM | 2024-12-01 | 41751.73 | USD
391 | SM12 | PETROZONE | 2024-12-01 | 47028 | USD
392 | SM12 | TECHNOCRAT | 2024-12-01 | 2208 | USD
393 | SM12 | SGS | 2024-12-01 | 83471.62 | USD
394 | SM12 | PETRO-Q | 2024-12-01 | 1904 | USD
395 | STA4 | DNV | 2024-12-01 | 42179.6 | USD
396 | STA4 | RINA | 2024-12-01 | 12612.15 | USD
397 | STA4 | INTERTEK | 2024-12-01 | 6882.84 | USD
398 | STA4 | ERAM | 2024-12-01 | 51418 | USD
399 | STA4 | PETROZONE | 2024-12-01 | 17984 | USD
400 | SHN1 | GOODIN | 2024-12-01 | 31210000 | KRW
401 | SHN1 | A&A | 2024-12-01 | 23007200 | KRW
402 | SHN1 | DNV | 2024-12-01 | 10220000 | KRW
403 | SHN1 | KOTEC | 2024-12-01 | 18480000 | KRW
404 | ALOM | DNV | 2024-12-01 | 800 | USD
405 | VEQU | APPLUS | 2024-11-01 | 18045 | USD
406 | MIP6 | DNV | 2024-11-01 | 3848 | USD
407 | MIP6 | APAVE | 2024-11-01 | 768 | USD
408 | MIP6 | ERAM | 2024-11-01 | 10573.64 | USD
409 | MIP6 | TECHNOCRAT | 2024-11-01 | 2208 | USD
410 | SM12 | INTERTEK | 2024-11-01 | 1414 | USD
411 | SM12 | DNV | 2024-11-01 | 4059 | USD
412 | SM12 | BV | 2024-11-01 | 1685.4 | USD
413 | SM12 | APAVE | 2024-11-01 | 1981.5 | USD
414 | SM12 | RINA | 2024-11-01 | 12855 | USD
415 | SM12 | ERAM | 2024-11-01 | 73215.22 | USD
416 | SM12 | TECHNOCRAT | 2024-11-01 | 2944 | USD
417 | SM12 | SGS | 2024-11-01 | 3183.72 | USD
418 | STA4 | DNV | 2024-11-01 | 23087.7 | USD
419 | STA4 | RINA | 2024-11-01 | 4352.08 | USD
420 | STA4 | INTERTEK | 2024-11-01 | 6246.12 | USD
421 | STA4 | ERAM | 2024-11-01 | 55250.44 | USD
422 | STA4 | PETROZONE | 2024-11-01 | 26148 | USD
423 | IBRU | GISCO | 2024-11-01 | 3042 | USD
424 | SHN1 | GOODIN | 2024-11-01 | 36367333.3333 | KRW
425 | SHN1 | A&A | 2024-11-01 | 19695200 | KRW
426 | SHN1 | DNV | 2024-11-01 | 4220000 | KRW
427 | SHN1 | KOTEC | 2024-11-01 | 22810000 | KRW
428 | ALOM | DNV | 2024-11-01 | 6460 | USD
429 | VEQU | APPLUS | 2024-10-01 | 16570.26 | USD
430 | MIP6 | INTERTEK | 2024-10-01 | 7201.35 | USD
431 | MIP6 | DNV | 2024-10-01 | 89005.5 | USD
432 | MIP6 | APAVE | 2024-10-01 | 24437.32 | USD
433 | MIP6 | ERAM | 2024-10-01 | 10213.33 | USD
434 | MIP6 | PETROZONE | 2024-10-01 | 47512 | USD
435 | MIP6 | TEXIN | 2024-10-01 | 3461 | USD
436 | MIP6 | TECHNOCRAT | 2024-10-01 | 30676.71 | USD
437 | SM12 | DNV | 2024-10-01 | 9527.5 | USD
438 | SM12 | APAVE | 2024-10-01 | 3893.5 | USD
439 | SM12 | RINA | 2024-10-01 | 11599.45 | USD
440 | SM12 | ERAM | 2024-10-01 | 53425.55 | USD
441 | SM12 | PETROZONE | 2024-10-01 | 20380 | USD
442 | SM12 | TEXIN | 2024-10-01 | 7359.6 | USD
443 | SM12 | SGS | 2024-10-01 | 32728.78 | USD
444 | SM12 | PETRO-Q | 2024-10-01 | 3392 | USD
445 | STA4 | RINA | 2024-10-01 | 9851.6 | USD
446 | STA4 | INTERTEK | 2024-10-01 | 8935.04 | USD
447 | STA4 | ERAM | 2024-10-01 | 41413.5 | USD
448 | STA4 | PETROZONE | 2024-10-01 | 15976 | USD
449 | IBRU | GISCO | 2024-10-01 | 6545 | USD
450 | IBRU | BV | 2024-10-01 | 708 | USD
451 | SHN1 | GOODIN | 2024-10-01 | 21194000 | KRW
452 | SHN1 | A&A | 2024-10-01 | 6668400 | KRW
453 | SHN1 | DNV | 2024-10-01 | 220000 | KRW
454 | SHN1 | KOTEC | 2024-10-01 | 22270000 | KRW
455 | ALOM | DNV | 2024-10-01 | 1200 | USD
456 | VEQU | APPLUS | 2024-09-01 | 11709.02 | USD
457 | MIP6 | INTERTEK | 2024-09-01 | 9600.52 | USD
458 | MIP6 | DNV | 2024-09-01 | 12099 | USD
459 | MIP6 | APAVE | 2024-09-01 | 5756.8 | USD
460 | MIP6 | ERAM | 2024-09-01 | 9915.14 | USD
461 | MIP6 | PETROZONE | 2024-09-01 | 45312 | USD
462 | MIP6 | TQ CERT | 2024-09-01 | 1744.9 | USD
463 | MIP6 | PETRO-Q | 2024-09-01 | 35510 | USD
464 | SM12 | INTERTEK | 2024-09-01 | 1956 | USD
465 | SM12 | DNV | 2024-09-01 | 11063.5 | USD
466 | SM12 | APAVE | 2024-09-01 | 5944.5 | USD
467 | SM12 | APPLUS | 2024-09-01 | 6755.36 | USD
468 | SM12 | RINA | 2024-09-01 | 14741.1 | USD
469 | SM12 | ERAM | 2024-09-01 | 61103.7 | USD
470 | SM12 | PETROZONE | 2024-09-01 | 22224 | USD
471 | SM12 | TEXIN | 2024-09-01 | 24813 | USD
472 | SM12 | SGS | 2024-09-01 | 44973.04 | USD
473 | STA4 | DNV | 2024-09-01 | 712.8 | USD
474 | STA4 | RINA | 2024-09-01 | 7528.3 | USD
475 | STA4 | INTERTEK | 2024-09-01 | 3712 | USD
476 | STA4 | ERAM | 2024-09-01 | 28931.2 | USD
477 | STA4 | PETROZONE | 2024-09-01 | 21712 | USD
478 | STA4 | SGS | 2024-09-01 | 955.72 | USD
479 | IBRU | GISCO | 2024-09-01 | 9953.6 | USD
480 | SHN1 | GOODIN | 2024-09-01 | 22837000 | KRW
481 | SHN1 | A&A | 2024-09-01 | 6967619.0476 | KRW
482 | SHN1 | KOTEC | 2024-09-01 | 22070000 | KRW
483 | ALOM | DNV | 2024-09-01 | 1160 | USD
484 | VEQU | APPLUS | 2024-08-01 | 7514.5 | USD
485 | MIP6 | INTERTEK | 2024-08-01 | 1543 | USD
486 | MIP6 | DNV | 2024-08-01 | 42841.5 | USD
487 | MIP6 | BV | 2024-08-01 | 6785.22 | USD
488 | MIP6 | APAVE | 2024-08-01 | 1536 | USD
489 | MIP6 | RINA | 2024-08-01 | 1810.48 | USD
490 | MIP6 | ERAM | 2024-08-01 | 10100.81 | USD
491 | MIP6 | PETROZONE | 2024-08-01 | 60424 | USD
492 | MIP6 | TEXIN | 2024-08-01 | 2816.2 | USD
493 | MIP6 | TECHNOCRAT | 2024-08-01 | 41759.49 | USD
494 | SM12 | INTERTEK | 2024-08-01 | 3626.6 | USD
495 | SM12 | DNV | 2024-08-01 | 8417 | USD
496 | SM12 | BV | 2024-08-01 | 4375.68 | USD
497 | SM12 | APAVE | 2024-08-01 | 6824 | USD
498 | SM12 | RINA | 2024-08-01 | 17354.16 | USD
499 | SM12 | ERAM | 2024-08-01 | 65143.92 | USD
500 | SM12 | PETROZONE | 2024-08-01 | 31432 | USD
501 | SM12 | TEXIN | 2024-08-01 | 20699.04 | USD
502 | SM12 | TECHNOCRAT | 2024-08-01 | 3036 | USD
503 | SM12 | SGS | 2024-08-01 | 24280.31 | USD
504 | STA4 | DNV | 2024-08-01 | 511.2 | USD
505 | STA4 | RINA | 2024-08-01 | 816.85 | USD
506 | STA4 | ERAM | 2024-08-01 | 12064.4 | USD
507 | IBRU | GISCO | 2024-08-01 | 11453.8 | USD
508 | SHN1 | GOODIN | 2024-08-01 | 20989347 | KRW
509 | SHN1 | A&A | 2024-08-01 | 14243640 | KRW
510 | SHN1 | KOTEC | 2024-08-01 | 24140000 | KRW
511 | ALOM | DNV | 2024-08-01 | 1400 | USD
512 | VEQU | APPLUS | 2024-07-01 | 4535 | USD
513 | MIP6 | INTERTEK | 2024-07-01 | 4359 | USD
514 | MIP6 | DNV | 2024-07-01 | 128613 | USD
515 | MIP6 | APAVE | 2024-07-01 | 1712 | USD
516 | MIP6 | ERAM | 2024-07-01 | 21414.62 | USD
517 | MIP6 | PETROZONE | 2024-07-01 | 28556 | USD
518 | MIP6 | TEXIN | 2024-07-01 | 2887.2 | USD
519 | MIP6 | TQ CERT | 2024-07-01 | 510 | USD
520 | MIP6 | TECHNOCRAT | 2024-07-01 | 82433.15 | USD
521 | SM12 | INTERTEK | 2024-07-01 | 2030 | USD
522 | SM12 | DNV | 2024-07-01 | 6292 | USD
523 | SM12 | BV | 2024-07-01 | 5056.36 | USD
524 | SM12 | APAVE | 2024-07-01 | 4322 | USD
525 | SM12 | RINA | 2024-07-01 | 16356 | USD
526 | SM12 | ERAM | 2024-07-01 | 43382.38 | USD
527 | SM12 | PETROZONE | 2024-07-01 | 10996 | USD
528 | SM12 | TECHNOCRAT | 2024-07-01 | 5566 | USD
529 | SM12 | SGS | 2024-07-01 | 8739.54 | USD
530 | STA4 | DNV | 2024-07-01 | 4644 | USD
531 | STA4 | ERAM | 2024-07-01 | 9084 | USD
532 | IBRU | GISCO | 2024-07-01 | 10948.8 | USD
533 | SHN1 | GOODIN | 2024-07-01 | 19227000 | KRW
534 | SHN1 | A&A | 2024-07-01 | 19212260 | KRW
535 | SHN1 | KOTEC | 2024-07-01 | 22020000 | KRW
536 | ALOM | DNV | 2024-07-01 | 1400 | USD
537 | VEQU | APPLUS | 2024-06-01 | 6620 | USD
538 | MIP6 | INTERTEK | 2024-06-01 | 2983.6 | USD
539 | MIP6 | DNV | 2024-06-01 | 64441 | USD
540 | MIP6 | BV | 2024-06-01 | 626.46 | USD
541 | MIP6 | APAVE | 2024-06-01 | 2274 | USD
542 | MIP6 | ERAM | 2024-06-01 | 23759.22 | USD
543 | MIP6 | PETROZONE | 2024-06-01 | 55472 | USD
544 | MIP6 | TQ CERT | 2024-06-01 | 2300.9 | USD
545 | SM12 | INTERTEK | 2024-06-01 | 6100.56 | USD
546 | SM12 | DNV | 2024-06-01 | 2485 | USD
547 | SM12 | BV | 2024-06-01 | 11095.68 | USD
548 | SM12 | APAVE | 2024-06-01 | 13660.5 | USD
549 | SM12 | RINA | 2024-06-01 | 18751 | USD
550 | SM12 | ERAM | 2024-06-01 | 89855.69 | USD
551 | SM12 | PETROZONE | 2024-06-01 | 20160 | USD
552 | SM12 | TEXIN | 2024-06-01 | 45600.59 | USD
553 | SM12 | TQ CERT | 2024-06-01 | 847.7 | USD
554 | SM12 | TECHNOCRAT | 2024-06-01 | 15502 | USD
555 | SM12 | SGS | 2024-06-01 | 43416.3 | USD
556 | STA4 | INTERTEK | 2024-06-01 | 5948.16 | USD
557 | STA4 | ERAM | 2024-06-01 | 6001.4 | USD
558 | STA4 | PETROZONE | 2024-06-01 | 376 | USD
559 | IBRU | GISCO | 2024-06-01 | 16897.6 | USD
560 | SHN1 | GOODIN | 2024-06-01 | 17177000 | KRW
561 | SHN1 | A&A | 2024-06-01 | 19942025 | KRW
562 | SHN1 | KOTEC | 2024-06-01 | 12610000 | KRW
563 | ALOM | DNV | 2024-06-01 | 1200 | USD
564 | VEQU | APPLUS | 2024-05-01 | 7449 | USD
565 | MIP6 | INTERTEK | 2024-05-01 | 4586.4 | USD
566 | MIP6 | DNV | 2024-05-01 | 53689.41 | USD
567 | MIP6 | BV | 2024-05-01 | 6158.76 | USD
568 | MIP6 | APAVE | 2024-05-01 | 5010.28 | USD
569 | MIP6 | ERAM | 2024-05-01 | 12621.1 | USD
570 | MIP6 | PETROZONE | 2024-05-01 | 30192 | USD
571 | MIP6 | TEXIN | 2024-05-01 | 1467.4 | USD
572 | MIP6 | TECHNOCRAT | 2024-05-01 | 32890 | USD
573 | MIP6 | PETRO-Q | 2024-05-01 | 15816 | USD
574 | SM12 | INTERTEK | 2024-05-01 | 3664.02 | USD
575 | SM12 | DNV | 2024-05-01 | 3707.5 | USD
576 | SM12 | BV | 2024-05-01 | 8748.68 | USD
577 | SM12 | APAVE | 2024-05-01 | 8091 | USD
578 | SM12 | APPLUS | 2024-05-01 | 1151.6 | USD
579 | SM12 | RINA | 2024-05-01 | 24958.28 | USD
580 | SM12 | ERAM | 2024-05-01 | 71106.87 | USD
581 | SM12 | PETROZONE | 2024-05-01 | 12160 | USD
582 | SM12 | TEXIN | 2024-05-01 | 9537.27 | USD
583 | SM12 | TECHNOCRAT | 2024-05-01 | 3284.4 | USD
584 | SM12 | SGS | 2024-05-01 | 36409.02 | USD
585 | STA4 | ERAM | 2024-05-01 | 2712.4 | USD
586 | IBRU | GISCO | 2024-05-01 | 18051.4 | USD
587 | IBRU | BV | 2024-05-01 | 35482.45 | USD
588 | SHN1 | GOODIN | 2024-05-01 | 21317000 | KRW
589 | SHN1 | A&A | 2024-05-01 | 17258660 | KRW
590 | SHN1 | KOTEC | 2024-05-01 | 15960000 | KRW
591 | ALOM | DNV | 2024-05-01 | 5800 | USD
592 | VEQU | APPLUS | 2024-04-01 | 8023 | USD
593 | MIP6 | INTERTEK | 2024-04-01 | 6939.7 | USD
594 | MIP6 | DNV | 2024-04-01 | 208309.47 | USD
595 | MIP6 | BV | 2024-04-01 | 4079.76 | USD
596 | MIP6 | APAVE | 2024-04-01 | 2816 | USD
597 | MIP6 | RINA | 2024-04-01 | 2543.2 | USD
598 | MIP6 | ERAM | 2024-04-01 | 20124.65 | USD
599 | MIP6 | PETROZONE | 2024-04-01 | 76304 | USD
600 | MIP6 | TEXIN | 2024-04-01 | 4673.2 | USD
601 | MIP6 | TECHNOCRAT | 2024-04-01 | 31740 | USD
602 | SM12 | INTERTEK | 2024-04-01 | 14142 | USD
603 | SM12 | DNV | 2024-04-01 | 2484 | USD
604 | SM12 | BV | 2024-04-01 | 8604.18 | USD
605 | SM12 | APAVE | 2024-04-01 | 4582.5 | USD
606 | SM12 | RINA | 2024-04-01 | 32297.25 | USD
607 | SM12 | ERAM | 2024-04-01 | 94532.8 | USD
608 | SM12 | PETROZONE | 2024-04-01 | 21320 | USD
609 | SM12 | TEXIN | 2024-04-01 | 27561.56 | USD
610 | SM12 | TECHNOCRAT | 2024-04-01 | 10368.4 | USD
611 | SM12 | SGS | 2024-04-01 | 36115.67 | USD
612 | IBRU | GISCO | 2024-04-01 | 17373.8 | USD
613 | SHN1 | GOODIN | 2024-04-01 | 22294160 | KRW
614 | SHN1 | A&A | 2024-04-01 | 17910315 | KRW
615 | SHN1 | KOTEC | 2024-04-01 | 15320000 | KRW
616 | ALOM | DNV | 2024-04-01 | 5000 | USD
617 | VEQU | APPLUS | 2024-03-01 | 2480 | USD
618 | MIP6 | INTERTEK | 2024-03-01 | 2652.3 | USD
619 | MIP6 | DNV | 2024-03-01 | 89888.08 | USD
620 | MIP6 | BV | 2024-03-01 | 2546.46 | USD
621 | MIP6 | APAVE | 2024-03-01 | 6862.07 | USD
622 | MIP6 | RINA | 2024-03-01 | 466.4 | USD
623 | MIP6 | ERAM | 2024-03-01 | 40800.26 | USD
624 | MIP6 | PETROZONE | 2024-03-01 | 62064 | USD
625 | MIP6 | TEXIN | 2024-03-01 | 1221 | USD
626 | MIP6 | TECHNOCRAT | 2024-03-01 | 22632 | USD
627 | SM12 | INTERTEK | 2024-03-01 | 11343 | USD
628 | SM12 | DNV | 2024-03-01 | 6573.5 | USD
629 | SM12 | BV | 2024-03-01 | 8731 | USD
630 | SM12 | APAVE | 2024-03-01 | 11583 | USD
631 | SM12 | APPLUS | 2024-03-01 | 3067.64 | USD
632 | SM12 | RINA | 2024-03-01 | 30384 | USD
633 | SM12 | ERAM | 2024-03-01 | 72034.03 | USD
634 | SM12 | PETROZONE | 2024-03-01 | 43216 | USD
635 | SM12 | TEXIN | 2024-03-01 | 15400 | USD
636 | SM12 | TECHNOCRAT | 2024-03-01 | 11426.4 | USD
637 | SM12 | SGS | 2024-03-01 | 10936.92 | USD
638 | IBRU | GISCO | 2024-03-01 | 28515.8 | USD
639 | SHN1 | GOODIN | 2024-03-01 | 34115302 | KRW
640 | SHN1 | A&A | 2024-03-01 | 31106795 | KRW
641 | SHN1 | DNV | 2024-03-01 | 516560 | KRW
642 | SHN1 | KOTEC | 2024-03-01 | 11030828 | KRW
643 | ALOM | DNV | 2024-03-01 | 3800 | USD
644 | VEQU | APPLUS | 2024-02-01 | 2959 | USD
645 | MIP6 | INTERTEK | 2024-02-01 | 4101 | USD
646 | MIP6 | DNV | 2024-02-01 | 208580.1 | USD
647 | MIP6 | BV | 2024-02-01 | 6650.4 | USD
648 | MIP6 | APAVE | 2024-02-01 | 9447.38 | USD
649 | MIP6 | RINA | 2024-02-01 | 3300.6 | USD
650 | MIP6 | ERAM | 2024-02-01 | 82757.7 | USD
651 | MIP6 | PETROZONE | 2024-02-01 | 42224 | USD
652 | MIP6 | TEXIN | 2024-02-01 | 6046.6 | USD
653 | MIP6 | TQ CERT | 2024-02-01 | 2550 | USD
654 | MIP6 | TECHNOCRAT | 2024-02-01 | 60214 | USD
655 | SM12 | INTERTEK | 2024-02-01 | 11872 | USD
656 | SM12 | DNV | 2024-02-01 | 6692.5 | USD
657 | SM12 | BV | 2024-02-01 | 10630.18 | USD
658 | SM12 | APAVE | 2024-02-01 | 17486.5 | USD
659 | SM12 | APPLUS | 2024-02-01 | 1727.4 | USD
660 | SM12 | RINA | 2024-02-01 | 25263.6 | USD
661 | SM12 | ERAM | 2024-02-01 | 101737.59 | USD
662 | SM12 | PETROZONE | 2024-02-01 | 39676 | USD
663 | SM12 | TEXIN | 2024-02-01 | 14198.88 | USD
664 | SM12 | TECHNOCRAT | 2024-02-01 | 11426.4 | USD
665 | SM12 | SGS | 2024-02-01 | 33560.71 | USD
666 | IBRU | GISCO | 2024-02-01 | 23813.2 | USD
667 | SHN1 | GOODIN | 2024-02-01 | 24121830 | KRW
668 | SHN1 | A&A | 2024-02-01 | 5139333 | KRW
669 | SHN1 | DNV | 2024-02-01 | 939120 | KRW
670 | SHN1 | KOTEC | 2024-02-01 | 9308790 | KRW
671 | ALOM | DNV | 2024-02-01 | 1600 | USD
672 | VEQU | APPLUS | 2024-01-01 | 13439 | USD
673 | MIP6 | INTERTEK | 2024-01-01 | 6027.68 | USD
674 | MIP6 | DNV | 2024-01-01 | 46354.35 | USD
675 | MIP6 | APAVE | 2024-01-01 | 8195.28 | USD
676 | MIP6 | RINA | 2024-01-01 | 9279.4 | USD
677 | MIP6 | ERAM | 2024-01-01 | 53344.49 | USD
678 | MIP6 | PETROZONE | 2024-01-01 | 30532 | USD
679 | MIP6 | TEXIN | 2024-01-01 | 15175.24 | USD
680 | MIP6 | TQ CERT | 2024-01-01 | 4248 | USD
681 | MIP6 | TECHNOCRAT | 2024-01-01 | 37191 | USD
682 | SM12 | INTERTEK | 2024-01-01 | 6916.94 | USD
683 | SM12 | DNV | 2024-01-01 | 3485 | USD
684 | SM12 | BV | 2024-01-01 | 3657 | USD
685 | SM12 | APAVE | 2024-01-01 | 11699.5 | USD
686 | SM12 | APPLUS | 2024-01-01 | 2669.6 | USD
687 | SM12 | RINA | 2024-01-01 | 30459 | USD
688 | SM12 | ERAM | 2024-01-01 | 94788.94 | USD
689 | SM12 | PETROZONE | 2024-01-01 | 54912 | USD
690 | SM12 | TEXIN | 2024-01-01 | 4543.85 | USD
691 | SM12 | TECHNOCRAT | 2024-01-01 | 13662 | USD
692 | SM12 | SGS | 2024-01-01 | 41272.97 | USD
693 | IBRU | GISCO | 2024-01-01 | 32845.2 | USD
694 | SHN1 | GOODIN | 2024-01-01 | 23024242 | KRW
695 | SHN1 | A&A | 2024-01-01 | 5139333 | KRW
696 | SHN1 | DNV | 2024-01-01 | 939120 | KRW
697 | SHN1 | KOTEC | 2024-01-01 | 3878662 | KRW
698 | ALOM | DNV | 2024-01-01 | 1400 | USD
699 | VEQU | APPLUS | 2023-12-01 | 10254 | USD
700 | MIP6 | INTERTEK | 2023-12-01 | 17789.83 | USD
701 | MIP6 | DNV | 2023-12-01 | 198655.5 | USD
702 | MIP6 | BV | 2023-12-01 | 3840 | USD
703 | MIP6 | APAVE | 2023-12-01 | 1560 | USD
704 | MIP6 | RINA | 2023-12-01 | 11767.98 | USD
705 | MIP6 | ERAM | 2023-12-01 | 64454.89 | USD
706 | MIP6 | PETROZONE | 2023-12-01 | 65648 | USD
707 | MIP6 | TEXIN | 2023-12-01 | 4597 | USD
708 | MIP6 | TQ CERT | 2023-12-01 | 5802 | USD
709 | MIP6 | TECHNOCRAT | 2023-12-01 | 53383 | USD
710 | SM12 | INTERTEK | 2023-12-01 | 11640.6 | USD
711 | SM12 | DNV | 2023-12-01 | 12135.5 | USD
712 | SM12 | BV | 2023-12-01 | 1219 | USD
713 | SM12 | APAVE | 2023-12-01 | 14189 | USD
714 | SM12 | APPLUS | 2023-12-01 | 13269.75 | USD
715 | SM12 | RINA | 2023-12-01 | 42002.14 | USD
716 | SM12 | ERAM | 2023-12-01 | 101915.91 | USD
717 | SM12 | PETROZONE | 2023-12-01 | 31648 | USD
718 | SM12 | TEXIN | 2023-12-01 | 1372.57 | USD
719 | SM12 | TQ CERT | 2023-12-01 | 1695.4 | USD
720 | SM12 | TECHNOCRAT | 2023-12-01 | 736 | USD
721 | SM12 | SGS | 2023-12-01 | 23979.78 | USD
722 | IBRU | GISCO | 2023-12-01 | 42441.4 | USD
723 | SHN1 | GOODIN | 2023-12-01 | 45829153 | KRW
724 | SHN1 | A&A | 2023-12-01 | 16604405 | KRW
725 | SHN1 | DNV | 2023-12-01 | 1565200 | KRW
726 | SHN1 | KOTEC | 2023-12-01 | 12411720 | KRW
727 | ALOM | DNV | 2023-12-01 | 2400 | USD
728 | MIP6 | INTERTEK | 2023-11-01 | 10729.46 | USD
729 | MIP6 | DNV | 2023-11-01 | 138452 | USD
730 | MIP6 | BV | 2023-11-01 | 6790.8 | USD
731 | MIP6 | APAVE | 2023-11-01 | 9177.66 | USD
732 | MIP6 | RINA | 2023-11-01 | 22090.42 | USD
733 | MIP6 | ERAM | 2023-11-01 | 68170.67 | USD
734 | MIP6 | PETROZONE | 2023-11-01 | 77072 | USD
735 | MIP6 | TEXIN | 2023-11-01 | 11417.4 | USD
736 | MIP6 | TQ CERT | 2023-11-01 | 1728 | USD
737 | MIP6 | TECHNOCRAT | 2023-11-01 | 43539 | USD
738 | SM12 | INTERTEK | 2023-11-01 | 17793.57 | USD
739 | SM12 | DNV | 2023-11-01 | 3880 | USD
740 | SM12 | BV | 2023-11-01 | 8987.36 | USD
741 | SM12 | APAVE | 2023-11-01 | 28555.24 | USD
742 | SM12 | APPLUS | 2023-11-01 | 4187.6 | USD
743 | SM12 | RINA | 2023-11-01 | 23987.63 | USD
744 | SM12 | ERAM | 2023-11-01 | 105468.19 | USD
745 | SM12 | PETROZONE | 2023-11-01 | 45460 | USD
746 | SM12 | TEXIN | 2023-11-01 | 19641.38 | USD
747 | SM12 | SGS | 2023-11-01 | 27714.07 | USD
748 | IBRU | GISCO | 2023-11-01 | 60971.08 | USD
749 | ALOM | DNV | 2023-11-01 | 2000 | USD
750 | MIP6 | INTERTEK | 2023-10-01 | 15189.54 | USD
751 | MIP6 | DNV | 2023-10-01 | 288227.02 | USD
752 | MIP6 | BV | 2023-10-01 | 2142 | USD
753 | MIP6 | APAVE | 2023-10-01 | 5701.5 | USD
754 | MIP6 | APPLUS | 2023-10-01 | 845.16 | USD
755 | MIP6 | RINA | 2023-10-01 | 9168.34 | USD
756 | MIP6 | ERAM | 2023-10-01 | 29000.11 | USD
757 | MIP6 | PETROZONE | 2023-10-01 | 50256 | USD
758 | MIP6 | TEXIN | 2023-10-01 | 1550 | USD
759 | MIP6 | TQ CERT | 2023-10-01 | 1272 | USD
760 | MIP6 | TECHNOCRAT | 2023-10-01 | 43286 | USD
761 | SM12 | INTERTEK | 2023-10-01 | 27705.11 | USD
762 | SM12 | DNV | 2023-10-01 | 23487.53 | USD
763 | SM12 | BV | 2023-10-01 | 10554.68 | USD
764 | SM12 | APAVE | 2023-10-01 | 23117.5 | USD
765 | SM12 | APPLUS | 2023-10-01 | 5409 | USD
766 | SM12 | RINA | 2023-10-01 | 78328.56 | USD
767 | SM12 | ERAM | 2023-10-01 | 79390.67 | USD
768 | SM12 | PETROZONE | 2023-10-01 | 49856 | USD
769 | SM12 | TEXIN | 2023-10-01 | 3575.95 | USD
770 | SM12 | TECHNOCRAT | 2023-10-01 | 10626 | USD
771 | SM12 | SGS | 2023-10-01 | 36768.8 | USD
772 | IBRU | GISCO | 2023-10-01 | 48233.44 | USD
773 | ALOM | DNV | 2023-10-01 | 3250 | USD
774 | VEQU | APPLUS | 2023-09-01 | 11804 | USD
775 | MIP6 | INTERTEK | 2023-09-01 | 24114.28 | USD
776 | MIP6 | BV | 2023-09-01 | 13283.8 | USD
777 | MIP6 | APAVE | 2023-09-01 | 8193.21 | USD
778 | MIP6 | RINA | 2023-09-01 | 32324.4 | USD
779 | MIP6 | ERAM | 2023-09-01 | 89857.53 | USD
780 | MIP6 | PETROZONE | 2023-09-01 | 96412 | USD
781 | MIP6 | TEXIN | 2023-09-01 | 26118.52 | USD
782 | MIP6 | TQ CERT | 2023-09-01 | 11576 | USD
783 | MIP6 | TECHNOCRAT | 2023-09-01 | 82708 | USD
784 | SM12 | INTERTEK | 2023-09-01 | 16853.93 | USD
785 | SM12 | BV | 2023-09-01 | 12176.68 | USD
786 | SM12 | APAVE | 2023-09-01 | 3302.5 | USD
787 | SM12 | APPLUS | 2023-09-01 | 5478.8 | USD
788 | SM12 | RINA | 2023-09-01 | 100547.07 | USD
789 | SM12 | ERAM | 2023-09-01 | 114736.42 | USD
790 | SM12 | PETROZONE | 2023-09-01 | 60428 | USD
791 | SM12 | TEXIN | 2023-09-01 | 11527.35 | USD
792 | SM12 | SGS | 2023-09-01 | 30131.85 | USD
793 | IBRU | GISCO | 2023-09-01 | 53202.08 | USD
794 | ALOM | DNV | 2023-09-01 | 6360 | USD
795 | MIP6 | INTERTEK | 2023-08-01 | 34220.44 | USD
796 | MIP6 | BV | 2023-08-01 | 16060.8 | USD
797 | MIP6 | APAVE | 2023-08-01 | 15586.37 | USD
798 | MIP6 | APPLUS | 2023-08-01 | 2069.87 | USD
799 | MIP6 | RINA | 2023-08-01 | 25838.43 | USD
800 | MIP6 | ERAM | 2023-08-01 | 101189.92 | USD
801 | MIP6 | PETROZONE | 2023-08-01 | 66840 | USD
802 | MIP6 | TEXIN | 2023-08-01 | 24086.25 | USD
803 | MIP6 | TQ CERT | 2023-08-01 | 9193.44 | USD
804 | MIP6 | TECHNOCRAT | 2023-08-01 | 25185 | USD
805 | SM12 | INTERTEK | 2023-08-01 | 17518.9 | USD
806 | SM12 | BV | 2023-08-01 | 31127.66 | USD
807 | SM12 | APAVE | 2023-08-01 | 32668.5 | USD
808 | SM12 | APPLUS | 2023-08-01 | 6560.6 | USD
809 | SM12 | RINA | 2023-08-01 | 108504.82 | USD
810 | SM12 | ERAM | 2023-08-01 | 84167.77 | USD
811 | SM12 | PETROZONE | 2023-08-01 | 24644 | USD
812 | SM12 | TEXIN | 2023-08-01 | 1237.14 | USD
813 | SM12 | TQ CERT | 2023-08-01 | 1093.68 | USD
814 | SM12 | TECHNOCRAT | 2023-08-01 | 4485 | USD
815 | SM12 | SGS | 2023-08-01 | 37786.29 | USD
816 | IBRU | GISCO | 2023-08-01 | 52824.96 | USD
817 | ALOM | DNV | 2023-08-01 | 10200 | USD
818 | MIP6 | INTERTEK | 2023-07-01 | 30183.38 | USD
819 | MIP6 | DNV | 2023-07-01 | 179329.19 | USD
820 | MIP6 | BV | 2023-07-01 | 25116.48 | USD
821 | MIP6 | APAVE | 2023-07-01 | 6086.6 | USD
822 | MIP6 | RINA | 2023-07-01 | 17003.83 | USD
823 | MIP6 | ERAM | 2023-07-01 | 161169.77 | USD
824 | MIP6 | PETROZONE | 2023-07-01 | 64364 | USD
825 | MIP6 | TEXIN | 2023-07-01 | 9344.2 | USD
826 | MIP6 | TQ CERT | 2023-07-01 | 5869.73 | USD
827 | MIP6 | TECHNOCRAT | 2023-07-01 | 17319 | USD
828 | SM12 | INTERTEK | 2023-07-01 | 35376.5 | USD
829 | SM12 | DNV | 2023-07-01 | 7529.54 | USD
830 | SM12 | BV | 2023-07-01 | 29787.9 | USD
831 | SM12 | APAVE | 2023-07-01 | 6605 | USD
832 | SM12 | APPLUS | 2023-07-01 | 10868.62 | USD
833 | SM12 | RINA | 2023-07-01 | 85989.11 | USD
834 | SM12 | ERAM | 2023-07-01 | 95787.67 | USD
835 | SM12 | PETROZONE | 2023-07-01 | 42720 | USD
836 | SM12 | TEXIN | 2023-07-01 | 9634.62 | USD
837 | IBRU | GISCO | 2023-07-01 | 70732 | USD
838 | ALOM | DNV | 2023-07-01 | 5876 | USD
839 | VEQU | APPLUS | 2023-06-01 | 11022 | USD
840 | MIP6 | INTERTEK | 2023-06-01 | 18527.13 | USD
841 | MIP6 | BV | 2023-06-01 | 3570 | USD
842 | MIP6 | APAVE | 2023-06-01 | 4608 | USD
843 | MIP6 | RINA | 2023-06-01 | 6740 | USD
844 | MIP6 | ERAM | 2023-06-01 | 120989.43 | USD
845 | MIP6 | PETROZONE | 2023-06-01 | 47772 | USD
846 | MIP6 | TEXIN | 2023-06-01 | 54525.83 | USD
847 | MIP6 | TECHNOCRAT | 2023-06-01 | 34592 | USD
848 | SM12 | INTERTEK | 2023-06-01 | 6143.76 | USD
849 | SM12 | BV | 2023-06-01 | 20940.48 | USD
850 | SM12 | APAVE | 2023-06-01 | 8055 | USD
851 | SM12 | APPLUS | 2023-06-01 | 8724.2 | USD
852 | SM12 | RINA | 2023-06-01 | 45793.23 | USD
853 | SM12 | ERAM | 2023-06-01 | 103797.16 | USD
854 | SM12 | PETROZONE | 2023-06-01 | 9616 | USD
855 | SM12 | TEXIN | 2023-06-01 | 9210.89 | USD
856 | SM12 | SGS | 2023-06-01 | 14679.48 | USD
857 | IBRU | GISCO | 2023-06-01 | 69414 | USD
858 | ALOM | DNV | 2023-06-01 | 13566 | USD
859 | MIP6 | INTERTEK | 2023-05-01 | 24254.62 | USD
860 | MIP6 | DNV | 2023-05-01 | 85893.36 | USD
861 | MIP6 | BV | 2023-05-01 | 14229.76 | USD
862 | MIP6 | RINA | 2023-05-01 | 12488.59 | USD
863 | MIP6 | ERAM | 2023-05-01 | 88783.38 | USD
864 | MIP6 | PETROZONE | 2023-05-01 | 28984 | USD
865 | MIP6 | TEXIN | 2023-05-01 | 1422 | USD
866 | MIP6 | TQ CERT | 2023-05-01 | 4080 | USD
867 | MIP6 | TECHNOCRAT | 2023-05-01 | 86829.6 | USD
868 | SM12 | INTERTEK | 2023-05-01 | 42687.13 | USD
869 | SM12 | DNV | 2023-05-01 | 10900.01 | USD
870 | SM12 | BV | 2023-05-01 | 19774 | USD
871 | SM12 | APAVE | 2023-05-01 | 22041.28 | USD
872 | SM12 | APPLUS | 2023-05-01 | 7502.8 | USD
873 | SM12 | RINA | 2023-05-01 | 55524.9 | USD
874 | SM12 | ERAM | 2023-05-01 | 118137.23 | USD
875 | SM12 | PETROZONE | 2023-05-01 | 27808 | USD
876 | SM12 | SGS | 2023-05-01 | 29989.45 | USD
877 | SM12 | BROOKE | 2023-05-01 | 4156.44 | USD
878 | IBRU | GISCO | 2023-05-01 | 68400 | USD
879 | IBRU | BV | 2023-05-01 | 51805.15 | USD
880 | ALOM | DNV | 2023-05-01 | 7930 | USD
881 | MIP6 | INTERTEK | 2023-04-01 | 45559.54 | USD
882 | MIP6 | DNV | 2023-04-01 | 130908.8 | USD
883 | MIP6 | BV | 2023-04-01 | 21641 | USD
884 | MIP6 | APAVE | 2023-04-01 | 4520 | USD
885 | MIP6 | ERAM | 2023-04-01 | 138854.1 | USD
886 | MIP6 | PETROZONE | 2023-04-01 | 110412 | USD
887 | MIP6 | TEXIN | 2023-04-01 | 42015.31 | USD
888 | MIP6 | 3P | 2023-04-01 | 5249.03 | USD
889 | MIP6 | TQ CERT | 2023-04-01 | 1351.93 | USD
890 | MIP6 | TECHNOCRAT | 2023-04-01 | 31970 | USD
891 | SM12 | INTERTEK | 2023-04-01 | 14476.97 | USD
892 | SM12 | DNV | 2023-04-01 | 2797.5 | USD
893 | SM12 | BV | 2023-04-01 | 11710.48 | USD
894 | SM12 | APAVE | 2023-04-01 | 26293.76 | USD
895 | SM12 | APPLUS | 2023-04-01 | 4288.84 | USD
896 | SM12 | RINA | 2023-04-01 | 70580.82 | USD
897 | SM12 | ERAM | 2023-04-01 | 42748.32 | USD
898 | SM12 | PETROZONE | 2023-04-01 | 31476 | USD
899 | SM12 | 3P | 2023-04-01 | 1929.45 | USD
900 | SM12 | SGS | 2023-04-01 | 38974.23 | USD
901 | SM12 | BROOKE | 2023-04-01 | 5167.8 | USD
902 | IBRU | GISCO | 2023-04-01 | 95004.2 | USD
903 | ALOM | DNV | 2023-04-01 | 12120 | USD
904 | MIP6 | INTERTEK | 2023-03-01 | 33746.84 | USD
905 | MIP6 | DNV | 2023-03-01 | 73253.96 | USD
906 | MIP6 | BV | 2023-03-01 | 24556.11 | USD
907 | MIP6 | APAVE | 2023-03-01 | 3192 | USD
908 | MIP6 | APPLUS | 2023-03-01 | 8712.9 | USD
909 | MIP6 | RINA | 2023-03-01 | 19734.14 | USD
910 | MIP6 | ERAM | 2023-03-01 | 171312.14 | USD
911 | MIP6 | PETROZONE | 2023-03-01 | 125852 | USD
912 | MIP6 | TEXIN | 2023-03-01 | 10398.2 | USD
913 | SM12 | INTERTEK | 2023-03-01 | 28409.45 | USD
914 | SM12 | DNV | 2023-03-01 | 8458.5 | USD
915 | SM12 | BV | 2023-03-01 | 11938.36 | USD
916 | SM12 | APAVE | 2023-03-01 | 24249.56 | USD
917 | SM12 | APPLUS | 2023-03-01 | 17778.32 | USD
918 | SM12 | RINA | 2023-03-01 | 86599.85 | USD
919 | SM12 | ERAM | 2023-03-01 | 122415.48 | USD
920 | SM12 | PETROZONE | 2023-03-01 | 40076 | USD
921 | SM12 | SGS | 2023-03-01 | 20529.07 | USD
922 | IBRU | GISCO | 2023-03-01 | 90652.4 | USD
923 | ALOM | DNV | 2023-03-01 | 8290 | USD
924 | MIP6 | INTERTEK | 2023-02-01 | 21776.42 | USD
925 | MIP6 | DNV | 2023-02-01 | 72900.33 | USD
926 | MIP6 | BV | 2023-02-01 | 25083.56 | USD
927 | MIP6 | APAVE | 2023-02-01 | 10153.6 | USD
928 | MIP6 | APPLUS | 2023-02-01 | 4062.3 | USD
929 | MIP6 | RINA | 2023-02-01 | 9351.26 | USD
930 | MIP6 | ERAM | 2023-02-01 | 133366.55 | USD
931 | MIP6 | PETROZONE | 2023-02-01 | 65100 | USD
932 | MIP6 | TEXIN | 2023-02-01 | 21670.08 | USD
933 | SM12 | INTERTEK | 2023-02-01 | 10278.15 | USD
934 | SM12 | DNV | 2023-02-01 | 6364 | USD
935 | SM12 | BV | 2023-02-01 | 3668.92 | USD
936 | SM12 | APAVE | 2023-02-01 | 23809.5 | USD
937 | SM12 | APPLUS | 2023-02-01 | 6146.92 | USD
938 | SM12 | RINA | 2023-02-01 | 66431.1 | USD
939 | SM12 | ERAM | 2023-02-01 | 135712.27 | USD
940 | SM12 | PETROZONE | 2023-02-01 | 25036 | USD
941 | SM12 | TEXIN | 2023-02-01 | 5600 | USD
942 | IBRU | GISCO | 2023-02-01 | 89102.6 | USD
943 | IBRU | BV | 2023-02-01 | 78512.6 | USD
944 | ALOM | DNV | 2023-02-01 | 10518 | USD
945 | MIP6 | INTERTEK | 2023-01-01 | 21909.49 | USD
946 | MIP6 | DNV | 2023-01-01 | 62819.67 | USD
947 | MIP6 | BV | 2023-01-01 | 36540.76 | USD
948 | MIP6 | APAVE | 2023-01-01 | 6079.4 | USD
949 | MIP6 | RINA | 2023-01-01 | 7590 | USD
950 | MIP6 | ERAM | 2023-01-01 | 120297.47 | USD
951 | MIP6 | PETROZONE | 2023-01-01 | 44174 | USD
952 | MIP6 | TEXIN | 2023-01-01 | 15621.41 | USD
953 | MIP6 | TQ CERT | 2023-01-01 | 5610 | USD
954 | SM12 | INTERTEK | 2023-01-01 | 20725 | USD
955 | SM12 | DNV | 2023-01-01 | 7592 | USD
956 | SM12 | BV | 2023-01-01 | 10731.8 | USD
957 | SM12 | APAVE | 2023-01-01 | 4636 | USD
958 | SM12 | APPLUS | 2023-01-01 | 17832.5 | USD
959 | SM12 | RINA | 2023-01-01 | 79557.59 | USD
960 | SM12 | ERAM | 2023-01-01 | 87024.47 | USD
961 | SM12 | PETROZONE | 2023-01-01 | 18136 | USD
962 | SM12 | TEXIN | 2023-01-01 | 1416.09 | USD
963 | IBRU | GISCO | 2023-01-01 | 139722.2 | USD
964 | ALOM | DNV | 2023-01-01 | 12816 | USD
965 | VEQU | APPLUS | 2022-12-01 | 646 | USD
966 | MIP6 | INTERTEK | 2022-12-01 | 48984.77 | USD
967 | MIP6 | DNV | 2022-12-01 | 104892.94 | USD
968 | MIP6 | BV | 2022-12-01 | 11372.7 | USD
969 | MIP6 | APAVE | 2022-12-01 | 9992.5 | USD
970 | MIP6 | RINA | 2022-12-01 | 13647.76 | USD
971 | MIP6 | ERAM | 2022-12-01 | 177250.35 | USD
972 | MIP6 | PETROZONE | 2022-12-01 | 54393 | USD
973 | MIP6 | TEXIN | 2022-12-01 | 12274.2 | USD
974 | MIP6 | TQ CERT | 2022-12-01 | 2040 | USD
975 | SM12 | INTERTEK | 2022-12-01 | 18760.66 | USD
976 | SM12 | DNV | 2022-12-01 | 7685 | USD
977 | SM12 | BV | 2022-12-01 | 357 | USD
978 | SM12 | APAVE | 2022-12-01 | 13813.12 | USD
979 | SM12 | APPLUS | 2022-12-01 | 9250.24 | USD
980 | SM12 | RINA | 2022-12-01 | 79416.16 | USD
981 | SM12 | ERAM | 2022-12-01 | 105978.43 | USD
982 | SM12 | PETROZONE | 2022-12-01 | 33760 | USD
983 | SM12 | TEXIN | 2022-12-01 | 2400 | USD
984 | IBRU | GISCO | 2022-12-01 | 113999 | USD
985 | ALOM | DNV | 2022-12-01 | 10726 | USD
986 | MIP6 | INTERTEK | 2022-11-01 | 57966.11 | USD
987 | MIP6 | DNV | 2022-11-01 | 63132.87 | USD
988 | MIP6 | BV | 2022-11-01 | 59896.83 | USD
989 | MIP6 | APAVE | 2022-11-01 | 6973.5 | USD
990 | MIP6 | RINA | 2022-11-01 | 5274 | USD
991 | MIP6 | ERAM | 2022-11-01 | 195072.57 | USD
992 | MIP6 | PETROZONE | 2022-11-01 | 99631.3 | USD
993 | MIP6 | TEXIN | 2022-11-01 | 26828.2 | USD
994 | SM12 | INTERTEK | 2022-11-01 | 18812.3 | USD
995 | SM12 | DNV | 2022-11-01 | 33614.09 | USD
996 | SM12 | BV | 2022-11-01 | 6148.5 | USD
997 | SM12 | APAVE | 2022-11-01 | 15760 | USD
998 | SM12 | APPLUS | 2022-11-01 | 3032.12 | USD
999 | SM12 | RINA | 2022-11-01 | 33303.74 | USD
1000 | SM12 | ERAM | 2022-11-01 | 81538.2 | USD
1001 | SM12 | PETROZONE | 2022-11-01 | 25904 | USD
1002 | SM12 | TEXIN | 2022-11-01 | 4400 | USD
1003 | IBRU | GISCO | 2022-11-01 | 114210 | USD
1004 | IBRU | BV | 2022-11-01 | 204559.5 | USD
1005 | ALOM | DNV | 2022-11-01 | 10540 | USD
1006 | VEQU | APPLUS | 2022-10-01 | 376 | USD
1007 | MIP6 | INTERTEK | 2022-10-01 | 35494.82 | USD
1008 | MIP6 | DNV | 2022-10-01 | 44071.5 | USD
1009 | MIP6 | BV | 2022-10-01 | 3372.68 | USD
1010 | MIP6 | APAVE | 2022-10-01 | 2936 | USD
1011 | MIP6 | RINA | 2022-10-01 | 6313.5 | USD
1012 | MIP6 | ERAM | 2022-10-01 | 61391.85 | USD
1013 | MIP6 | PETROZONE | 2022-10-01 | 25087.3 | USD
1014 | MIP6 | TEXIN | 2022-10-01 | 18905.4 | USD
1015 | SM12 | INTERTEK | 2022-10-01 | 22101.97 | USD
1016 | SM12 | DNV | 2022-10-01 | 3589 | USD
1017 | SM12 | BV | 2022-10-01 | 10420.5 | USD
1018 | SM12 | APAVE | 2022-10-01 | 6024 | USD
1019 | SM12 | RINA | 2022-10-01 | 23720.5 | USD
1020 | SM12 | ERAM | 2022-10-01 | 22410.42 | USD
1021 | SM12 | PETROZONE | 2022-10-01 | 6760 | USD
1022 | IBRU | GISCO | 2022-10-01 | 107469.76 | USD
1023 | ALOM | DNV | 2022-10-01 | 7285 | USD
1024 | VEQU | APPLUS | 2022-09-01 | 1376 | USD
1025 | MIP6 | INTERTEK | 2022-09-01 | 43077.15 | USD
1026 | MIP6 | DNV | 2022-09-01 | 42518.11 | USD
1027 | MIP6 | BV | 2022-09-01 | 78879.4 | USD
1028 | MIP6 | APAVE | 2022-09-01 | 4385 | USD
1029 | MIP6 | RINA | 2022-09-01 | 22197 | USD
1030 | MIP6 | ERAM | 2022-09-01 | 90817.7 | USD
1031 | MIP6 | PETROZONE | 2022-09-01 | 19496 | USD
1032 | MIP6 | TEXIN | 2022-09-01 | 31246.13 | USD
1033 | SM12 | INTERTEK | 2022-09-01 | 20399.23 | USD
1034 | SM12 | DNV | 2022-09-01 | 31054 | USD
1035 | SM12 | BV | 2022-09-01 | 1253 | USD
1036 | SM12 | APAVE | 2022-09-01 | 7100 | USD
1037 | SM12 | RINA | 2022-09-01 | 39438.05 | USD
1038 | SM12 | ERAM | 2022-09-01 | 59435.1 | USD
1039 | SM12 | PETROZONE | 2022-09-01 | 7232 | USD
1040 | SM12 | TEXIN | 2022-09-01 | 2184.95 | USD
1041 | IBRU | GISCO | 2022-09-01 | 72731.06 | USD
1042 | ALOM | DNV | 2022-09-01 | 9630 | USD
1043 | MIP6 | INTERTEK | 2022-08-01 | 39334.24 | USD
1044 | MIP6 | DNV | 2022-08-01 | 40570.51 | USD
1045 | MIP6 | BV | 2022-08-01 | 12837.46 | USD
1046 | MIP6 | RINA | 2022-08-01 | 11498.71 | USD
1047 | MIP6 | ERAM | 2022-08-01 | 32726.21 | USD
1048 | MIP6 | PETROZONE | 2022-08-01 | 35048 | USD
1049 | MIP6 | TEXIN | 2022-08-01 | 3200 | USD
1050 | SM12 | INTERTEK | 2022-08-01 | 16785.37 | USD
1051 | SM12 | DNV | 2022-08-01 | 10566 | USD
1052 | SM12 | BV | 2022-08-01 | 7687.32 | USD
1053 | SM12 | APPLUS | 2022-08-01 | 622.96 | USD
1054 | SM12 | RINA | 2022-08-01 | 16279.53 | USD
1055 | SM12 | ERAM | 2022-08-01 | 39031.91 | USD
1056 | SM12 | PETROZONE | 2022-08-01 | 3840 | USD
1057 | IBRU | GISCO | 2022-08-01 | 79420.2 | USD
1058 | IBRU | BV | 2022-08-01 | 29206 | USD
1059 | ALOM | DNV | 2022-08-01 | 13812 | USD
1060 | MIP6 | INTERTEK | 2022-07-01 | 34101.1 | USD
1061 | MIP6 | DNV | 2022-07-01 | 34058.51 | USD
1062 | MIP6 | BV | 2022-07-01 | 4332.64 | USD
1063 | MIP6 | APAVE | 2022-07-01 | 1686.5 | USD
1064 | MIP6 | RINA | 2022-07-01 | 2617.95 | USD
1065 | MIP6 | ERAM | 2022-07-01 | 80379.26 | USD
1066 | MIP6 | PETROZONE | 2022-07-01 | 35152 | USD
1067 | MIP6 | TEXIN | 2022-07-01 | 29915.76 | USD
1068 | SM12 | INTERTEK | 2022-07-01 | 21689.26 | USD
1069 | SM12 | DNV | 2022-07-01 | 21447 | USD
1070 | SM12 | APAVE | 2022-07-01 | 12976 | USD
1071 | SM12 | RINA | 2022-07-01 | 17963.25 | USD
1072 | SM12 | ERAM | 2022-07-01 | 31459.85 | USD
1073 | SM12 | PETROZONE | 2022-07-01 | 5120 | USD
1074 | SM12 | TEXIN | 2022-07-01 | 400 | USD
1075 | IBRU | GISCO | 2022-07-01 | 54896 | USD
1076 | IBRU | BV | 2022-07-01 | 79290.15 | USD
1077 | ALOM | DNV | 2022-07-01 | 11480 | USD
1078 | VEQU | APPLUS | 2022-06-01 | 1504 | USD
1079 | MIP6 | INTERTEK | 2022-06-01 | 29069.62 | USD
1080 | MIP6 | DNV | 2022-06-01 | 18889.87 | USD
1081 | MIP6 | BV | 2022-06-01 | 5894.6 | USD
1082 | MIP6 | APAVE | 2022-06-01 | 768 | USD
1083 | MIP6 | RINA | 2022-06-01 | 15175.4 | USD
1084 | MIP6 | ERAM | 2022-06-01 | 38290.3 | USD
1085 | MIP6 | PETROZONE | 2022-06-01 | 5208 | USD
1086 | MIP6 | TEXIN | 2022-06-01 | 22664.77 | USD
1087 | SM12 | INTERTEK | 2022-06-01 | 12800.44 | USD
1088 | SM12 | DNV | 2022-06-01 | 36384 | USD
1089 | SM12 | BV | 2022-06-01 | 503.5 | USD
1090 | SM12 | APAVE | 2022-06-01 | 3456 | USD
1091 | SM12 | APPLUS | 2022-06-01 | 1800 | USD
1092 | SM12 | RINA | 2022-06-01 | 35575.15 | USD
1093 | SM12 | ERAM | 2022-06-01 | 15809.92 | USD
1094 | SM12 | PETROZONE | 2022-06-01 | 4640 | USD
1095 | IBRU | GISCO | 2022-06-01 | 45621.2 | USD
1096 | ALOM | DNV | 2022-06-01 | 13020 | USD
1097 | MIP6 | INTERTEK | 2022-05-01 | 34668.5 | USD
1098 | MIP6 | DNV | 2022-05-01 | 47398.09 | USD
1099 | MIP6 | BV | 2022-05-01 | 2293.84 | USD
1100 | MIP6 | APAVE | 2022-05-01 | 1280 | USD
1101 | MIP6 | RINA | 2022-05-01 | 12245 | USD
1102 | MIP6 | ERAM | 2022-05-01 | 91042.19 | USD
1103 | MIP6 | PETROZONE | 2022-05-01 | 29696 | USD
1104 | MIP6 | TEXIN | 2022-05-01 | 29602.22 | USD
1105 | MIP6 | TQ CERT | 2022-05-01 | 510 | USD
1106 | SM12 | INTERTEK | 2022-05-01 | 15554.19 | USD
1107 | SM12 | DNV | 2022-05-01 | 8311.5 | USD
1108 | SM12 | BV | 2022-05-01 | 1880 | USD
1109 | SM12 | APAVE | 2022-05-01 | 25812 | USD
1110 | SM12 | APPLUS | 2022-05-01 | 7674 | USD
1111 | SM12 | RINA | 2022-05-01 | 19825.55 | USD
1112 | SM12 | ERAM | 2022-05-01 | 19980.52 | USD
1113 | SM12 | TEXIN | 2022-05-01 | 1702.97 | USD
1114 | IBRU | GISCO | 2022-05-01 | 38231.26 | USD
1115 | ALOM | DNV | 2022-05-01 | 12485 | USD
1116 | MIP6 | INTERTEK | 2022-04-01 | 50563.46 | USD
1117 | MIP6 | DNV | 2022-04-01 | 51546 | USD
1118 | MIP6 | BV | 2022-04-01 | 1489.6 | USD
1119 | MIP6 | APAVE | 2022-04-01 | 3448 | USD
1120 | MIP6 | RINA | 2022-04-01 | 13798.1 | USD
1121 | MIP6 | ERAM | 2022-04-01 | 61052.65 | USD
1122 | MIP6 | PETROZONE | 2022-04-01 | 28032 | USD
1123 | MIP6 | TEXIN | 2022-04-01 | 16718.17 | USD
1124 | SM12 | INTERTEK | 2022-04-01 | 18266.86 | USD
1125 | SM12 | DNV | 2022-04-01 | 16615.01 | USD
1126 | SM12 | BV | 2022-04-01 | 3712.36 | USD
1127 | SM12 | APAVE | 2022-04-01 | 2560 | USD
1128 | SM12 | APPLUS | 2022-04-01 | 9000 | USD
1129 | SM12 | RINA | 2022-04-01 | 19213.17 | USD
1130 | SM12 | ERAM | 2022-04-01 | 29594.63 | USD
1131 | SM12 | PETROZONE | 2022-04-01 | 576 | USD
1132 | SM12 | TEXIN | 2022-04-01 | 1708.7 | USD
1133 | ALOM | DNV | 2022-04-01 | 8330 | USD
1134 | MIP6 | INTERTEK | 2022-03-01 | 14197.28 | USD
1135 | MIP6 | DNV | 2022-03-01 | 38313.08 | USD
1136 | MIP6 | BV | 2022-03-01 | 376 | USD
1137 | MIP6 | APAVE | 2022-03-01 | 5343.5 | USD
1138 | MIP6 | RINA | 2022-03-01 | 7530 | USD
1139 | MIP6 | ERAM | 2022-03-01 | 6454.67 | USD
1140 | MIP6 | PETROZONE | 2022-03-01 | 6880 | USD
1141 | MIP6 | TEXIN | 2022-03-01 | 474 | USD
1142 | SM12 | INTERTEK | 2022-03-01 | 7843.46 | USD
1143 | SM12 | DNV | 2022-03-01 | 840 | USD
1144 | SM12 | BV | 2022-03-01 | 2256 | USD
1145 | SM12 | APAVE | 2022-03-01 | 5120 | USD
1146 | SM12 | APPLUS | 2022-03-01 | 5406.06 | USD
1147 | SM12 | RINA | 2022-03-01 | 16284.62 | USD
1148 | SM12 | ERAM | 2022-03-01 | 29178.3 | USD
1149 | SM12 | PETROZONE | 2022-03-01 | 2304 | USD
1150 | SM12 | TEXIN | 2022-03-01 | 2771.81 | USD
1151 | ALOM | DNV | 2022-03-01 | 7934 | USD
1152 | MIP6 | INTERTEK | 2022-02-01 | 35312.54 | USD
1153 | MIP6 | APAVE | 2022-02-01 | 256 | USD
1154 | MIP6 | RINA | 2022-02-01 | 8609.2 | USD
1155 | MIP6 | ERAM | 2022-02-01 | 42858.61 | USD
1156 | MIP6 | PETROZONE | 2022-02-01 | 19920 | USD
1157 | MIP6 | TEXIN | 2022-02-01 | 11724.6 | USD
1158 | SM12 | INTERTEK | 2022-02-01 | 9179.38 | USD
1159 | SM12 | DNV | 2022-02-01 | 280 | USD
1160 | SM12 | BV | 2022-02-01 | 3008 | USD
1161 | SM12 | APAVE | 2022-02-01 | 7245.25 | USD
1162 | SM12 | APPLUS | 2022-02-01 | 9741.45 | USD
1163 | SM12 | RINA | 2022-02-01 | 18725.8 | USD
1164 | SM12 | ERAM | 2022-02-01 | 35592.98 | USD
1165 | SM12 | PETROZONE | 2022-02-01 | 3808 | USD
1166 | IBRU | BV | 2022-02-01 | 257090.33 | USD
1167 | ALOM | DNV | 2022-02-01 | 11930 | USD
1168 | MIP6 | INTERTEK | 2022-01-01 | 33471.99 | USD
1169 | MIP6 | DNV | 2022-01-01 | 43061.63 | USD
1170 | MIP6 | BV | 2022-01-01 | 3220.8 | USD
1171 | MIP6 | APAVE | 2022-01-01 | 5520 | USD
1172 | MIP6 | RINA | 2022-01-01 | 7348.3 | USD
1173 | MIP6 | ERAM | 2022-01-01 | 51164.52 | USD
1174 | MIP6 | PETROZONE | 2022-01-01 | 25824 | USD
1175 | MIP6 | TEXIN | 2022-01-01 | 6023.4 | USD
1176 | SM12 | INTERTEK | 2022-01-01 | 21545.05 | USD
1177 | SM12 | DNV | 2022-01-01 | 280 | USD
1178 | SM12 | BV | 2022-01-01 | 6432 | USD
1179 | SM12 | APAVE | 2022-01-01 | 3896 | USD
1180 | SM12 | RINA | 2022-01-01 | 4306.22 | USD
1181 | SM12 | ERAM | 2022-01-01 | 20808.71 | USD
1182 | SM12 | PETROZONE | 2022-01-01 | 1152 | USD
1183 | ALOM | DNV | 2022-01-01 | 10336 | USD
1184 | MIP6 | INTERTEK | 2021-12-01 | 44942.41 | USD
1185 | MIP6 | DNV | 2021-12-01 | 31213.55 | USD
1186 | MIP6 | APAVE | 2021-12-01 | 6576 | USD
1187 | MIP6 | RINA | 2021-12-01 | 5429.9 | USD
1188 | MIP6 | ERAM | 2021-12-01 | 46086.76 | USD
1189 | MIP6 | PETROZONE | 2021-12-01 | 11008 | USD
1190 | MIP6 | TEXIN | 2021-12-01 | 16817.04 | USD
1191 | SM12 | INTERTEK | 2021-12-01 | 17154.61 | USD
1192 | SM12 | BV | 2021-12-01 | 752 | USD
1193 | SM12 | APAVE | 2021-12-01 | 2912 | USD
1194 | SM12 | RINA | 2021-12-01 | 2912.05 | USD
1195 | SM12 | ERAM | 2021-12-01 | 37936.03 | USD
1196 | SM12 | PETROZONE | 2021-12-01 | 576 | USD
1197 | IBRU | GISCO | 2021-12-01 | 42286.4 | USD
1198 | IBRU | BV | 2021-12-01 | 114108.83 | USD
1199 | ALOM | DNV | 2021-12-01 | 11728.6 | USD
1200 | MIP6 | INTERTEK | 2021-11-01 | 30002.7 | USD
1201 | MIP6 | DNV | 2021-11-01 | 29138.47 | USD
1202 | MIP6 | APAVE | 2021-11-01 | 9455.5 | USD
1203 | MIP6 | RINA | 2021-11-01 | 3671.8 | USD
1204 | MIP6 | ERAM | 2021-11-01 | 63036.01 | USD
1205 | MIP6 | PETROZONE | 2021-11-01 | 32608 | USD
1206 | MIP6 | TEXIN | 2021-11-01 | 18100.06 | USD
1207 | SM12 | INTERTEK | 2021-11-01 | 12582.46 | USD
1208 | SM12 | DNV | 2021-11-01 | 560 | USD
1209 | SM12 | APAVE | 2021-11-01 | 4384 | USD
1210 | SM12 | APPLUS | 2021-11-01 | 7295.4 | USD
1211 | SM12 | RINA | 2021-11-01 | 722.68 | USD
1212 | SM12 | ERAM | 2021-11-01 | 21553.96 | USD
1213 | SM12 | PETROZONE | 2021-11-01 | 2016 | USD
1214 | ALOM | DNV | 2021-11-01 | 10764.6 | USD
1215 | MIP6 | INTERTEK | 2021-10-01 | 49669.87 | USD
1216 | MIP6 | DNV | 2021-10-01 | 28047.05 | USD
1217 | MIP6 | BV | 2021-10-01 | 752 | USD
1218 | MIP6 | APAVE | 2021-10-01 | 14048 | USD
1219 | MIP6 | RINA | 2021-10-01 | 6002.4 | USD
1220 | MIP6 | ERAM | 2021-10-01 | 42023.4 | USD
1221 | MIP6 | PETROZONE | 2021-10-01 | 21952 | USD
1222 | MIP6 | TEXIN | 2021-10-01 | 11136.96 | USD
1223 | SM12 | INTERTEK | 2021-10-01 | 3461.76 | USD
1224 | SM12 | DNV | 2021-10-01 | 479.5 | USD
1225 | SM12 | APPLUS | 2021-10-01 | 2595.8 | USD
1226 | SM12 | ERAM | 2021-10-01 | 12325.15 | USD
1227 | ALOM | DNV | 2021-10-01 | 5390 | USD
1228 | MIP6 | INTERTEK | 2021-09-01 | 50344.28 | USD
1229 | MIP6 | DNV | 2021-09-01 | 8580.25 | USD
1230 | MIP6 | APAVE | 2021-09-01 | 5024 | USD
1231 | MIP6 | RINA | 2021-09-01 | 9229.2 | USD
1232 | MIP6 | ERAM | 2021-09-01 | 78240.62 | USD
1233 | MIP6 | PETROZONE | 2021-09-01 | 26784 | USD
1234 | MIP6 | TEXIN | 2021-09-01 | 15638.19 | USD
1235 | SM12 | INTERTEK | 2021-09-01 | 3766.4 | USD
1236 | SM12 | APPLUS | 2021-09-01 | 820 | USD
1237 | SM12 | ERAM | 2021-09-01 | 12798.3 | USD
1238 | ALOM | DNV | 2021-09-01 | 9820 | USD
1239 | MIP6 | INTERTEK | 2021-08-01 | 30468.19 | USD
1240 | MIP6 | DNV | 2021-08-01 | 12950.76 | USD
1241 | MIP6 | BV | 2021-08-01 | 5180 | USD
1242 | MIP6 | APAVE | 2021-08-01 | 6712 | USD
1243 | MIP6 | RINA | 2021-08-01 | 5364.4 | USD
1244 | MIP6 | ERAM | 2021-08-01 | 32752.26 | USD
1245 | MIP6 | PETROZONE | 2021-08-01 | 19976 | USD
1246 | MIP6 | TEXIN | 2021-08-01 | 13311.64 | USD
1247 | SM12 | INTERTEK | 2021-08-01 | 2837.6 | USD
1248 | SM12 | APPLUS | 2021-08-01 | 9890.85 | USD
1249 | SM12 | ERAM | 2021-08-01 | 8098.1 | USD
1250 | ALOM | DNV | 2021-08-01 | 6360 | USD
1251 | MIP6 | INTERTEK | 2021-07-01 | 44118.3 | USD
1252 | MIP6 | DNV | 2021-07-01 | 7873.5 | USD
1253 | MIP6 | BV | 2021-07-01 | 1596.8 | USD
1254 | MIP6 | APAVE | 2021-07-01 | 4096 | USD
1255 | MIP6 | RINA | 2021-07-01 | 13250.38 | USD
1256 | MIP6 | ERAM | 2021-07-01 | 78251.19 | USD
1257 | MIP6 | PETROZONE | 2021-07-01 | 17488 | USD
1258 | MIP6 | TEXIN | 2021-07-01 | 14256.8 | USD
1259 | SM12 | INTERTEK | 2021-07-01 | 1837.6 | USD
1260 | SM12 | APPLUS | 2021-07-01 | 2870 | USD
1261 | SM12 | ERAM | 2021-07-01 | 9467.2 | USD
1262 | ALOM | DNV | 2021-07-01 | 8360 | USD
1263 | MIP6 | INTERTEK | 2021-06-01 | 27983.94 | USD
1264 | MIP6 | DNV | 2021-06-01 | 5322.25 | USD
1265 | MIP6 | BV | 2021-06-01 | 3245.6 | USD
1266 | MIP6 | APAVE | 2021-06-01 | 5214 | USD
1267 | MIP6 | RINA | 2021-06-01 | 3635.58 | USD
1268 | MIP6 | ERAM | 2021-06-01 | 31359.93 | USD
1269 | MIP6 | PETROZONE | 2021-06-01 | 15696 | USD
1270 | MIP6 | TEXIN | 2021-06-01 | 12458.4 | USD
1271 | SM12 | INTERTEK | 2021-06-01 | 3766.4 | USD
1272 | SM12 | APPLUS | 2021-06-01 | 2460 | USD
1273 | SM12 | RINA | 2021-06-01 | 727.32 | USD
1274 | SM12 | ERAM | 2021-06-01 | 856.5 | USD
1275 | SM12 | PETROZONE | 2021-06-01 | 576 | USD
1276 | MIP6 | INTERTEK | 2021-05-01 | 25934.71 | USD
1277 | MIP6 | DNV | 2021-05-01 | 4083.75 | USD
1278 | MIP6 | BV | 2021-05-01 | 5739.2 | USD
1279 | MIP6 | APAVE | 2021-05-01 | 5240 | USD
1280 | MIP6 | RINA | 2021-05-01 | 11394.96 | USD
1281 | MIP6 | ERAM | 2021-05-01 | 41153.34 | USD
1282 | MIP6 | PETROZONE | 2021-05-01 | 13008 | USD
1283 | MIP6 | TEXIN | 2021-05-01 | 29134.07 | USD
1284 | SM12 | INTERTEK | 2021-05-01 | 7071.02 | USD
1285 | SM12 | APAVE | 2021-05-01 | 640 | USD
1286 | SM12 | APPLUS | 2021-05-01 | 4100 | USD
1287 | SM12 | ERAM | 2021-05-01 | 333.5 | USD
1288 | ALOM | DNV | 2021-05-01 | 2200 | USD
1289 | MIP6 | INTERTEK | 2021-04-01 | 23954.64 | USD
1290 | MIP6 | DNV | 2021-04-01 | 8334.5 | USD
1291 | MIP6 | BV | 2021-04-01 | 7520 | USD
1292 | MIP6 | APAVE | 2021-04-01 | 3824 | USD
1293 | MIP6 | RINA | 2021-04-01 | 2629 | USD
1294 | MIP6 | ERAM | 2021-04-01 | 35256.61 | USD
1295 | MIP6 | PETROZONE | 2021-04-01 | 8352 | USD
1296 | MIP6 | TEXIN | 2021-04-01 | 9910.42 | USD
1297 | SM12 | INTERTEK | 2021-04-01 | 4015.2 | USD
1298 | SM12 | APPLUS | 2021-04-01 | 2460 | USD
1299 | MIP6 | INTERTEK | 2021-03-01 | 25124.36 | USD
1300 | MIP6 | DNV | 2021-03-01 | 3498.25 | USD
1301 | MIP6 | BV | 2021-03-01 | 1128 | USD
1302 | MIP6 | APAVE | 2021-03-01 | 5376 | USD
1303 | MIP6 | RINA | 2021-03-01 | 1577.4 | USD
1304 | MIP6 | ERAM | 2021-03-01 | 40389 | USD
1305 | MIP6 | PETROZONE | 2021-03-01 | 8544 | USD
1306 | MIP6 | TEXIN | 2021-03-01 | 16237.74 | USD
1307 | SM12 | INTERTEK | 2021-03-01 | 6879.2 | USD
1308 | SM12 | APPLUS | 2021-03-01 | 7600.07 | USD
1309 | SM12 | ERAM | 2021-03-01 | 1480.5 | USD
1310 | MIP6 | INTERTEK | 2021-02-01 | 23427.02 | USD
1311 | MIP6 | BV | 2021-02-01 | 4072 | USD
1312 | MIP6 | APAVE | 2021-02-01 | 4352 | USD
1313 | MIP6 | RINA | 2021-02-01 | 1863.36 | USD
1314 | MIP6 | ERAM | 2021-02-01 | 33024.93 | USD
1315 | MIP6 | PETROZONE | 2021-02-01 | 9504 | USD
1316 | MIP6 | TEXIN | 2021-02-01 | 17127 | USD
1317 | SM12 | INTERTEK | 2021-02-01 | 8520 | USD
1318 | SM12 | BV | 2021-02-01 | 376 | USD
1319 | SM12 | APPLUS | 2021-02-01 | 8640 | USD
1320 | SM12 | ERAM | 2021-02-01 | 1912.43 | USD
1321 | MIP6 | INTERTEK | 2021-01-01 | 18364.99 | USD
1322 | MIP6 | BV | 2021-01-01 | 1504 | USD
1323 | MIP6 | APAVE | 2021-01-01 | 6656 | USD
1324 | MIP6 | RINA | 2021-01-01 | 6011.88 | USD
1325 | MIP6 | ERAM | 2021-01-01 | 20484.6 | USD
1326 | MIP6 | PETROZONE | 2021-01-01 | 13952 | USD
1327 | SM12 | INTERTEK | 2021-01-01 | 14412.6 | USD
1328 | SM12 | BV | 2021-01-01 | 4136 | USD
1329 | SM12 | APPLUS | 2021-01-01 | 960 | USD
1330 | SM12 | ERAM | 2021-01-01 | 10906.64 | USD
1331 | MIP6 | INTERTEK | 2020-12-01 | 16170.18 | USD
1332 | MIP6 | DNV | 2020-12-01 | 816.75 | USD
1333 | MIP6 | BV | 2020-12-01 | 1210.8 | USD
1334 | MIP6 | APAVE | 2020-12-01 | 2562 | USD
1335 | MIP6 | RINA | 2020-12-01 | 1349.25 | USD
1336 | MIP6 | ERAM | 2020-12-01 | 11921.2 | USD
1337 | MIP6 | PETROZONE | 2020-12-01 | 5632 | USD
1338 | MIP6 | TEXIN | 2020-12-01 | 8233 | USD
1339 | SM12 | INTERTEK | 2020-12-01 | 10882.2 | USD
1340 | SM12 | BV | 2020-12-01 | 5488 | USD
1341 | SM12 | APAVE | 2020-12-01 | 2973 | USD
1342 | SM12 | RINA | 2020-12-01 | 1265 | USD
1343 | SM12 | ERAM | 2020-12-01 | 12677.78 | USD
1344 | MIP6 | INTERTEK | 2020-11-01 | 19809.3 | USD
1345 | MIP6 | DNV | 2020-11-01 | 1633.5 | USD
1346 | MIP6 | BV | 2020-11-01 | 1210.8 | USD
1347 | MIP6 | APAVE | 2020-11-01 | 2340 | USD
1348 | MIP6 | RINA | 2020-11-01 | 671.25 | USD
1349 | MIP6 | ERAM | 2020-11-01 | 13971.17 | USD
1350 | MIP6 | PETROZONE | 2020-11-01 | 5088 | USD
1351 | MIP6 | TEXIN | 2020-11-01 | 5464 | USD
1352 | SM12 | INTERTEK | 2020-11-01 | 13972.1 | USD
1353 | SM12 | DNV | 2020-11-01 | 2815 | USD
1354 | SM12 | RINA | 2020-11-01 | 3142.42 | USD
1355 | SM12 | ERAM | 2020-11-01 | 9500.69 | USD
1356 | SM12 | PETROZONE | 2020-11-01 | 1748 | USD
1357 | SM12 | TQ CERT | 2020-11-01 | 2460 | USD
1358 | MIP6 | INTERTEK | 2020-10-01 | 23340.4 | USD
1359 | MIP6 | DNV | 2020-10-01 | 3267 | USD
1360 | MIP6 | BV | 2020-10-01 | 1816.2 | USD
1361 | MIP6 | APAVE | 2020-10-01 | 273 | USD
1362 | MIP6 | RINA | 2020-10-01 | 4413.63 | USD
1363 | MIP6 | ERAM | 2020-10-01 | 18384.71 | USD
1364 | MIP6 | TEXIN | 2020-10-01 | 1572 | USD
1365 | SM12 | INTERTEK | 2020-10-01 | 7944.4 | USD
1366 | SM12 | ERAM | 2020-10-01 | 7719.64 | USD
1367 | MIP6 | INTERTEK | 2020-09-01 | 16251.15 | USD
1368 | MIP6 | DNV | 2020-09-01 | 2160 | USD
1369 | MIP6 | BV | 2020-09-01 | 1199.8 | USD
1370 | MIP6 | RINA | 2020-09-01 | 2320.78 | USD
1371 | MIP6 | ERAM | 2020-09-01 | 10871.4 | USD
1372 | MIP6 | PETROZONE | 2020-09-01 | 576 | USD
1373 | SM12 | INTERTEK | 2020-09-01 | 5487 | USD
1374 | SM12 | RINA | 2020-09-01 | 1608.2 | USD
1375 | SM12 | ERAM | 2020-09-01 | 5553.84 | USD
1376 | SM12 | TQ CERT | 2020-09-01 | 780 | USD
1377 | MIP6 | INTERTEK | 2020-08-01 | 15331.84 | USD
1378 | MIP6 | DNV | 2020-08-01 | 6120 | USD
1379 | MIP6 | APAVE | 2020-08-01 | 258 | USD
1380 | MIP6 | RINA | 2020-08-01 | 6913.8 | USD
1381 | MIP6 | ERAM | 2020-08-01 | 12685.2 | USD
1382 | SM12 | INTERTEK | 2020-08-01 | 5704 | USD
1383 | SM12 | ERAM | 2020-08-01 | 2923.29 | USD
1384 | MIP6 | INTERTEK | 2020-07-01 | 925 | USD
1385 | MIP6 | DNV | 2020-07-01 | 3320 | USD
1386 | MIP6 | BV | 2020-07-01 | 190.8 | USD
1387 | MIP6 | APAVE | 2020-07-01 | 192 | USD
1388 | MIP6 | RINA | 2020-07-01 | 2178 | USD
1389 | MIP6 | ERAM | 2020-07-01 | 744 | USD
1390 | SM12 | INTERTEK | 2020-07-01 | 5808 | USD
1391 | SM12 | APPLUS | 2020-07-01 | 1048 | USD
1392 | SM12 | RINA | 2020-07-01 | 705 | USD
1393 | MIP6 | APAVE | 2020-06-01 | 192 | USD
1394 | MIP6 | RINA | 2020-06-01 | 5992.5 | USD
1395 | SM12 | INTERTEK | 2020-06-01 | 4752 | USD
1396 | MIP6 | RINA | 2020-05-01 | 4725 | USD
1397 | SM12 | INTERTEK | 2020-05-01 | 5280 | USD
1398 | SM12 | DNV | 2020-05-01 | 1376 | USD
1399 | MIP6 | INTERTEK | 2020-04-01 | 2306.4 | USD
1400 | MIP6 | RINA | 2020-04-01 | 14061.76 | USD
1401 | MIP6 | ERAM | 2020-04-01 | 1182 | USD
1402 | SM12 | INTERTEK | 2020-04-01 | 5808 | USD
1403 | MIP6 | INTERTEK | 2020-03-01 | 3379.74 | USD
1404 | MIP6 | DNV | 2020-03-01 | 808 | USD
1405 | MIP6 | ERAM | 2020-03-01 | 2576.51 | USD
1406 | SM12 | INTERTEK | 2020-03-01 | 5280 | USD
1407 | SM12 | INTERTEK | 2020-02-01 | 5016 | USD
1408 | SM12 | INTERTEK | 2020-01-01 | 3696 | USD

## 인력운영_현황
순번 | 이름 | 소속 | 근무지 | 직급 | 파트 | 담당 공종 | PQCM | PQC_Engineer | Number_of_PO
1 | 유요석 팀장 | 플랜트구매품질팀 | 본사 | G3 |  |  |  |  | 해당없음
2 | 강택기 책임 | 플랜트구매품질팀 | 본사 | G3 | 배관 | Piping |  | SAC2 / VEQU | 9
3 | 윤희수 책임 | 플랜트구매품질팀 | 본사 | G3 | 전기/계장 | Electrical & Instrument | ALOM / VEQU | STA4 / ALOM / CSSP | 38
4 | 서민 책임 | 플랜트구매품질팀 | 본사 | G3 | 회전기계 | Rotating |  | STA4 / CSSP / PNG1 | 46
5 | 장동철 책임 | 플랜트구매품질팀 | 본사 | G3 | 배관 | Rotating / Piping | SM12 | SM12 / IBRU / CSSP / PNG1 | 25
6 | 정진우 책임 | 플랜트구매품질팀 | 본사 | G3 | 장치기계 | Static | CSSP | SM12 / ALOM / CSSP | 9
7 | 나광조 책임 | 플랜트구매품질팀 | 본사 | G2 | 장치기계 | Static |  | SHN1 / ALOM / CSSP / PNG1 | 16
8 | 강태준 책임 | 플랜트구매품질팀 | 본사 | G2 | 전략기획 | Rotating / Piping | PNG1 / ALSM | VEQU / CSSP / PNG1 | 39
9 | 이해석 책임 | 플랜트구매품질팀 | 본사 | G2 | 전기/계장 | Electrical & Instrument | SHN1 | STA4 / SHN1 | 21
10 | 최종현 책임 | 플랜트구매품질팀 | 본사 | G2 | 전기/계장 | Electrical & Instrument | SAC2 | SAC2 | 17
11 | 석우경 매니저 | 플랜트구매품질팀 | 본사 | G1 | 배관 | Piping |  | ALOM / CSSP / PNG1 | 53
12 | 고팔라크리스낸 매니저 | 플랜트구매품질팀 | 본사 | GS | 철골 | Static / Structural Steel |  | STA4 / VEQU / CSSP / PNG1 | 19
13 | 술탄 매니저 | 플랜트구매품질팀 | 본사 | GS | 전기/계장 | Electrical & Instrument |  | VEQU / CSSP | 24
14 | 엥흐철멍 매니저 | 플랜트구매품질팀 | 본사 | GS | 배관 | Piping |  | PNG1 | 1
15 | 최우석 책임 | STA4 | 현장 | G3 | 장치기계 |  | STA4 |  | 해당없음
16 | 강인묵 책임 | STA4 | 서울사무소 | G2 | 전기/계장 | Electrical & Instrument |  | STA4 / CSSP | 28
17 | 최영준 책임 | STA4 | 현장 | G2 | 장치기계 | Static |  | STA4 | 8
18 | 임효원 책임 | STA4 | 현장 | P6 | 배관 | Piping |  | STA4 | 37
19 | 황윤섭 책임 | SAC2 | 현장 | P5 | 배관 | Piping |  | SAC2 | 13
20 | 조상래 매니저 | SAC2 | 현장 | G1 | 전기/계장 | 시공품질 |  |  | 해당없음
21 | 박지애 매니저 | SAC2 | 서울사무소 | P2 | 배관 | Piping |  | SAC2 | 12
22 | 박재석 책임 | SHN1 | 현장 | P6 | 장치기계 | Static |  | SHN1 | 1
23 | 유녕희 매니저 | STA4 | 서울사무소 | P3 |  | Inspection Coordinator |  |  | 해당없음
24 | 최보윤 매니저 | STA4 | 서울사무소 | P1 |  | Inspection Coordinator |  |  | 해당없음
25 | 성유진 매니저 | SAC2 | 서울사무소 | P1 |  | Inspection Coordinator |  |  | 해당없음

## 인력운영_세부내역
순번 | 프로젝트 | 공종 | PO | PO Description | Quantity | 업무 종료 예상 시기 | IRC % | 비고 | 담당자(정) | 담당자(부)
1 | STA4 | 장치 | MS001 | PRESSURE VESSEL I | 12 ea | 2026-05-30 | 86% |  | 고팔라크리스낸 매니저 | 최영준 책임
2 | STA4 | 장치 | MS002 | PRESSURE VESSEL II | 13 ea | 2026-06-30 | 73% |  | 고팔라크리스낸 매니저 | 최영준 책임
3 | STA4 | 장치 | MS003 | PRESSURE VESSEL III | 1 ea | 완료 | 100% |  | 고팔라크리스낸 매니저 | 최영준 책임
4 | STA4 | 장치 | MS004 | FILTER | 7 ea | 완료 | 100% | IDR 작성/제출 완료, VIRB 제출완료 / 서류 종료 26.03 | 최영준 책임 | 정진우
5 | STA4 | 장치 | MS005 | SHELL AND TUBE HEAT EXCHANGER | 3 ea | 2026-06-30 | 95% |  | 고팔라크리스낸 매니저 | 최영준 책임
6 | STA4 | 장치 | MS006 | AIR COOLED HEAT EXCHANGER |  | 완료 | 100% | IDR 제출완료/VIRB 제출완료 / 서류 종료 예상시기 26.03 | 최영준 책임 | 고팔라크리스낸 매니저
7 | STA4 | 장치 | MS007 | PLATE & FRAME HEAT EXCHANGER |  | 완료 | 100% |  | 최영준 책임 | 고팔라크리스낸 매니저
8 | STA4 | 장치 | MS008 | SALINE COOLING WATER FILTER PACKAGE | 33 ea | 2026-04-30 | 100% | IDR 필요없음 (Inspection Level 3) / AET Procedure 발주처 승인 완료 / VIRB 진행 필요(현재 미접수) / 서류 종료 예상시기 26.04 | 최영준 책임 | 정진우 책임
9 | STA4 | 장치 | MS011 | STORAGE TANK | 17 ea | 2026-09-30 | 46% |  | 고팔라크리스낸 매니저 | 최영준 책임
10 | STA4 | 장치 | MS012 | EDUCTOR |  | 완료 | 100% | IDR 필요없음 / VIRB 제출완료 | 최영준 책임 | 고팔라크리스낸 매니저
11 | STA4 | 장치 | MS013 | STATIC MIXER |  | 완료 | 100% | IDR 필요없음 / VIRB 제출완료 | 최영준 책임 | 고팔라크리스낸 매니저
12 | STA4 | 장치 | MS014 | DESUPER HEATER |  | 완료 | 100% | IDR 체출완료 / VIRB 제출완료 | 최영준 책임 | 고팔라크리스낸 매니저
13 | STA4 | 장치 | MS015 | SILENCER |  | 완료 | NA | Non inspectable | 최영준 책임 | 고팔라크리스낸 매니저
14 | STA4 | 장치 | MS016 | DEAERATOR | 1 ea | 2026-04-30 | 100% | IDR 작성/제출 필요, VIRB 접수(26.04.08) / 서류 종료 예상시기 26.04 | 최영준 책임 | 정진우 책임
15 | STA4 | 장치 | MS017 | AIR DRYER PACKAGE | AIR DRYER PACKAGE 1 lot | 2026-04-30 | 100% | Loose Supplied Valve 검사 완료 | 최영준 책임 | 고팔라크리스낸 매니저
16 | STA4 | 장치 | MS018 | LIN STORAGE & VAPORIZATION SYSTEM | LIN STORAGE & VAPORIZATION 1 lot -. LIN Storage Vessel (6ea) (Inner / outer) -. Steam Bath Vaporizer (3ea) -. Nitrogen Pressure Built-up Vaporizer (6ea) - 완료 -. Nitrogen boil off heater (2ea) - 완료 -. Interconnecting piping -. Piping Skid (1set) | 2026-07-01 | 35% |  | 최영준 책임 | 고팔라크리스낸 매니저
17 | STA4 | 장치 | MS019 | ACTIVATED CARBON FILTER PACKAGE | ACFP (FILTREX SRL) 3 Skid Filter Vessel (Fabtech) 3 EA | 2026-05-30 | 20% | IRC Filter Vessel 12/22일 발행 완료 / Skid 4/16 발행 예정 | 최영준 책임 | 정진우 책임
18 | STA4 | 장치 | MS020 | INCINERATOR PACKAGE | Incinerator Package 1 lot (ZEECO) Chamber & Stack 4 set (Morimatsu) - 완료 Air blower 4 set Burner 2 set - 완료 | 2026-06-30 | 20% | Skid IRC 발급 기준 / Anchor bolt IRC 발행 완료 / Chamber & Stack STD Flange 수급으로 11월 말 납품가능 | 최영준 책임 | 고팔라크리스낸 매니저
19 | STA4 | 장치 | MS021 | FLARE PACKAGE | LPEF 1 lot (ZEECO) MPGF 1 lot (ZEECO) Derrick Structure 1 lot (FMC) Water Seal Drum 1 lot (SAMIF) Dish Head for WSD 2 ea (AOI) Radiation Fence 1 lot (Al Kabii) | 2026-05-30 | 43% | Stack Riser 7기 모두 IRC 발행 (ZEECO), Derrick Structure IRC 100% (FMC), Derrick 2nd Structure IRC 90% (Al Kaabi), LPEF & MPGF 납기지연 공문 접수 | 최영준 책임 | 고팔라크리스낸 매니저
20 | STA4 | 장치 | MS023 | FLARE GAS RECOVERY PACKAGE | FGRP 1 lot Centri. Pump 1 lot Air Cooler 1 lot - 완료 Spearator Vessel 1 lot Motor 1 lot - 완료 | 2026-09-01 | 0% |  | 최영준 책임 | 고팔라크리스낸 매니저
21 | STA4 | 장치 | MS024 | EXPLOSION HATCH |  | 완료 | 100% | IDR 필요없음 / VIRB 제출완료 | 최영준 책임 | 고팔라크리스낸 매니저
22 | STA4 | 장치 | MS025 | EQUIPMENT PLATFORM & LADDER | 307.5 MT | 2026-07-30 | 32.7% | IDR 필요없음 / VIRB 진행필요 | 고팔라크리스낸 매니저 | 최우석 책임
23 | STA4 | 철골 | SS001 | STRUCTURAL STEEL | 22500 MT | 2026-07-30 | 77% | IDR 작성필요 / VIRB 제출필요 | 고팔라크리스낸 매니저 | 최우석 책임
24 | STA4 | 철골 | SC002 | ISOLATED SUPPORT | 2150 MT | 2026-07-30 | 26% | IDR 필요없음 / VIRB 진행필요없음 | 고팔라크리스낸 매니저 | 최우석 책임
25 | STA4 | 회전 | MR001 | CENTRIFUGAL COMPRESSOR (API 617) | CENTRIFUGAL COMPRESSOR (API 617) : 1 ea MOTOR FOR CENTRIFUGAL COMPRESSOR (API 617) : 1 ea Gear Box FOR CENTRIFUGAL COMPRESSOR (API 617) : 1 ea Lube Oil Unit FOR CENTRIFUGAL COMPRESSOR (API 617) : 1 ea | 2026-05-30 | 100% 100% 100% 100% | VIRB 진행필요 / IDR 작성필요 | 서민 책임 | 장동철 책임
26 | STA4 | 회전 | MR003 | AIR COMPRESSOR PACKAGE (API 672) | AIR COMPRESSOR PACKAGE (API 672) : 4 ea Motor for AIR COMPRESSOR PACKAGE (API 672) : 4 ea | 2026-05-30 | 100% 100% | VIRB 진행필요 / IDR 작성필요 | 서민 책임 | 장동철 책임
27 | STA4 | 회전 | MR004 | BOILER FEED WATER PUMP (API 610 BB) | BOILER FEED WATER PUMP (API 610 BB) : 3 ea Motor for BOILER FEED WATER PUMP (API 610 BB) : 3 ea | 2026-05-30 | 100% 100% | VIRB 진행 중 / IDR 작성 필요 | 서민 책임 | 장동철 책임
28 | STA4 | 회전 | MR005 | COOLING WATER PUMP (API 610 BB) | COOLING WATER PUMP (API 610 BB) : 34 ea MOTOR FOR COOLING WATER PUMP (API 610 BB) : 34 ea | 2026-05-30 | 100% 100% | VIRB 진행 중 / IDR 작성 필요 | 서민 책임 | 장동철 책임
29 | STA4 | 회전 | MR006 | CENTRIFUGAL PUMP (API 610 BB) -BLOW DOWN PUMP | CENTRIFUGAL PUMP (API 610 BB) -Blow Down Pump : 3 ea Motor for CENTRIFUGAL PUMP (API 610 BB) -Blow Down Pump : 3 ea | 2026-05-30 | 100% 100% | VIRB 진행필요 / IDR 작성필요 | 서민 책임 | 장동철 책임
30 | STA4 | 회전 | MR007 | CENTRIFUGAL PUMP (OH TYPE) | CENTRIFUGAL PUMP (OH TYPE) : 32 ea MOTOR FOR CENTRIFUGAL PUMP (OH TYPE) : 2 ea | 2026-05-30 | 100% 100% | VIRB 진행필요 / IDR 작성필요 (Inspection Level 1 item) | 서민 책임 | 장동철 책임
31 | STA4 | 회전 | MR007(VO) | CENTRIFUGAL PUMP (OH TYPE) | CENTRIFUGAL PUMP (OH TYPE) : 6 ea | 2026-05-30 | 0% | 430-G-0041-A/B, 430-G-0043-A/B, 405-G-0010-A/B 추가됨 | 서민 책임 | 장동철 책임
32 | STA4 | 회전 | MR008 | CENTRIFUGAL PUMP (VERTICAL TYPE) | CENTRIFUGAL PUMP (VERTICAL TYPE) : 10 EA | 2026-12-30 | 60% | 401-G-0001-A/B/C/D 추가됨 | 서민 책임 | 장동철 책임
33 | STA4 | 회전 | MR010 | SEALLESS PUMP (API 685) | SEALLESS PUMP (API 685) : 2 ea | 2026-05-30 | 100% | Impeller Diameter 문제 확인으로 현재 NCR 발행 및 Waiver Request 제출, Conditional IRC issue, VIRB 진행필요 | 서민 책임 | 장동철 책임
34 | STA4 | 회전 | MR010(VO) | SEALLESS PUMP (API 685) | SEALLESS PUMP (API 685) : 2 ea | 2026-12-05 | 50% | 420-G-0045-A/B 추가 | 서민 책임 | 장동철 책임
35 | STA4 | 회전 | MR011 | SUBMERSIBLE PUMP (NON-API) | 29 ea | 2026-06-30 | 100% | VIRB 진행필요 / IDR 필요없음(IL 3) Auto Coupling의 adaptor 추가 제작 5월 검사 예정 | 서민 책임 | 장동철 책임
36 | STA4 | 회전 | MR012 | FIRE WATER PUMP (NFPA 20) | FIRE WATER PUMP (NFPA 20) : 9 ea MOTOR FOR FIRE WATER PUMP (NFPA 20) : 3 ea | 2026-05-30 | 100% 100% | VIRB 완료, IDR 작성 필요 | 서민 책임 | 장동철 책임
37 | STA4 | 회전 | MR013 | COOLING TOWER | COOLING TOWER : 1 ea Motor for COOLING TOWER : 54 ea | 2026-05-30 | 100% | VIRB 진행필요 / IDR 작성필요 | 서민 책임 | 장동철 책임
38 | STA4 | 회전 | MR014 | ELECTROCHLORINATION PACKAGE | ELECTROCHLORINATION PACKAGE : 9 ea | 2026-06-30 | 95% | Platform, Pipe Supports and cable tray supports 제작중 | 서민 책임 | 장동철 책임
39 | STA4 | 회전 | MR015 | CHILLER PACKAGE | 2 ea | 2026-04-30 | 100% | IAP 없음(IL3), VIRB 진행필요 / IDR 필요없음(IL 3) | 서민 책임 | 장동철 책임
40 | STA4 | 회전 | MR016 | CHEMICAL INJECTION PACKAGE | CHEMICAL INJECTION PACKAGE : 5 ea | 2026-05-30 | 0% |  | 서민 책임 | 장동철 책임
41 | STA4 | 회전 | MR017 | CRANE | 9 ea | 2026-05-30 | 100% | IAP 없음(IL3), VIRB 진행 중 / IDR 필요없음(IL 3) | 서민 책임 | 장동철 책임
42 | STA4 | 회전 | MR019 | SIDE ENTRY MIXER | 2 ea | 2026-11-15 | 0% | 추가 PO(KOM 완료) | 서민 책임 | 장동철 책임
43 | STA4 | 회전 | MR020 | SEA WATER BOOSER PUMP | 4 ea | 2026-11-23 | 0% | 추가 PO(KOM 완료) | 서민 책임 | 장동철 책임
44 | STA4 | 소방/안전 | SE001 | FIRE & SAFETY EQUIPMENT | 1 lot | 2026-05-30 | 90% | IAP 없음(IL3) | 서민 책임 | 장동철 책임
45 | STA4 | 소방/안전 | SE002 | CLEAN AGENT FIRE EXTINGUISHING SYSTEM | 1 lot | 2026-05-30 | 90% | IAP 없음(IL3) | 서민 책임 | 장동철 책임
46 | STA4 | 공조 | HV001 | HVAC EQUIPMENT | 1 lot | 2026-05-30 | 90% | IAP 없음(IL3) | 서민 책임 | 장동철 책임
47 | STA4 | 기타 | PR001 | CHEMICAL |  | NA | NA | Non inspectable | 서민 책임 | 장동철 책임
48 | STA4 | 기타 | PR002 | SPECIAL CHEMICAL |  | NA | NA | Non inspectable | 서민 책임 | 장동철 책임
49 | STA4 | 배관 | PI001 | RTR PIPING | 117200 m | 2026-12-01 | 96% |  | 임효원 책임 | 최우석 책임
50 | STA4 | 배관 | PI002 | CPVC PIPING AND VALVE | 24973 ea, 6465 ea | 2026-05-01 | 99% | 2개 PO 분리 발주, VIRB 접수 필요 (IL 3) , IDR 필요없음 | 임효원 책임 | 최우석 책임
51 | STA4 | 배관 | PI003 | CARBON STEEL SMLS PIPE | 271874 m | 2026-07-01 | 95% |  | 임효원 책임 | 최우석 책임
52 | STA4 | 배관 | PI004 | CARBON STEEL WELDED PIPE | 29616 m | 2026-07-01 | 99% |  | 임효원 책임 | 최우석 책임
53 | STA4 | 배관 | PI005 | STAINLESS STEEL SMLS PIPE | 16230 m | 2026-07-01 | 98% |  | 임효원 책임 | 최우석 책임
54 | STA4 | 배관 | PI006 | STAINLESS STEEL WELDED PIPE | 4440 m | 완료 | 100% | IDR 체출완료 / VIRB 제출완료 | 임효원 책임 | 최우석 책임
55 | STA4 | 배관 | PI007 | LOW ALLOY STEEL SMLS PIPE | 402 m | 완료 | 100% | IDR 체출완료 / VIRB 제출완료 | 임효원 책임 | 최우석 책임
56 | STA4 | 배관 | PI008 | LOW ALLOY STEEL WELDED PIPE | 600 m | 완료 | 100% | IDR 체출완료 / VIRB 제출완료 | 임효원 책임 | 최우석 책임
57 | STA4 | 배관 | PI009 | FORGED FITTING | 47491 ea | 2026-06-01 | 95% |  | 임효원 책임 | 최우석 책임
58 | STA4 | 배관 | PI010 | WROUGHT FITTING | 18862 ea, 9418 ea | 2026-06-01 | 98% | 2개 PO 분리 발주 | 임효원 책임 | 최우석 책임
59 | STA4 | 배관 | PI011 | FABRICATED FITTING (LATERAL) | 24 ea | 완료 | 100% | IDR 체출완료 / VIRB 제출완료 | 임효원 책임 | 최우석 책임
60 | STA4 | 배관 | PI012 | FLANGE | 47427 ea, 818 ea, 134 ea | 2026-08-01 | 90% | 3개 PO 분리 발주, 1건 IDR 제출 완료 | 임효원 책임 | 최우석 책임
61 | STA4 | 배관 | PI013 | FIRE WATER VALVE | 1079 ea, 39 ea | 2026-06-01 | 100% | 2개 PO 분리 발주, 1건 IDR 제출 완료 | 임효원 책임 | 최우석 책임
62 | STA4 | 배관 | PI014 | FORGED VALVE | 9780 ea | 2026-12-01 | 96% |  | 임효원 책임 | 최우석 책임
63 | STA4 | 배관 | PI015 | DIAPHRAGM VALVE | 909 ea | 2026-06-01 | 93% | IDR 필요없음 / VIRB 진행필요 | 임효원 책임 | 최우석 책임
64 | STA4 | 배관 | PI016 | CASTING VALVE | 2567 ea, 9 ea | 2026-10-01 | 90% | 2개 PO 분리 발주 | 임효원 책임 | 최우석 책임
65 | STA4 | 배관 | PI017 | DUCTILE IRON EPOXY LINED VALVE | 800 ea, 12 ea | 2026-08-01 | 90% | 2개 PO 분리 발주 | 임효원 책임 | 최우석 책임
66 | STA4 | 배관 | PI018 | BUTTERFLY VALVE | 595 ea, 18 ea | 2026-12-01 | 90% | 2개 PO 분리 발주 | 임효원 책임 | 최우석 책임
67 | STA4 | 배관 | PI019 | BALL VALVE | 211 ea, 50 ea | 2026-12-01 | 95% | 2개 PO 분리 발주, 1건 IDR 제출 완료 | 임효원 책임 | 최우석 책임
68 | STA4 | 배관 | PI021 | DUAL PLATE CHECK VALVE | 167 ea | 2026-06-01 | 79% |  | 임효원 책임 | 최우석 책임
69 | STA4 | 배관 | PI022 | PLUG VALVE | 217 ea, 20 ea | 2026-10-01 | 75% | 2개 PO 분리 발주 | 임효원 책임 | 최우석 책임
70 | STA4 | 배관 | PI023 | BRONZE VALVE | 160 ea, 10 ea | 2026-08-01 | 90% | 2개 PO 분리 발주 | 임효원 책임 | 최우석 책임
71 | STA4 | 배관 | PI024 | AXIAL CHECK VALVE | 2 ea | 완료 | 100% | IDR 체출완료 / VIRB 제출완료 | 임효원 책임 | 최우석 책임
72 | STA4 | 배관 | PI025 | GASKET AND INSULATION KIT | 55660 ea | 2026-10-01 | 95% | VIRB 접수 필요, IDR 작성/제출 불 필요 (inspection level 3) | 임효원 책임 | 최우석 책임
73 | STA4 | 배관 | PI026 | BOLT AND NUT | 350415 ea | 2026-10-01 | 80% | VIRB 접수 필요, IDR 작성/제출 불 필요 (inspection level 3) | 임효원 책임 | 최우석 책임
74 | STA4 | 배관 | PI027 | STEAM TRAP AND MANIFOLD | 366 ea | 2026-06-01 | 0% | VIRB 접수 필요, IDR 작성/제출 불 필요 (inspection level 3) | 임효원 책임 | 최우석 책임
75 | STA4 | 배관 | PI028 | STRAINER | 247 ea | 완료 | 100% | IDR 체출완료 / VIRB 제출완료 | 임효원 책임 | 최우석 책임
76 | STA4 | 배관 | PI029 | HOSE AND CONNECTOR | 533 ea | 2026-05-01 | 80% | VIRB 접수 필요, IDR 작성/제출 불 필요 (inspection level 3) | 임효원 책임 | 최우석 책임
77 | STA4 | 배관 | PI030 | EXPANSION JOINT | 124 ea | 2026-06-01 | 95% |  | 임효원 책임 | 최우석 책임
78 | STA4 | 배관 | PI031 | INJECTION NOZZLE | 2 ea | 완료 | 100% | VIRB 제출완료, IDR 작성/제출 불 필요 (inspection level 3) | 임효원 책임 | 최우석 책임
79 | STA4 | 배관 | PI032 | FBE LINED AND COATED PIPING | 9238 | 2026-08-01 | 75% |  | 임효원 책임 | 최우석 책임
80 | STA4 | 배관 | PI033 | INTERLOCKING SYSTEM | 73 | 2026-06-01 | 0% | VIRB 접수 필요, IDR 작성/제출 불 필요 (inspection level 3) | 임효원 책임 | 최우석 책임
81 | STA4 | 배관 | PI034 | TUBE AND TUBE FITTING | 22963, 4326 | 2026-05-01 | 100% | VIRB 접수 필요, IDR 작성/제출 불 필요 (inspection level 3) | 임효원 책임 | 최우석 책임
82 | STA4 | 배관 | PI036 | SPRING (INCL. COLD SUPPORT) | 1734 ea | 2026-05-01 | 95% | VIRB 접수 필요, IDR 작성/제출 불 필요 (inspection level 3) | 임효원 책임 | 최우석 책임
83 | STA4 | 배관 | PI037 | PARALLEL SLIDE GATE VALVE (BULK) | 44 ea | 2026-10-01 | 93% |  | 임효원 책임 | 최우석 책임
84 | STA4 | 배관 | PI038 | KNIFE GATE VALVE | 69 ea | 2026-06-01 | 96% |  | 임효원 책임 | 최우석 책임
85 | STA4 | 배관 | PI039 | SPECIAL FITTING (BULK) | 39 ea | 완료 | 100% | IDR 체출완료 / VIRB 제출완료 | 임효원 책임 | 최우석 책임
86 | STA4 | 배관 | PI040 | AIR RELEASE VALVE | 42 ea | 완료 | 100% | VIRB 제출완료, IDR 작성/제출 불 필요 (inspection level 3) | 임효원 책임 | 최우석 책임
87 | STA4 | 전기 | EL001 | 230KV GIS | 14 bays | 2026-05-01 | 100% | LV.2 / IDR 제출 완료 / VIRB 진행 중 | 윤희수 책임 | 강인묵 책임
88 | STA4 | 전기 | EL002 | 230/34.5KV POWER TRANSFORMER | 6대 | 완료 | 100% | LV.2 / IDR 제출 완료 / VIRB 제출 완료 | 윤희수 책임 | 강인묵 책임
89 | STA4 | 전기 | EL003 | 230KV CABLE & ACCESSORIES | 9,585 m | 완료 | 100% | LV.2 / IDR 제출 완료 / VIRB 제출 완료 | 윤희수 책임 | 강인묵 책임
90 | STA4 | 전기 | EL004 | POWER TRANSFORMER & NGR | 68대 | 2026-05-01 | 100% | LV.2 / IDR 작성 중 / VIRB 진행 필요 | 이해석 책임 | 강인묵 책임
91 | STA4 | 전기 | EL005 | POWER CAPACITOR | 6대 | 2026-05-01 | 100% | LV.2 / IDR 제출 완료 / VIRB 독려중 | 이해석 책임 | 강인묵 책임
92 | STA4 | 전기 | EL006 | HV SWGR (34.5KV) HV SWGR/MCC | 5 sets | 2026-05-01 | 100% | LV.2 / IDR 작성 중 / VIRB 독려중 | 윤희수 책임 | 강인묵 책임
93 | STA4 | 전기 | EL007 | HV SWGR (13.8KV & 4.16KV) HV CONTROL GEAR | 9 sets | 2026-05-01 | 100% | LV.2 / IDR 작성 중 / VIRB 독려중 / NCR 종결 필요 | 이해석 책임 | 강인묵 책임
94 | STA4 | 전기 | EL008 | LV SWGR | 12 sets | 2026-05-01 | 100% | LV.2 / IDR 작성 중 / VIRB 독려중 / NCR 종결 필요 | 이해석 책임 | 강인묵 책임
95 | STA4 | 전기 | EL009 | LV CONTROLGEAR | 22 sets | 2026-05-01 | 100% | LV.2 / IDR 작성 중 / VIRB 독려중 / NCR 종결 필요 | 이해석 책임 | 강인묵 책임
96 | STA4 | 전기 | EL010 | EMERGENCY DIESEL GENERATOR | 4 sets | 2026-05-01 | 100% | LV.3 / IDR 불필요 / VIRB 진행 필요 | 윤희수 책임 | 강인묵 책임
97 | STA4 | 전기 | EL011 | AC UPS & DC SYSTEM | 58 sets | 2026-05-01 | 100% | LV.2 / IDR 제출 완료 / VIRB 독려중 | 이해석 책임 | 강인묵 책임
98 | STA4 | 전기 | EL012 | ELECTRICAL CONTROL SYSTEM (ECS) | 8 sets | 2026-05-01 | 100% | LV.2 / IDR 작성 중 / VIRB 진행 필요 / NCR 종결 필요 | 강인묵 책임 | 윤희수 책임
99 | STA4 | 전기 | EL012-1 | POWER MONITORING SYSTEM (PMS) | 12 sets | 2026-05-01 | 100% | LV.2 / EL012 ECS 와 동시 진행 예정 | 윤희수 책임 | 강인묵 책임
100 | STA4 | 전기 | EL013 | CATHODIC PROTECTION SYSTEM | 1 lot | 2026-06-01 | 40% | Lv 3 / IDR 불필요 / VIRB 진행 필요 | 강인묵 책임 | 윤희수 책임
101 | STA4 | 전기 | EL014 | FIRE ALARM SYSTEM | 1 lot | 2026-05-01 | 100% | Lv 3 / IDR 불필요 / VIRB 진행 필요 | 윤희수 책임 | 강인묵 책임
102 | STA4 | 전기 | EL015 | ELECTRIC HEAT TRACING SYSTEM | 1 lot | NA | NA | Non inspectable | 강인묵 책임 | 강인묵 책임
103 | STA4 | 전기 | EL016 | POWER & CONTROL CABLE | 1,841,105 m | 2026-05-30 | 95% | LV.2 / IDR, VIRB 진행 필요 / 전체 물량 납기 완료 예상(26.5월) | 강인묵 책임 | 윤희수 책임
104 | STA4 | 전기 | EL017 | CABLE TRAY | 1 lot | 2026-05-01 | 93% | LV.3 / IDR 불필요 / VIRB 진행 필요 / 전체 물량 납기 완료 예상(26.5월) | 강인묵 책임 | 최종현 책임
105 | STA4 | 전기 | EL018 | POWER DISTRIBUTION BOARD (NON-EX) -> INDOOR) | 126 ea | 2026-05-01 | 0% | LV.3 / IDR 불필요 / VIRB 진행 필요 / 전체 물량 납기 완료 예상(26.4월) | 강인묵 책임 | 이해석 책임
106 | STA4 | 전기 | EL019 | POWER DISTRIBUTION BOARD (EX) -> (WP) | 60 ea | 2026-06-01 | 0% | LV.3 / IDR 불필요 / VIRB 진행 필요 / 전체 물량 납기 완료 예상 (26.5월) | 강인묵 책임 | 이해석 책임
107 | STA4 | 전기 | EL020 | LOCAL CONTROL STATION & JUNCTION BOX | 279 ea | NA | NA | Non inspectable | 강인묵 책임 | 강인묵 책임
108 | STA4 | 전기 | EL021 | OUTDOOR LIGHTING FIXTURE (EX, NON-EX) | 1 lot | NA | NA | Non inspectable | 강인묵 책임 | 강인묵 책임
109 | STA4 | 전기 | EL022 | INDOOR LIGHTING FIXTURE (EX, NON-EX) | 1 lot | NA | NA | Non inspectable | 강인묵 책임 | 강인묵 책임
110 | STA4 | 전기 | EL023 | CABLE GLAND | 1 lot | NA | NA | Non inspectable | 강인묵 책임 | 강인묵 책임
111 | STA4 | 전기 | EL024 | TERMINATION & SPLICING KIT | 1 lot | NA | NA | Non inspectable | 강인묵 책임 | 강인묵 책임
112 | STA4 | 전기 | EL025 | GROUNDING SYSTEM | 1 lot | NA | NA | Non inspectable | 강인묵 책임 | 강인묵 책임
113 | STA4 | 전기 | EL026 | CONDUIT & FITTING | 1 lot | NA | NA | Non inspectable | 강인묵 책임 | 강인묵 책임
114 | STA4 | 전기 | EL027 | ELECTRIC CAR CHARGING SYSTEM | 1 lot | NA | NA | Non inspectable | 강인묵 책임 | 강인묵 책임
115 | STA4 | 전기 | EL030 | SIGNAL CABLE | 179,450 m | 2026-05-30 | 97.6% | LV.3 / IDR 불필요 / VIRB 진행 필요 / 전체 물량 납기 완료 예상 (26.5월) | 강인묵 책임 | 최종현 책임
116 | STA4 | 전기 | EL031 | FIBER OPTIC CABLE | 69,200 m | 2026-05-01 | 95% | LV.2 / IDR, VIRB 진행필요 / 전체 물량 납기 완료 예상 (26.5월) | 강인묵 책임 | 최종현 책임
117 | STA4 | 전기 | EL032 | ELECTRICAL MCT | 1 lot | 완료 | 100% | IDR 불필요, VIRB 제출 완료 | 강인묵 책임 | 최종현 책임
118 | STA4 | 전기 | EL033 | ERGONOMIC LIGHTING | 1 lot | NA | NA | Non inspectable | 강인묵 책임 | 강인묵 책임
119 | STA4 | 통신 | TE001 | PASSIVE COMPONENT | 1 lot | NA | NA | Non inspectable | 강인묵 책임 | 강인묵 책임
120 | STA4 | 계장 | CI001 | PCS - MAC | 161 면 | 2026-05-01 | 93% | 1) PDP (RAWABI) 총 26개 중 14개 IRC (WITH NCR) 처리 완료 , 12면 Punch 종결 진행중 -> PUNCH Close 지연중 (Touch up paint 불량 이슈) 2) MMS 1면 (VO) Punch 종결 지연중 3) OTS : TBD | 이해석 책임 | 윤희수 책임
121 | STA4 | 계장 | CI003 | ANALYZER SYSTEM | 20 set | 2026-06-01 | 0% |  | 강인묵 책임 | 이해석 책임
122 | STA4 | 계장 | CI004 | AIR QUALITY MONITORING SYSTEM | 1 set | NA | NA | Non inspectable | 강인묵 책임 | 이해석 책임
123 | STA4 | 계장 | CI005 | ON-OFF VALVE (BALL) | 45 ea | 2026-06-01 | 85% |  | 임효원 책임 | 최우석 책임
124 | STA4 | 계장 | CI006 | ON-OFF VALVE (PLUG) | 17 ea | 2026-06-01 | 12% |  | 임효원 책임 | 최우석 책임
125 | STA4 | 계장 | CI007 | BUTTERFLY VALVE (LUG TYPE) -> (CONCENTRIC) | 127 ea | 2027-01-01 | 86% |  | 임효원 책임 | 최우석 책임
126 | STA4 | 계장 | CI008 | BUTTERFLY VALVE (HIGH PERFORMANCE) | 28 ea | 2027-01-01 | 60% |  | 임효원 책임 | 최우석 책임
127 | STA4 | 계장 | CI009 | CONTROL VALVE (GLOBE) & PCV | 89 ea | 2026-06-01 | 60% | VIRB 접수 필요, IDR 작성/제출 불 필요 (inspection level 3) | 임효원 책임 | 최우석 책임
128 | STA4 | 계장 | CI010 | CONTROL VALVE (BUTTERFLY) | 14 ea | 2026-05-01 | 100% | VIRB 접수 필요, IDR 작성/제출 불 필요 (inspection level 3) | 임효원 책임 | 최우석 책임
129 | STA4 | 계장 | CI011 | PRESSURE RELIEF VALVE | 167 ea | 2026-05-01 | 95% |  | 임효원 책임 | 최우석 책임
130 | STA4 | 계장 | CI012 | FLOWMETER (VORTEX, CORIOLIS, MAGNETIC) | 2 ea | 2026-05-01 | 100% | LV 2 / IDR, VIRB 진행 필요 | 윤희수 책임 | 강인묵 책임
131 | STA4 | 계장 | CI014 | FLOWMETER (ULTRASONIC) | 35 ea | 2026-05-01 | 100% | LV.2 / IDR 준비 중, VIRB 진행 필요 | 윤희수 책임 | 강인묵 책임
132 | STA4 | 계장 | CI015 | TRANSMITTERS | 917 ea | 2026-05-01 | 90% | LV. 3 / IDR 불필요 / VIRB 진행 필요 | 윤희수 책임 | 강인묵 책임
133 | STA4 | 계장 | CI016 | LEVEL GAUGE AND SIGHT GLASS | 58 ea | 2026-05-01 | 0% | LV 2 / IDR, VIRB 진행 필요 | 강인묵 책임 | 윤희수 책임
134 | STA4 | 계장 | CI018 | LEVEL TRANSMITTER (GWR/RADAR) | 99 ea | 2026-05-30 | 70% | LV. 3 / IDR 불필요 / VIRB 진행 필요 | 윤희수 책임 | 강인묵 책임
135 | STA4 | 계장 | CI019 | FLOW ELEMENT | 172 ea | 2026-05-01 | 5% | LV. 3 / IDR 불필요 / VIRB 진행 필요 | 강인묵 책임 | 윤희수 책임
136 | STA4 | 계장 | CI020 | LOCAL GAUGE | 1 lot | 2026-05-01 | 94% | LV. 3 / IDR 불필요 / VIRB 진행 필요 | 강인묵 책임 | 윤희수 책임
137 | STA4 | 계장 | CI021 | GAS DETECTOR, HORN AND BEACON | 421 ea | 2026-06-01 | 45% | LV. 3 / IDR 불필요 / VIRB 진행 필요 | 윤희수 책임 | 강인묵 책임
138 | STA4 | 계장 | CI022 | OPEN PATH GAS DETECTOR | 73 ea | 2026-06-01 | 80% | LV. 3 / IDR 불필요 / VIRB 진행 필요 | 윤희수 책임 | 강인묵 책임
139 | STA4 | 계장 | CI023 | ROTAMETER | 1 lot | NA | NA | Non inspectable | 강인묵 책임 | 강인묵 책임
140 | STA4 | 계장 | CI024 | CORROSION COUPON AND PROBE | 1 lot | NA | NA | Non inspectable | 강인묵 책임 | 강인묵 책임
141 | STA4 | 계장 | CI025 | INSTRUMENT CABLE | 856,560 m | 2026-05-01 | 95% | LV. 3 / IDR 불필요 / VIRB 진행 필요 | 강인묵 책임 | 최종현 책임
142 | STA4 | 계장 | CI026 | INSTRUMENT CABLE TRAY | 1 lot | 완료 | 100% | IDR 불필요, VIRB 제출 완료 | 강인묵 책임 | 최종현 책임
143 | STA4 | 계장 | CI027 | INSTRUMENT JUNCTION BOX | 359 ea | NA | NA | Non inspectable | 강인묵 책임 | 최종현 책임
144 | STA4 | 계장 | CI028 | INSTRUMENT CABLE GLAND | 1 lot | NA | NA | Non inspectable | 강인묵 책임 | 최종현 책임
145 | STA4 | 계장 | CI029 | INSTRUMENT TUBE | 1 lot | 완료 | 100% | LV 3 / IDR 불필요 / VIRB 제출 완료 | 강인묵 책임 | 최종현 책임
146 | STA4 | 계장 | CI030 | INSTRUMENT TUBE FITTING | 1 lot | 2026-05-01 | 100% | LV 3 / IDR 불필요 / VIRB 진행 필요 | 강인묵 책임 | 최종현 책임
147 | STA4 | 계장 | CI033 | INSTRUMENT CONDUIT & FITTING | 1 lot | NA | NA | Non inspectable | 강인묵 책임 | 최종현 책임
148 | STA4 | 계장 | CI034 | INSTRUMENT BLOCK VALVE | 1 lot | 2026-05-01 | 100% | LV 3 / IDR 불필요 / VIRB 진행 필요 | 강인묵 책임 | 최종현 책임
149 | STA4 | 계장 | CI035 | INSTRUMENT SUPPORT & CONSUMABLE | 1 lot | NA | NA | Non inspectable | 강인묵 책임 | 최종현 책임
150 | STA4 | 계장 | CI036 | INSTRUMENT MCT | 1 lot | 완료 | 100% | LV 3 / IDR 불필요 / VIRB 제출 완료 | 강인묵 책임 | 최종현 책임
151 | STA4 | 계장 | CI038 | CONTROL VALVE (NON-GENERAL) | 14 | 2026-05-01 | 90% |  | 임효원 책임 | 최우석 책임
152 | SHN1 | 장치 | 2110-2001-001 | CRACKING FURNACE (PROPRIETARY) | Transfer Line Exchanger : 80 ea Radiant Coil (Liquid Heater) : 64 Set Radiant Coil (Gas Heater) : 16 Set High Alloy Castings : 3330 ea Desuperheaters : 18 ea Finning : 9424 ea Strainer and Seat Ring : 80 ea Burner & Accessories : 1440 ea | 완료 | 100% | Burner NCR 종료검사는 5월 말 경 예상 | 박재석 책임 | 나광조 책임
153 | SHN1 | 장치 | 2110-2001-002 | CRACKING FURNACE (NON-PROPRIETARY) | Radiant/ STACK : 10 Set S/S : 7262.5 ton GTE DUCT : 2163 ton Convection module : 96 ea damper/ Seal air fan : 40 Set seal air fan : 14 Set flow meter : 100 ea ignition panel : 10 Pnl. | 2026-04-30 | 99.9% | MV cable IRC 잔여, MDRS 미제출 | 박재석 책임 | 나광조 책임
154 | SHN1 | 장치 | 2130-2004-001 | REGENRATIVE THERMAL OXIDIZER |  | 2026-04-10 | 100% | MDRS 4월 10일 제출 | 나광조 책임 | 박재석 책임
155 | SHN1 | 장치 | 2000-2013-001 | STORAGE TANK | 19 ea | 완료 | 100% | MDRS 제출 완료 | 박재석 책임 | 나광조 책임
156 | SHN1 | 회전 | 2000-1014-001 | CRANE & HOIST | 20 Set | 완료 | 100% | MDRS 종결 | 나광조 책임 | 박재석 책임
157 | SHN1 | 회전 | 2135-1003-001 | COOLING TOWER |  | 완료 | 100% | MDRS 종결 | 나광조 책임 | 박재석 책임
158 | SHN1 | 전기 | 2000-3003-001 | 33KV GAS INSULATED SWITCHGEAR (C-GIS) | 26 Set | 완료 | 100% |  | 이해석 책임 | 술탄 매니저
159 | SHN1 | 전기 | 2000-3005-001 | LV SWITCHGEAR AND MCC WITH BUS DUCT (LV VVVF 제외) | 414 Pnl. BUSDUCT: 293 ea Aux PDP : 76 Pnl. | 완료 | 100% | MDRS 제출 완료 - Code.A | 이해석 책임 | 술탄 매니저
160 | SHN1 | 전기 | 2000-3007-001 | POWER CAPACITOR BANK | 10 Set | 2026-04-30 | 100% | MDRS 제출/수정 진행중 - Code.B (4/13 Vout) | 이해석 책임 | 술탄 매니저
161 | SHN1 | 전기 | 2000-3009-001 | DISTRIBUTION POWER TRANSFORMER WITH NGR | 71 Set | 완료 | 100% | MDRS 제출 완료 - Code.A | 이해석 책임 | 술탄 매니저
162 | SHN1 | 전기 | 2000-3011-001 | PMS (POWER MONITORING SYSTEM) | 30 Pnl. | 2026-04-30 | 90% | MDRS 제출 완료 - CodeA Cout (발주처 검토중 ,4/10~) | 이해석 책임 | 술탄 매니저
163 | SHN1 | 전기 | 2000-3012-001 | AC / DC UPS WITH BATTERY | 19 Set | 2026-04-30 | 100% | MDRS 제출 완료 - CodeA Cout (발주처 검토중 ,4/10~) | 이해석 책임 | 술탄 매니저
164 | SHN1 | 전기 | 2000-3013-001 | SOLAR POWER SYSTEM | 7 Group | 2026-04-30 | 99% | 주자재 납품 완료 ( 잔여 : Cable ,Tray 일부) | 이해석 책임 | 술탄 매니저
165 | SHN1 | 전기 | 2000-3021-001 | CATHODIC PROTECTION SYSTEM | 1 lot | 2026-05-30 | 90% | TR/RECTIFIER 21대 4/ 20~ 검사 진행 예정 | 이해석 책임 | 술탄 매니저
166 | SHN1 | 전기 | 2000-3028-001 | 33KV POWER AND CONTROL CABLE WITH ACCESSORIES | 0.6kV/1kV TFR-CVV 12C x 2.5 ㎟ 6,720 m 33kv Power Cable 150mm^2) 10650 m 33kv Power Cable 185mm^2) 6040 m 33kv Power Cable 240mm^2) 660 m 33kv Power Cable 300mm^2) 3540 m 33kv Power Cable 400mm^2) 4530 m 33kv Power Cable 500mm^2) 8498 m 33kv Power Cable 630mm^2) 12480 m Fiber optic cable : 11688 m Termination kit : 7 set | 2026-04-30 | 100% | MDR 제출 지연중 | 이해석 책임 | 술탄 매니저
167 | SHN1 | 전기 | 2000-3201-001 | COMMUNICATION SYSTEM (PKG #1) | 1 lot | 2026-05-30 | 97% | - Video conference sytem , PABX VO 검사 일정 협의중 - LAB Building remodeling 관련 추가물량 발생 (TBD) | 이해석 책임 | 술탄 매니저
168 | SHN1 | 전기 | 2000-3202-001 | ACS SYSTEM | 1 lot | 2026-04-30 | 100% | MDRS 제출 지연중 | 이해석 책임 | 술탄 매니저
169 | SHN1 | 전기 | 2000-3203-001 | CCTV SYSTEM (PKG #1) | 1 lot | 2026-05-30 | 73% | 잔여 검사 일정 확인중 (VO 물량 포함) | 이해석 책임 | 술탄 매니저
170 | SHN1 | 전기 | 2000-3204-001 | PAGING SYSTEM (PKG #1) | 1 lot | 2026-05-30 | 99% | 잔여 검사 일정 확인중 | 이해석 책임 | 술탄 매니저
171 | SHN1 | 전기 | 2000-3010-001 | DIESEL ENGINE GENERATOR | 1 Set | 2026-04-30 | 100% | MDRS 제출/수정 진행중 - Code.B (3/30 Vout) | 이해석 책임 | 술탄 매니저
172 | SHN1 | 계장 | 2130-4009-001 | ODOR MONITORING SYSTEM | 1 Lot | 완료 | 100% | MDRS 제출 완료 - Code.A | 이해석 책임 | 술탄 매니저
173 | SHN1 | 계장 | 2110-4012-001 | LEAK DETECTION AND REPAIRING SYSTEM (LDAR) | 1 lot | 2026-05-01 | 0% | 구매 자재로서, TEST 행위 X. 서류만 검토 | 이해석 책임 | 술탄 매니저
174 | SHN1 | 기타 | 2110-8003-001 | LABORATORY EQUIPMENT | 1 lot | 2026-04-01 | 99% | IRC 100%발급후 ODC LAB에서 보관 (잔여 : 시약 1 SET) | 이해석 책임
175 | SHN1 | 기타 | 2110-8003-002 | LABORATORY EQUIPMENT (GC) | 1 lot | 2026-04-01 | 100% | MDR 제출 지연중 | 이해석 책임
176 | SEED | 회전 | RM001 | STEAM TURBINE GNERATOR PKG | Duct, Bellow, Dumper 1 Lot |  | 0% |  | 강태준 책임 | 나광조 책임
177 | MIP6 | 장치 | MS019 | DEHYDRATOR & DESALTER |  | 완료 | 100% | - | 정진우 책임
178 | MIP6 | 장치 | MS020 | WATER OIL SEPARATOR PKG |  | 완료 | 100% | - | 정진우 책임
179 | MIP6 | 장치 | MS021 | LOW PRESSURE PRODUCTION TRAP (LPPT) |  | 완료 | 100% | - | 정진우 책임
180 | MIP6 | 장치 | MS001 | VESSEL I (CS) |  | 완료 | 100% | - | 정진우 책임
181 | MIP6 | 장치 | MS002 | VESSEL II (SS) |  | 완료 | 100% | - | 정진우 책임
182 | MIP6 | 장치 | MS004 | INTERNAL OF STABILIZER |  | 완료 | 100% | - | 정진우 책임
183 | MIP6 | 장치 | MS005 | FILTER (NON SOUR) |  | 완료 | 100% | - | 정진우 책임
184 | MIP6 | 장치 | MS006 | SHELL & TUBE HEAT EXCHANGER |  | 완료 | 100% | - | 정진우 책임
185 | MIP6 | 장치 | MS007 | AIR COOLED HEAT EXCHANGER (TUBE BUNDLE ASSEMBLY) |  | 완료 | 100% | - | 정진우 책임
186 | MIP6 | 장치 | MS008 | ELECTRICAL HEATER | 4 sets | 2026-04-30 | 100% | IDR / VIRB 제출 필요 | 나광조 책임 | 정진우 책임
187 | MIP6 | 장치 | MS009 | STORAGE TANK |  | 완료 | 100% | - | 정진우 책임
188 | MIP6 | 장치 | MS011 | STATIC MIXER |  | 완료 | 100% | - | 정진우 책임
189 | MIP6 | 장치 | MS012 | AIR DRYER PACKAGE |  | 완료 | 100% | - | 정진우 책임
190 | MIP6 | 장치 | MS013 | N2 GENERATION PACKAGE |  | 완료 | 100% | - | 정진우 책임
191 | MIP6 | 장치 | MS014 | LIQUID NITROGEN VAPORISER PACKAGE |  | 완료 | 100% | - | 정진우 책임
192 | MIP6 | 장치 | MS015 | VACCUM DEAERATION PACKAGE |  | 완료 | 100% | - | 정진우 책임
193 | MIP6 | 장치 | MS016 | FLARE PACKAGE |  | 완료 | 100% | - | 정진우 책임
194 | MIP6 | 장치 | MS017 | CHEMICAL INJECTION PKG OF TEG DEHYDRATION PACKAGE |  | 완료 | 100% | - | 정진우 책임
195 | MIP6 | 장치 | MS018 | STEEL WORK OF HOT OIL FURNACE PACKAGE |  | 완료 | 100% | - | 정진우 책임
196 | MIP6 | 장치 | MS022 | STORAGE TANK (FRP) |  | 완료 | 100% | - | 정진우 책임
197 | MIP6 | 회전 | MR001 | CENTRIFUGAL COMPRESSOR |  | 완료 | 100% | - | 장동철 책임
198 | MIP6 | 회전 | MR002 | RECIPROCATING COMPRESSOR |  | 완료 | 100% | - | 장동철 책임
199 | MIP6 | 회전 | MR003 | AIR COMPRESSOR PACKAGE (INTEGRALLY GEARED) |  | 완료 | 100% | - | 장동철 책임
200 | MIP6 | 회전 | MR004 | CENTRIFUGAL PUMP (API 610 - OH TYPE) |  | 완료 | 100% | - | 장동철 책임
201 | MIP6 | 회전 | MR005 | CENTRIFUGAL PUMP (API 610 - BB TYPE) |  | 완료 | 100% | - | 장동철 책임
202 | MIP6 | 회전 | MR006 | CENTRIFUGAL PUMP (API 610 - VS TYPE) |  | 완료 | 100% | - | 장동철 책임
203 | MIP6 | 회전 | MR007 | ROTARY PUMP (API 676) |  | 완료 | 100% | - | 장동철 책임
204 | MIP6 | 회전 | MR008 | SEALLESS PUMP ASME B 73.3 / ISO 15783 |  | 완료 | 100% | - | 장동철 책임
205 | MIP6 | 회전 | MR009 | CENTRIFUGAL PUMP (API 610 - OH6 TYPE) |  | 완료 | 100% | - | 장동철 책임
206 | MIP6 | 회전 | MR010 | CENTRIFUGAL PUMP-OH TYPE |  | 완료 | 100% | - | 장동철 책임
207 | MIP6 | 회전 | MR011 | API CENTRIFUGAL PUMP-VS |  | 완료 | 100% | - | 장동철 책임
208 | MIP6 | 회전 | MR012 | FIREWATER PUMP |  | 완료 | 100% | - | 장동철 책임
209 | MIP6 | 회전 | MR013 | SUBMERSIBLE PUMP |  | 완료 | 100% | - | 장동철 책임
210 | MIP6 | 회전 | MR015 | ODOR ABATEMENT PACKAGE |  | 완료 | 100% | - | 장동철 책임
211 | MIP6 | 회전 | MR016 | OILY WATER TREATMENT PACKAGE |  | 완료 | 100% | - | 장동철 책임
212 | MIP6 | 회전 | MR017 | OIL DISC SKIMMER (FLOATING) |  | 완료 | 100% | - | 장동철 책임
213 | MIP6 | 회전 | MR018 | CHEMICAL INJECTION PACKAGE |  | 완료 | 100% | - | 장동철 책임
214 | MIP6 | 회전 | MR019 | CRANE |  | 완료 | 100% | - | 장동철 책임
215 | MIP6 | 회전 | MR020 | WORKSHOP EQUIPMENT |  | 완료 | 100% | - | 장동철 책임
216 | MIP6 | 회전 | MR021 | FIRE AND SAFETY EQUIPMENT |  | 완료 | 100% | - | 장동철 책임
217 | MIP6 | 회전 | MR022 | CRANE & HOIST |  | 완료 | 100% | - | 장동철 책임
218 | MIP6 | 회전 | MR024 | OWSF WATER TREATMENT PACKAGE |  | 완료 | 100% | - | 장동철 책임
219 | MIP6 | 회전 | MR025 | SEWAGE TREATMENT PACKAGE |  | 완료 | 100% | - | 장동철 책임
220 | MIP6 | 회전 | MR026 | WATER INJECTION PUMP |  | 완료 | 100% | - | 장동철 책임
221 | MIP6 | 회전 | MR027 | TRUCK WEIGH BRIDGE |  | 완료 | 100% | - | 장동철 책임
222 | MIP6 | 회전 | MR028 | SIDE ENTRY TANK MIXER |  | 완료 | 100% | - | 장동철 책임
223 | MIP6 | 배관 | PI001 | PIPE (CS, LTCS, GALV. SMLS) |  | 완료 | 100% | - | 장동철 책임
224 | MIP6 | 배관 | PI002 | PIPE (CS, LTCS WELD) |  | 완료 | 100% | - | 장동철 책임
225 | MIP6 | 배관 | PI003 | PIPE (SS, SUPER DUPLEX, NICKEL ALLOY, SMLS) |  | 완료 | 100% | - | 장동철 책임
226 | MIP6 | 배관 | PI004 | PIPE (SS, SUPER DUPLEX WELD) |  | 완료 | 100% | - | 장동철 책임
227 | MIP6 | 배관 | PI005 | FBE LINED AND COATED PIPING |  | 완료 | 100% | - | 장동철 책임
228 | MIP6 | 배관 | PI006 | PERT PIPING |  | 완료 | 100% | - | 장동철 책임
229 | MIP6 | 배관 | PI007 | PTFE LINED PIPING |  | 완료 | 100% | - | 장동철 책임
230 | MIP6 | 배관 | PI008 | COPPER NICKEL PIPING |  | 완료 | 100% | - | 장동철 책임
231 | MIP6 | 배관 | PI009 | RTR PIPING |  | 완료 | 100% |  | 장동철 책임 | 강태준 책임
232 | MIP6 | 배관 | PI010 | HDPE PIPING |  | 완료 | 100% | - | 장동철 책임
233 | MIP6 | 배관 | PI011 | FORGED FITTING |  | 완료 | 100% | - | 장동철 책임
234 | MIP6 | 배관 | PI012 | WROUGHT FITTING |  | 완료 | 100% | - | 장동철 책임
235 | MIP6 | 배관 | PI013 | FLANGE |  | 완료 | 100% | - | 장동철 책임
236 | MIP6 | 배관 | PI015 | HOT BEND |  | 완료 | 100% | - | 장동철 책임
237 | MIP6 | 배관 | PI016 | FABRICATED LATERAL |  | 완료 | 100% | - | 장동철 책임
238 | MIP6 | 배관 | PI019 | PIPE (NA SMLS) |  | 완료 | 100% | - | 장동철 책임
239 | MIP6 | 배관 | PI020 | PIPE (NA WELD) |  | 완료 | 100% | - | 장동철 책임
240 | MIP6 | 배관 | PI021 | BOLT & NUT |  | 완료 | 100% | - | 장동철 책임
241 | MIP6 | 배관 | PI022 | GASKET |  | 완료 | 100% | - | 장동철 책임
242 | MIP6 | 배관 | PI031 | FORGED VALVE |  | 완료 | 100% | - | 장동철 책임
243 | MIP6 | 배관 | PI032 | CASTING VALVE |  | 완료 | 100% | - | 장동철 책임
244 | MIP6 | 배관 | PI033 | BALL VALVE |  | 완료 | 100% | - | 장동철 책임
245 | MIP6 | 배관 | PI034 | BUTTERFLY VALVE |  | 완료 | 100% | - | 장동철 책임
246 | MIP6 | 배관 | PI035 | DUAL PLATE CHECK VALVE |  | 완료 | 100% | - | 장동철 책임
247 | MIP6 | 배관 | PI036 | NON SLAM CHECK VALVE |  | 완료 | 100% | - | 장동철 책임
248 | MIP6 | 배관 | PI037 | POST INDICATOR VALVE |  | 완료 | 100% | - | 장동철 책임
249 | MIP6 | 배관 | PI038 | BRONZE VALVE |  | 완료 | 100% | - | 장동철 책임
250 | MIP6 | 배관 | PI039 | DUCTILE IRON VALVE |  | 완료 | 100% | - | 장동철 책임
251 | MIP6 | 배관 | PI040 | PLUG VALVE |  | 완료 | 100% | - | 장동철 책임
252 | MIP6 | 배관 | PI041 | AIR RELEASE VALVE |  | 완료 | 100% | - | 장동철 책임
253 | MIP6 | 배관 | PI044 | CHOKE VALVE |  | 완료 | 100% | - | 장동철 책임
254 | MIP6 | 배관 | PI046 | API 6A BALL VALVE |  | 완료 | 100% | - | 장동철 책임
255 | MIP6 | 배관 | PI047 | LINED PLUG VALVE |  | 완료 | 100% | - | 장동철 책임
256 | MIP6 | 배관 | PI048 | CRYOGENIC VALVE |  | 완료 | 100% | - | 장동철 책임
257 | MIP6 | 배관 | PI051 | STRAINER |  | 완료 | 100% | - | 장동철 책임
258 | MIP6 | 배관 | PI053 | HOSE & HOSE CONNECTOR |  | 완료 | 100% | - | 장동철 책임
259 | MIP6 | 배관 | PI054 | INSULATON JOINT |  | 완료 | 100% | - | 장동철 책임
260 | MIP6 | 배관 | PI054 | SMLS FORGED RINGS |  | 완료 | 100% | - | 장동철 책임
261 | MIP6 | 배관 | PI056 | FLAME ARRESTOR |  | 완료 | 100% | - | 장동철 책임
262 | MIP6 | 배관 | PI057 | INJECTION QUILL |  | 완료 | 100% | - | 장동철 책임
263 | MIP6 | 배관 | PI058 | AIR TRAP |  | 완료 | 100% | - | 장동철 책임
264 | MIP6 | 배관 | PI059 | BARRED TEE |  | 완료 | 100% | - | 장동철 책임
265 | MIP6 | 배관 | PI060 | MECHANICAL INTERLOCK |  | 완료 | 100% | - | 장동철 책임
266 | MIP6 | 배관 | PI062 | SUPPORT (BULK / ITEMIZED) |  | 완료 | 100% | - | 장동철 책임
267 | MIP6 | 배관 | PI063 | SPRING SUPPORT |  | 완료 | 100% | - | 장동철 책임
268 | MIP6 | 배관 | PI065 | U-BOLT |  | 완료 | 100% | - | 장동철 책임
269 | MIP6 | 배관 | PI066 | CONICAL TYPE STRAINER |  | 완료 | 100% | - | 장동철 책임
270 | MIP6 | 배관 | PI101 | PIPE (CS, LTCS, GALV. SMLS) - 2 |  | 완료 | 100% | - | 장동철 책임
271 | MIP6 | 배관 | PI121 | BOLT & NUT - 2 |  | 완료 | 100% | - | 장동철 책임
272 | MIP6 | 배관 | PI113 | FLANGE |  | 완료 | 100% | - | 장동철 책임
273 | MIP6 | 배관 | PI131 | FORGED VALVE |  | 완료 | 100% | - | 장동철 책임
274 | MIP6 | 배관 | PI162 | SUPPORT- 2 |  | 완료 | 100% | - | 장동철 책임
275 | MIP6 | 배관 | PI163 | SPRING SUPPORT |  | 완료 | 100% | - | 장동철 책임
276 | MIP6 | 배관 | PI201 | STOCKIEST CS, LTCS, GALV, SMLS PIPE |  | 완료 | 100% | - | 장동철 책임
277 | MIP6 | 배관 | PI213 | FLANGE-3 |  | 완료 | 100% | - | 장동철 책임
278 | MIP6 | 전기 | EL001 | 230KV GIS |  | 완료 | 100% | - | 이해석 책임
279 | MIP6 | 전기 | EL002 | 230KV CABLE AND ACCESSORIES |  | 완료 | 100% | - | 이해석 책임
280 | MIP6 | 전기 | EL003 | CONTROL AND PROTECTIVE PANEL |  | 완료 | 100% | - | 이해석 책임
281 | MIP6 | 전기 | EL005 | 230KV GANTRY |  | 완료 | 100% | - | 이해석 책임
282 | MIP6 | 전기 | EL006 | MODIFICATION WORK FOR MV SWGR |  | 완료 | 100% | - | 이해석 책임
283 | MIP6 | 전기 | EL007 | MV SWGR/MCC, CABLEBUS |  | 완료 | 100% | - | 이해석 책임
284 | MIP6 | 전기 | EL008 | LV SWGR/MCC, CABLEBUS |  | 완료 | 100% | - | 이해석 책임
285 | MIP6 | 전기 | EL009 | POWER SYSTEM AUTOMATION |  | 완료 | 100% | - | 이해석 책임
286 | MIP6 | 전기 | EL010 | EMERGENCY DIESEL GENERATOR |  | 완료 | 100% | - | 이해석 책임
287 | MIP6 | 전기 | EL011 | 230KV POWER TRANSFORMER & NGR & SHUNT REACTOR |  | 완료 | 100% | - | 이해석 책임
288 | MIP6 | 전기 | EL012 | DISTRIBUTION TRANSFORMER & NGR |  | 완료 | 100% | - | 이해석 책임
289 | MIP6 | 전기 | EL013 | AC UPS & DC BATTERY CHARGER SYSTEM |  | 완료 | 100% | - | 이해석 책임
290 | MIP6 | 전기 | EL014 | CATHODIC PROTECTION SYSTEM |  | 완료 | 100% | - | 이해석 책임
291 | MIP6 | 전기 | EL015 | ELECTRICAL HEAT TRACING SYSTEM |  | 완료 | 100% | - | 이해석 책임
292 | MIP6 | 전기 | EL016 | TELECOMMUNICATION SYSTEM |  | 완료 | 100% | - | 이해석 책임
293 | MIP6 | 전기 | EL017 | FIRE ALARM SYSTEM |  | 완료 | 100% | - | 이해석 책임
294 | MIP6 | 전기 | EL018 | POWER DISTRIBUTION BOARD (NON. EXP.) |  | 완료 | 100% | - | 이해석 책임
295 | MIP6 | 전기 | EL019 | POWER DISTRIBUTION BOARD (EXP.) |  | 완료 | 100% | - | 이해석 책임
296 | MIP6 | 전기 | EL020 | LIGHTING FIXTURE, RECEPTACLE |  | 완료 | 100% | - | 이해석 책임
297 | MIP6 | 전기 | EL021 | LCS & JUNCTION BOX |  | 완료 | 100% | - | 이해석 책임
298 | MIP6 | 전기 | EL022 | CABLE TRAYS |  | 완료 | 100% | - | 이해석 책임
299 | MIP6 | 전기 | EL023 | GROUNDING & LIGHTNING PROTECTION SYSTEM |  | 완료 | 100% | - | 이해석 책임
300 | MIP6 | 전기 | EL024 | CABLE GLAND |  | 완료 | 100% | - | 이해석 책임
301 | MIP6 | 전기 | EL025 | TERMINATION KIT |  | 완료 | 100% | - | 이해석 책임
302 | MIP6 | 전기 | EL026 | POWER CABLE |  | 완료 | 100% | - | 이해석 책임
303 | MIP6 | 전기 | EL027 | CONDUIT & FITTINGS |  | 완료 | 100% | - | 이해석 책임
304 | MIP6 | 전기 | EL028 | ELECTRICAL MISCELLANEOUS MATERIALS |  | 완료 | 100% | - | 이해석 책임
305 | MIP6 | 전기 | EL030 | PAD MOUNTED SF6 SWGR |  | 완료 | 100% | - | 이해석 책임
306 | MIP6 | 전기 | EL031 | COMMUNICATION CABLE (FIBER OPTIC) |  | 완료 | 100% | - | 이해석 책임
307 | MIP6 | 전기 | EL032 | MODIFICATION WORK FOR AC UPS |  | 완료 | 100% | - | 이해석 책임
308 | MIP6 | 계장 | IN001 | PROCESS CONTROL SYSTEM (DCS/DISTRIBUTION CONTROL SYSTEM) |  | 완료 | 100% | - | 이해석 책임
309 | MIP6 | 계장 | IN002 | ANALYZER SYSTEM WITH SHELTER |  | 완료 | 100% | - | 이해석 책임
310 | MIP6 | 계장 | IN003 | CORROSION MONITORING SYSTEM (CRMS) |  | 완료 | 100% | - | 이해석 책임
311 | MIP6 | 계장 | IN005 | PIPELINE LEAK DETECTION SYSTEM (PLDS) |  | 완료 | 100% | - | 이해석 책임
312 | MIP6 | 계장 | IN006 | AIR QUALITY MONITORING SYSTEM (AQMS) |  | 완료 | 100% | - | 이해석 책임
313 | MIP6 | 계장 | IN008 | ON-OFF VALVE_HIPS |  | 완료 | 100% | - | 장동철 책임
314 | MIP6 | 계장 | IN009 | CONTROL VALVE |  | 완료 | 100% | - | 장동철 책임
315 | MIP6 | 계장 | IN010 | ON-OFF VALVE_BALL TYPE |  | 완료 | 100% | - | 장동철 책임
316 | MIP6 | 계장 | IN011 | ON-OFF VALVE_GATE TYPE |  | 완료 | 100% | - | 장동철 책임
317 | MIP6 | 계장 | IN012 | ON-OFF VALVE (GLOBE) |  | 완료 | 100% | - | 장동철 책임
318 | MIP6 | 계장 | IN013 | MOTOR OPERATED VALVE_BALL |  | 완료 | 100% | - | 장동철 책임
319 | MIP6 | 계장 | IN014 | MOTOR OPERATED VALVE_GATE |  | 완료 | 100% | - | 장동철 책임
320 | MIP6 | 계장 | IN015 | PRESSURE SAFETY & RELIEF VALVE |  | 완료 | 100% | - | 장동철 책임
321 | MIP6 | 계장 | IN016 | MAGNETIC FLOWMETER |  | 완료 | 100% | - | 이해석 책임
322 | MIP6 | 계장 | IN017 | ULTRASONIC FLOWMETER |  | 완료 | 100% | - | 이해석 책임
323 | MIP6 | 계장 | IN018 | FLOW ELEMENT |  | 완료 | 100% | - | 이해석 책임
324 | MIP6 | 계장 | IN019 | TRANSMITTER |  | 완료 | 100% | - | 이해석 책임
325 | MIP6 | 계장 | IN020 | NUCLEAR LEVEL TRANSMITTER |  | 완료 | 100% | - | 이해석 책임
326 | MIP6 | 계장 | IN021 | LEVEL TRANSMITTER |  | 완료 | 100% | - | 이해석 책임
327 | MIP6 | 계장 | IN022 | LEVEL GAUGE |  | 완료 | 100% | - | 이해석 책임
328 | MIP6 | 계장 | IN023 | LOCAL GAUGE |  | 완료 | 100% | - | 이해석 책임
329 | MIP6 | 계장 | IN024 | GAS DETECTOR |  | 완료 | 100% | - | 이해석 책임
330 | MIP6 | 계장 | IN025 | CONTROL VALVE (NON-GENERAL SERVICES) |  | 완료 | 100% | - | 장동철 책임
331 | MIP6 | 계장 | IN026 | ROTAMETER |  | 완료 | 100% | - | 이해석 책임
332 | MIP6 | 계장 | IN031 | BUCKLING PIN RELIEF VALVE |  | 완료 | 100% | - | 장동철 책임
333 | MIP6 | 계장 | IN032 | CORIOLIS FLOWMETER |  | 완료 | 100% | - | 이해석 책임
334 | MIP6 | 계장 | IN033 | HIGH INTEGRITY PROTECTION SYSTEM (HIPS) |  | 완료 | 100% | - | 이해석 책임
335 | MIP6 | 계장 | IN100 | INSTRUMENT CABLE |  | 완료 | 100% | - | 이해석 책임
336 | MIP6 | 계장 | IN101 | INSTRUMENT CABLE TRAY& TRAY FITTING |  | 완료 | 100% | - | 이해석 책임
337 | MIP6 | 계장 | IN102 | INSTRUMENT JUNCTION BOX |  | 완료 | 100% | - | 이해석 책임
338 | MIP6 | 계장 | IN103 | INSTRUMENT CABLE GLAND |  | 완료 | 100% | - | 이해석 책임
339 | MIP6 | 계장 | IN104 | INSTRUMENT CONDUIT & CONDUIT FITTING |  | 완료 | 100% | - | 이해석 책임
340 | MIP6 | 계장 | IN105 | INSTRUMENT TUBE |  | 완료 | 100% | - | 이해석 책임
341 | MIP6 | 계장 | IN106 | INSTRUMENT TUBE FITTING |  | 완료 | 100% | - | 이해석 책임
342 | MIP6 | 계장 | IN107 | MULTI CABLE TRANSIT (MCT) |  | 완료 | 100% | - | 이해석 책임
343 | MIP6 | 계장 | IN108 | INSTRUMENT SUPPORT & CONSUMABLE MATERIAL |  | 완료 | 100% | - | 이해석 책임
344 | MIP6 | 공조 | HV001 | HVAC EQUIPMENT & CONTROL SYSTEM |  | 완료 | 100% | - | 장동철 책임
345 | MIP6 | 공조 | HV003 | MFD, MFSD, MFGD & MGD |  | 완료 | 100% | - | 장동철 책임
346 | MIP6 | 철골 | SC001 | STEEL STRUCTURE |  | 완료 | 100% | - | 고팔라크리스낸 매니저 | 장동철 책임
347 | MIP6 | 철골 | SC002 | ANCHOR BOLT FOR STEEL STRUCTURE |  | 완료 | 100% | - | 고팔라크리스낸 매니저 | 장동철 책임
348 | SM12 | 장치 | MS001 | PRESSURE VESSEL-I (CS) |  | 완료 | 100% | - | 정진우 책임
349 | SM12 | 장치 | MS002 | PRESSURE VESSEL II (SS) |  | 완료 | 100% | - | 정진우 책임
350 | SM12 | 장치 | MS003 | PLATE AND FRAME TYPE HEAT EXCHANGER |  | 완료 | 100% | - | 정진우 책임
351 | SM12 | 장치 | MS004 | FIELD FABRICATED STORAGE TANK |  | 완료 | 100% | - | 정진우 책임
352 | SM12 | 장치 | MS005 | STORAGE TANK (FRP) |  | 완료 | 100% | - | 정진우 책임
353 | SM12 | 장치 | MS006 | WALNUT SHELL FILTRATION PACKAGE |  | 완료 | 100% | - | 정진우 책임
354 | SM12 | 장치 | MS007 | AIR DRYER PACKAGE |  | 완료 | 100% | - | 정진우 책임
355 | SM12 | 장치 | MS008 | LIN AND LOX STORAGE AND VAPORIZATION PACKAGE |  | 완료 | 100% | - | 정진우 책임
356 | SM12 | 장치 | MS009 | FLARE PACKAGE (FLARE & BURN PIT PACKAGE) | HP Flare 3set (Tip, Stack, Seal, Skid 각 3 ea) LP Flare 2set (Tip, Stack, Seal, Skid 각 2EA, Seal Drum 4 ea) LT Flare 2set (Tip, Stack, Seal Skid 각 2 ea) Commmon HP/LT T&I (Tip, Stack, Seal, Skid 각 1 ea) Burn Pit (Tip 4EA, Skid 2 ea) | 완료 | 100% | IRC 상 99.997%이나 종결로 간주, IDR 작성 / 제출 필요 | 정진우 책임 | 최영준 책임
357 | SM12 | 장치 | MS010 | FLARE GAS RECOVERY PACKAGE | Flare Gas Recovery PKG 2 PKG (Piping Spool, Valve, Instrument etc.) Ejector 4 ea Air Cooled HEX 2 ea Separation Vessel 4 ea Centrifugal Pump 4 ea | 2026-05-28 | 99% | FGRU Suction Piping Line 설계 오류로 인한 Design THK 부족으로 추가 발주 되어야 함 | 정진우 책임 | 최영준 책임
358 | SM12 | 장치 | MS011 | EXPLOSION RELIEF PANEL |  | 완료 | 100% | - | 정진우 책임
359 | SM12 | 장치 | MS012 | STATIC MIXER |  | 완료 | 100% | - | 정진우 책임
360 | SM12 | 장치 | MS014 | AIR SEPARATION UNIT |  | 완료 | 100% | ASU 사고 후 재 발주 필요 Item 파악 중 | 장동철 책임 | 강태준 책임
361 | SM12 | 장치 | MS015 | TSA REACTIVATION HEATER |  | 완료 | 100% |  | 나광조 책임 | 정진우 책임
362 | SM12 | 장치 | MS017 | DISPOSAL VAPORIZER |  | 완료 | 100% | - | 정진우 책임
363 | SM12 | 장치 | MS018 | SAND FILTER PACKAGE |  | 완료 | 100% | - | 정진우 책임
364 | SM12 | 장치 | MS020 | ODOR ABATEMENT PACKAGE |  | 완료 | 100% | - | 정진우 책임
365 | SM12 | 회전 | RM001 | AIR COMPRESSOR |  | 완료 | 100% | - | 강태준 책임
366 | SM12 | 회전 | RM002 | CENTRIFUGAL PUMP API 610-BB |  | 완료 | 100% | - | 강태준 책임
367 | SM12 | 회전 | RM003 | CENTRIFUGAL PUMP API 610-OH2 |  | 완료 | 100% | - | 강태준 책임
368 | SM12 | 회전 | RM004 | CENTRIFUGAL PUMP ASME B73.1 OR ISO 5199 |  | 완료 | 100% | - | 강태준 책임
369 | SM12 | 회전 | RM005 | SELF-PRIMING PUMP |  | 완료 | 100% | - | 강태준 책임
370 | SM12 | 회전 | RM006 | SUBMERSIBLE PUMP |  | 완료 | 100% | - | 강태준 책임
371 | SM12 | 회전 | RM009 | FIRE WATER PUMP |  | 완료 | 100% | - | 강태준 책임
372 | SM12 | 회전 | RM010 | VERTICAL PUMP |  | 완료 | 100% | - | 강태준 책임
373 | SM12 | 회전 | RM011 | CHEMICAL INJECTION PACKAGE |  | 완료 | 100% |  | 강태준 책임
374 | SM12 | 회전 | RM012 | CHILLER PACKAGE |  | 완료 | 100% | - | 강태준 책임
375 | SM12 | 회전 | RM013 | CPI (CORRUGATED PLATE INTERCEPTOR) & OIL SKIMMER |  | 완료 | 100% | - | 강태준 책임
376 | SM12 | 회전 | RM014 | WATER RECOVERY PACKAGE |  | 완료 | 100% |  | 강태준 책임 | 강태준 책임
377 | SM12 | 회전 | RM015 | OILY WATER BOOM |  | 완료 | 100% | - | 강태준 책임
378 | SM12 | 회전 | RM016 | COOLING TOWER |  | 완료 | 100% |  | 강태준 책임
379 | SM12 | 회전 | RM017 | CRANE AND HOIST |  | 완료 | 100% |  | 강태준 책임
380 | SM12 | 회전 | RM018 | WORKSHOP EQUIPMENT |  | 완료 | 100% | - | 강태준 책임
381 | SM12 | 회전 | RM020 | VERTICAL PUMP II (API 610 VS1 TYPE) |  | 완료 | 100% | - | 강태준 책임
382 | SM12 | 회전 | RM021 | MAIN AIR COMPRESSOR FOR ASU |  | 완료 | 100% |  | 강태준 책임
383 | SM12 | 회전 | RM022 | CENTRIFUGAL PUMP (API 610 - OH2) - II |  | 완료 | 100% | - | 강태준 책임
384 | SM12 | 회전 | RM023 | SEALLESS PUMP |  | 완료 | 100% | - | 강태준 책임
385 | SM12 | 배관 | PI001 | PIPE (CS, LTCS, GALV, SMLS) |  | 완료 | 100% | - | 장동철 책임
386 | SM12 | 배관 | PI002 | PIPE (CS, LTCS WELDED) |  | 완료 | 100% | - | 장동철 책임
387 | SM12 | 배관 | PI003 | PIPE (SS, NICKEL ALLOY, SMLS) |  | 완료 | 100% | 2개 PO 분리 발주 | 장동철 책임
388 | SM12 | 배관 | PI004 | PIPE (SS, WELDED) |  | 완료 | 100% | - | 장동철 책임
389 | SM12 | 배관 | PI007 | FBE LINED AND COATED PIPING | Pipe: 32,195.6 m, Fitting: 20,489 ea | 완료 | 109.1% | IDR 작성/제출 필요 | 장동철 책임 | 강태준 책임
390 | SM12 | 배관 | PI008 | PTFE LINED PIPING |  | 완료 | 100% | External Coating 결함 관련 현장에서 조치 완료 | 장동철 책임 | 강태준 책임
391 | SM12 | 배관 | PI009 | COPPER NICKEL PIPING |  | 완료 | 100% |  | 장동철 책임
392 | SM12 | 배관 | PI010 | RTR PIPING |  | 완료 | 100% | - | 장동철 책임
393 | SM12 | 배관 | PI011 | HDPE PIPING |  | 완료 | 100% | - | 장동철 책임
394 | SM12 | 배관 | PI012 | CLAD PIPING |  | 완료 | 100% |  | 장동철 책임 | 강태준 책임
395 | SM12 | 배관 | PI016 | FORGED FITTING |  | 완료 | 100% |  | 장동철 책임 | 강태준 책임
396 | SM12 | 배관 | PI017 | WROUGHT FITTING |  | 완료 | 100% | 3개 PO 분리 발주 | 장동철 책임 | 강태준 책임
397 | SM12 | 배관 | PI018 | FLANGE |  | 완료 | 100% | 9/22 추가 분 검사 예정 | 장동철 책임 | 강태준 책임
398 | SM12 | 배관 | PI021 | BOLT / NUT |  | 완료 | 100% |  | 장동철 책임 | 강태준 책임
399 | SM12 | 배관 | PI022 | GASKET |  | 완료 | 100% | Level 0 | 장동철 책임 | 강태준 책임
400 | SM12 | 배관 | PI024 | HOT BEND |  | 완료 | 100% | 100% | 장동철 책임
401 | SM12 | 배관 | PI025 | FABRICATED LATERAL |  | 완료 | 100% | - | 장동철 책임
402 | SM12 | 배관 | PI031 | FORGED VALVE |  | 완료 | 100% |  | 장동철 책임 | 강태준 책임
403 | SM12 | 배관 | PI032 | CASTING VALVE |  | 완료 | 100% | 3개 PO 분리 발주 1. AMPO: 100.00% 2. SPSV: 100.00% 3. PK: 100.00% | 장동철 책임 | 강태준 책임
404 | SM12 | 배관 | PI033 | BALL VALVE |  | 완료 | 100% | 1. IVM: 100.00% 2. OMB: 100.00% | 장동철 책임 | 강태준 책임
405 | SM12 | 배관 | PI034 | BUTTERFLY VALVE |  | 완료 | 100% | (IDR 작성/제출 필요) | 장동철 책임 | 강태준 책임
406 | SM12 | 배관 | PI035 | DUAL PLATE CHECK VALVE |  | 완료 | 100% | - | 장동철 책임
407 | SM12 | 배관 | PI036 | NON-SLAM CHECK VALVE |  | 완료 | 100% | - | 장동철 책임
408 | SM12 | 배관 | PI037 | POST INDICATE VALVE |  | 완료 | 100% | - | 장동철 책임
409 | SM12 | 배관 | PI038 | BRONZE VALVE |  | 완료 | 100% | 추가 발주 VO7 | 장동철 책임 | 강태준 책임
410 | SM12 | 배관 | PI039 | DUCTILE IRON EPOXY LINED VALVE |  | 완료 | 100% | - | 장동철 책임
411 | SM12 | 배관 | PI040 | PLUG VALVE |  | 완료 | 100% | 2개 PO 분리 발주 1. Flowserve: 100.00% 2. G&C: 100.00% | 장동철 책임 | 강태준 책임
412 | SM12 | 배관 | PI041 | AIR RLEASE VALVE |  | 완료 | 100% | - | 장동철 책임
413 | SM12 | 배관 | PI051 | STRAINER |  | 완료 | 100% | - | 장동철 책임
414 | SM12 | 배관 | PI052 | STEAM AND AIR TRAP |  | 완료 | 100% | Level 0 | 장동철 책임
415 | SM12 | 배관 | PI053 | EXPANSION JOINT |  | 완료 | 100% | - | 장동철 책임
416 | SM12 | 배관 | PI054 | SUPPORT |  | 완료 | 100% | - | 장동철 책임
417 | SM12 | 배관 | PI055 | SPRING SUPPORT |  | 완료 | 100% | - | 장동철 책임
418 | SM12 | 배관 | PI056 | HOSE CONNECTOR |  | 완료 | 100% | - | 장동철 책임
419 | SM12 | 배관 | PI058 | FLAME ARRESTOR |  | 완료 | 100% | - | 장동철 책임
420 | SM12 | 배관 | PI060 | MEHANICAL INTERLOCK |  | 완료 | 100% | - | 장동철 책임
421 | SM12 | 배관 | PI062 | INJECTION QUILL |  | 완료 | 100% | - | 장동철 책임
422 | SM12 | 배관 | PI063 | OXYGEN NEEDLE VALVE |  | 완료 | 100% | - | 장동철 책임
423 | SM12 | 배관 | PI064 | OXYGEN GENERAL VALVE |  | 완료 | 100% | IDR 작성/제출 필요 | 장동철 책임 | 강태준 책임
424 | SM12 | 배관 | PI068 | NICKEL ALLOY PIPE |  | 완료 | 100% |  | 장동철 책임
425 | SM12 | 배관 | PI069 | BALL VALVE |  | 완료 | 100% | - | 장동철 책임
426 | SM12 | 배관 | PI070 | INSULATION JOINT |  | 완료 | 100% |  | 장동철 책임 | 강태준 책임
427 | SM12 | 배관 | PI071 | ASU OXYGEN GASKET |  | 완료 | 100% | - | 장동철 책임
428 | SM12 | 전기 | EL001 | HV SWGR & MCC | 22 sets | 완료 | 100% | - | 윤희수 책임
429 | SM12 | 전기 | EL002 | LV SWGR & MCC, LV SWITCHRACK | 36 sets | 완료 | 100% | - | 윤희수 책임
430 | SM12 | 전기 | EL003 | TRANSFORMER & NGR (230 / 13.8KV) | 26 units | 완료 | 100% | - | 윤희수 책임
431 | SM12 | 전기 | EL004 | TRANSFORMER & NGR | 31 units | 완료 | 100% | - | 윤희수 책임
432 | SM12 | 전기 | EL005 | POWER SYSTEM AUTOMATION | 27 sets | 완료 | 100% | - | 윤희수 책임
433 | SM12 | 전기 | EL006 | AC UPS & DC SYSTEM | 22 sets | 완료 | 100% | - | 윤희수 책임
434 | SM12 | 전기 | EL007 | EMERGENCY DIESEL GENERATOR | 4 units | 완료 | 100% | - | 윤희수 책임
435 | SM12 | 전기 | EL008 | LOCAL CONTROL STATION & JUNCTION BOX | 1 lot | 완료 | 100% | Level 0 | 윤희수 책임
436 | SM12 | 전기 | EL009 | FIRE ALARM SYSTEM | 1 lot | 완료 | 100% | Level 0 | 윤희수 책임
437 | SM12 | 전기 | EL010 | POWER DISTRIBUTION BOARD (EX, NON-EX) | 1 lot | 완료 | 100% | Level 0 | 윤희수 책임
438 | SM12 | 전기 | EL011 | ELECTRICAL TRACING SYSTEM | 1 lot | 완료 | 100% | Level 0 | 윤희수 책임
439 | SM12 | 전기 | EL012 | CATHODIC PROTECTION SYSTEM | 1 lot | 완료 | 100% | - | 윤희수 책임
440 | SM12 | 전기 | EL013 | LIGHTING FIXTURE (EX, NON-EX) | 1 lot | 완료 | 100% | Level 0 | 윤희수 책임
441 | SM12 | 전기 | EL014 | CABLE TRAY | 1 lot | 완료 | 100% | Level 0 | 윤희수 책임
442 | SM12 | 전기 | EL015 | GROUNDING SYSTEM | 1 lot | 완료 | 100% | Level 0 | 윤희수 책임
443 | SM12 | 전기 | EL016 | CABLE GLAND | 1 lot | 완료 | 100% | Level 0 | 윤희수 책임
444 | SM12 | 전기 | EL017 | TERMINATION & SPLICING KIT | 1 lot | 완료 | 100% | Level 0 | 윤희수 책임
445 | SM12 | 전기 | EL018 | CONDUIT & FITTING, BULK MATERIAL | 1 lot | 완료 | 100% | Level 0 | 윤희수 책임
446 | SM12 | 전기 | EL020 | POWER & CONTROL CABLE | 1 lot | 완료 | 100% | - | 윤희수 책임
447 | SM12 | 통신 | TE001 | TELECOMMUNICATION CABLE |  | 완료 | 100% | - | 윤희수 책임
448 | SM12 | 통신 | TE002 | PE ROUTER |  | 완료 | 100% | - | 윤희수 책임
449 | SM12 | 통신 | TE003 | TRANSMISSON SYSTEM |  | 완료 | 100% | - | 윤희수 책임
450 | SM12 | 통신 | TE004 | RADIO SYSTEM |  | 완료 | 100% | - | 윤희수 책임
451 | SM12 | 통신 | TE005 | PA/PAGING SYSTEM |  | 완료 | 100% | - | 윤희수 책임
452 | SM12 | 통신 | TE006 | RADIO TOWER |  | 완료 | 100% | - | 윤희수 책임
453 | SM12 | 전기 | EL201 | 230KV GIS (GAS INSULATED SWITCHGEAR) & GIB | 50 bays | 완료 | 100% | - | 윤희수 책임
454 | SM12 | 전기 | EL202 | 230KV CABLE & ACCESSORIES | 44,273 m | 완료 | 100% | - | 윤희수 책임
455 | SM12 | 전기 | EL203 | CONTROL AND PROTECTIVE RELAY PANEL | 88 sets | 완료 | 100% | - | 윤희수 책임
456 | SM12 | 계장 | IN001 | PROCESS CONTROL SYSTEM (DCS, ESD, MPS, CCS AND ETC.) | 325 sets | 완료 | 100% | - | 윤희수 책임
457 | SM12 | 계장 | IN002 | ANALYZER SYSTEM WITH SHELTER | 20 units | 완료 | 100% | Shop 검사 모두 완료 (MPS Shelter NCR open 남음) | 윤희수 책임 | 이해석 책임
458 | SM12 | 계장 | IN003 | STEAM TRAP MONITORING SYSTEM | 1 lot | 완료 | 100% | Level 0 | 윤희수 책임
459 | SM12 | 계장 | IN004 | CORROSION MONITORING SYSTEM (CRMS) | 1 lot | 완료 | 100% | Level 0 | 윤희수 책임
460 | SM12 | 계장 | IN005 | ON-OFF VALVE (BALL) |  | 완료 | 100% | 3개 PO 분리 발주 1. IVM: 100.00% 2. OMS: 100.00% 3. Petrolvalve: 100.00% | 장동철 책임 | 강태준 책임
461 | SM12 | 계장 | IN006 | MOV (MOTOR OPERATED VALVE - BUTTERFLY) |  | 완료 | 100% | - | 장동철 책임
462 | SM12 | 계장 | IN007 | CONTROL VALVE (GENERAL) |  | 완료 | 100% | - | 장동철 책임 | 강태준 책임
463 | SM12 | 계장 | IN008 | PRESSURE RELIEF VALVE |  | 완료 | 100% | - | 장동철 책임
464 | SM12 | 계장 | IN009 | BUCKING PIN RELIEF VALVE |  | 완료 | 100% | - | 장동철 책임
465 | SM12 | 계장 | IN010 | ULTRASONIC FLOWMETER | 12 ea | 완료 | 100% | - | 윤희수 책임
466 | SM12 | 계장 | IN011 | FLOWMETER (ROTAMETER) | 53 ea | 완료 | 100% | - | 윤희수 책임
467 | SM12 | 계장 | IN012 | AIR QUALITY MONITORING STATION (AQMS) | 1 unit | 완료 | 100% | - | 윤희수 책임 | 이해석 책임
468 | SM12 | 계장 | IN021 | TRANSMITTERS (PRESS.,TEMP., DIFF. PRESS., DBB) | 545 ea | 완료 | 100% | - | 윤희수 책임
469 | SM12 | 계장 | IN022 | LEVEL GAUGE | 82 ea | 완료 | 100% | - | 윤희수 책임 | 이해석 책임
470 | SM12 | 계장 | IN023 | LEVEL TRANSMITTER (GWR, NCR, ETC) | 138 ea | 완료 | 100% | - | 윤희수 책임 | 이해석 책임
471 | SM12 | 계장 | IN024 | FLOW ELEMENT (ORIFICE, VENTURI TUBE, ETC.) | 162 ea | 완료 | 100% | - | 윤희수 책임
472 | SM12 | 계장 | IN025 | LOCAL GAUGE | 1.252 ea | 완료 | 100% | - | 윤희수 책임
473 | SM12 | 계장 | IN026 | GAS DETECTOR, HORN AND BEACON | 1 lot | 완료 | 100% | - | 윤희수 책임
474 | SM12 | 계장 | IN027 | FLOWMETER (MAGNETIC) | 22 sets | 완료 | 100% | - | 윤희수 책임
475 | SM12 | 계장 | IN031 | INSTRUMENT CABLE | 1 lot | 완료 | 100% | - | 윤희수 책임
476 | SM12 | 계장 | IN032 | INSTRUMENT CABLE TRAY | 1 lot | 완료 | 100% | - | 윤희수 책임
477 | SM12 | 계장 | IN033 | JUNCTION BOX | 1 lot | 완료 | 100% | - | 윤희수 책임
478 | SM12 | 계장 | IN034 | INSTRUMENT CABLE GLAND | 1 lot | 완료 | 100% | - | 윤희수 책임
479 | SM12 | 계장 | IN035 | INSTRUMENT TUBE | 1 lot | 완료 | 100% | - | 윤희수 책임
480 | SM12 | 계장 | IN036 | INSTRUMENT TUBE FITTING & BLOCK VALVE | 1 lot | 완료 | 100% | - | 윤희수 책임
481 | SM12 | 계장 | IN039 | CONTROL VALVE (NON-GENERAL) | 7 EA | 2026-04-30 | 85.71% | Valve 1개 남았으며 공장 설치 용이 아닌 Training 용 | 장동철 책임 | 강태준 책임
482 | SM12 | 계장 | IN041 | SAMPLING CONNECTION | 16 units | 완료 | 100% | - | 윤희수 책임
483 | SM12 | 계장 | IN042 | PRESSURE REGULATOR |  | 완료 | 100% | - | 장동철 책임
484 | SM12 | 계장 | IN043 | CONTROL VALVE GENERAL BUTTERFLY |  | 완료 | 100% | - | 장동철 책임 | 강태준 책임
485 | SM12 | 계장 | IN044 | PRESSURE RELIEF VALVE |  | 완료 | 100% | - | 장동철 책임
486 | SM12 | 계장 | IN045 | CORIOLIS MASS FLOWMETER | 4 ea | 완료 | 100% | - | 윤희수 책임
487 | SM12 | 계장 | IN047 | ON-OFF VALVE FOR ASU |  | 완료 | 100% | - | 장동철 책임
488 | SM12 | 계장 | IN048 | CONTROL VALVE (NON-GENERAL) FOR ASU |  | 완료 | 100% | - | 장동철 책임 | 강태준 책임
489 | SM12 | 기타 | PR001 | CHEMICAL |  | 완료 | 100% | - | 정진우 책임
490 | SM12 | 기타 | PR003 | LABORATORY EQUIPMENT |  | 완료 | 100% | - | 정진우 책임
491 | SM12 | 소방/안전 | SE001 | FIRE AND SAFETY EQUIPMENT |  | 완료 | 100% | - | 장동철 책임
492 | SM12 | 공조 | HV001 | HVAC EQUIPMENT & CONTROL SYSTEM |  | 완료 | - | - | 장동철 책임
493 | SM12 | 철골 | SC001 | STEEL STRUCTURE - I |  | 완료 | 100% |  | 고팔라크리스낸 매니저 | 장동철 책임
494 | SM12 | 철골 | SC002 | STEEL STRUCTURE - II |  | 완료 | 100% | - | 고팔라크리스낸 매니저 | 강태준 책임
495 | SAC2 | 계장 | CI0001 | PROCESS CONTROL SYSTEM | 378 ea | 2026-07-30 | 52.3% |  | 최종현 책임 | 이해석 책임
496 | SAC2 | 계장 | CI0002 | CUSTODY METERING PACKAGE | SKID 1 ea Cabinet 3 ea | 2026-07-30 | 0% | QM 35 감독관 수배하여 상주 검사 진행 중, FAT 일정 : 4/26~27일 | 최종현 책임 | 이해석 책임
497 | SAC2 | 계장 | CI0003 | SULFUR TRUCK LOADING SYSTEM | Cabinet - 4 EA | 2026-05-31 | 100% | IDR 제출 | 최종현 책임 | 이해석 책임
498 | SAC2 | 계장 | CI0004 | STEAM TRAP MONITORING SYSTEM | 1 Lot 7,500 ea | NA | NA | Non inspectable | 최종현 책임 | 이해석 책임
499 | SAC2 | 계장 | CI0005 | CORROSION MONITORING SYSTEM | 1 Lot 26 ea | NA | NA | Non inspectable | 최종현 책임 | 이해석 책임
500 | SAC2 | 계장 | CI0007 | ANALYZER SYSTEM (INCLUDING CEMS) | Shelter 7 ea Cabinet 8 ea 3-side shelter 6 ea Rack 26 ea Sampling 146 ea | 2026-10-30 | 21.9% |  | 최종현 책임 | 이해석 책임
501 | SAC2 | 계장 | CI0011 | ON-OFF VALVE (BALL) | 192 ea | 2026-11-19 | 20.8% |  | 강택기 책임 | 황윤섭 책임
502 | SAC2 | 계장 | CI0012 | ON-OFF VALVE (BUTTERFLY) | 76 ea | 2026-07-13 | 31.6% | Emerson 신규 PO(19 ea) IAP/PIM 예정 | 강택기 책임 | 황윤섭 책임
503 | SAC2 | 계장 | CI0013 | ON-OFF VALVE (GATE) | 32 ea | 2026-07-05 | 20% |  | 강택기 책임 | 황윤섭 책임
504 | SAC2 | 계장 | CI0015 | CONTROL VALVE (GENERAL) | 234 ea | 2026-11-01 | 39.7% | Inspection Level 0 | 강택기 책임 | 황윤섭 책임
505 | SAC2 | 계장 | CI0016 | CONTROL VALVE (NON GENERAL) | 86 ea | 2026-11-01 | 53.5% | BH-Conde(10 ea), Valmet Finland(10 ea) IAP/PIM 예정 | 강택기 책임 | 황윤섭 책임
506 | SAC2 | 계장 | CI0017 | PRESSURE RELIEF VALVE | 184 ea | 2026-07-01 | 85.3% |  | 강택기 책임 | 황윤섭 책임
507 | SAC2 | 계장 | CI0018 | RUPTURE DISC | 8 ea | 2026-05-31 | 100% | VIRB 제출 필요 | 최종현 책임 | 황윤섭 책임
508 | SAC2 | 계장 | CI0021 | ORIFICE | 335 ea | 2026-07-01 | 93.1% |  | 최종현 책임 | 이해석 책임
509 | SAC2 | 계장 | CI0022 | ANNUBAR & VENTURI TUBE | 54 ea | 2026-07-30 | 0% |  | 최종현 책임 | 이해석 책임
510 | SAC2 | 계장 | CI0023 | FLOWMETER (ULTRASONIC) | 4 ea | 2026-05-31 | 100% | VIRB 제출 필요 | 최종현 책임 | 이해석 책임
511 | SAC2 | 계장 | CI0024 | FLOWMETER (MAGNETIC, VORTEX) | 39 ea | 2026-06-30 | 100% | IDR 작성 중 / VIRB 제출 필요 | 최종현 책임 | 이해석 책임
512 | SAC2 | 계장 | CI0025 | FLOWMETER (COLIOLIS) | 27 ea | 2026-06-30 | 100% | IDR 작성 중 / VIRB 제출 필요 | 최종현 책임 | 이해석 책임
513 | SAC2 | 계장 | CI0026 | ROTAMETER | 119 ea | NA | NA | Non inspectable | 최종현 책임 | 술탄 매니저
514 | SAC2 | 계장 | CI0027 | RADAR TYPE LEVEL TRANSMITTER | Transmitter 242 ea Chamber 137 ea | 2026-07-30 | 94.1% | Chamber는 Level 0이나, FAT는 시공사 TPI witness 필요, 검사 진행 중 - 4/10, 4/20 | 최종현 책임 | 이해석 책임
515 | SAC2 | 계장 | CI0028 | LEVEL GAUGE | 69 ea | 2026-05-31 | 100% | IDR 완료 / VIRB 제출 필요 | 최종현 책임 | 이해석 책임
516 | SAC2 | 계장 | CI0029 | TRANSMITTER | 2,146 ea | 2026-08-30 | 41.75% |  | 최종현 책임 | 술탄 매니저
517 | SAC2 | 계장 | CI0030 | LOCAL GAUGE & TEMPERATURE ELEMENT | 463 ea | 2026-08-30 | 66% |  | 최종현 책임 | 술탄 매니저
518 | SAC2 | 계장 | CI0031 | FIRE AND GAS DETECTOR & ALARM DEVICE | 516 ea | 완료 | 100% |  | 술탄 매니저 | 최종현 책임
519 | SAC2 | 계장 | CI0032 | DELUGE VALVE | 5 ea | 2026-05-31 | 0% | Instrument cable (Level 0) : 3.35% | 강택기 책임 | 황윤섭 책임
520 | SAC2 | 계장 | CI0041 | INSTRUMENT CABLE | FO - 328,602 m Instrument - 2,205,160 m | 2026-11-01 | 70% |  | 최종현 책임 | 술탄 매니저
521 | SAC2 | 계장 | CI0042 | INSTRUMENT CABLE TRAY & TRAY FITTING | 180,630 ea | 2026-07-30 | 99.7% | Level 1으로 상향되어, FAT에 검사원 배정하여 진행중 | 최종현 책임 | 술탄 매니저
522 | SAC2 | 계장 | CI0043 | INSTRUMENT JUNCTION BOX | 940 ea | 2026-05-30 | 100% |  | 술탄 매니저 | 최종현 책임
523 | SAC2 | 계장 | CI0044 | INSTRUMENT CABLE GLAND | 17,696 ea | NA | NA | Non inspectable | 최종현 책임 | 술탄 매니저
524 | SAC2 | 계장 | CI0045 | INSTRUMENT TUBE & TUBE FITTING | Fitting - 17,751 ea | 2026-07-30 | 34.2% |  | 최종현 책임 | 술탄 매니저
525 | SAC2 | 계장 | CI0047 | INSTRUMENT CONDUIT & CONDUIT FITTING | Conduit - 173,550 ea Fitting - 100,098 ea | NA | NA | Non inspectable | 최종현 책임 | 술탄 매니저
526 | SAC2 | 계장 | CI0048 | INSTRUMENT MCT | 5,637 ea | 2026-05-30 | 90% |  | 술탄 매니저 | 최종현 책임
527 | SAC2 | 계장 | CI0050 | SUPPORT & CONSUMABLE | 187,465 ea | NA | NA | Non inspectable | 최종현 책임 | 술탄 매니저
528 | SAC2 | 통신 | TEL0001 | TELECOM SYSTEM | 1 Lot 2,598 ea | NA | NA | Non inspectable | 최종현 책임 | 술탄 매니저
529 | SAC2 | 통신 | TEL0002 | TELECOM SYSTEM (NON-IT) | 1 Lot 3,901 ea | NA | NA | Non inspectable | 최종현 책임 | 술탄 매니저
530 | SAC2 | 통신 | TEL0003 | SECURITY SYSTEM | 1 Lot 510 ea | NA | NA | Non inspectable | 최종현 책임 | 술탄 매니저
531 | SAC2 | 배관 | PI0001 | CS SMLS PIPE | 204338.79 m | 2026-08-01 | 99.9% | 3개 PO 분리 발주 (1개 P.O IDR 제출) | 박지애 매니저 | 강택기 책임
532 | SAC2 | 배관 | PI0002 | CS WELDED PIPE | 16271.52 m | 2026-08-01 | 99.3% | 4개 PO 분리 발주, Sub-P.O 3개(2개 P.O & 2개 Sub P.O IDR 제출) | 황윤섭 책임 | 박지애 매니저
533 | SAC2 | 배관 | PI0003 | HIGH ALLOY PIPE | 59471.83 m | 2026-07-01 | 99.9% | 2개 PO 분리 발주 | 박지애 매니저 | 강택기 책임
534 | SAC2 | 배관 | PI0007 | CLAD PIPING | 411.7 m/ea | 2026-08-01 | 91.5% | Sub P.O 4개(Sub P.O 3개 IDR 제출) | 박지애 매니저 | 강택기 책임
535 | SAC2 | 배관 | PI0008 | FBE LINED AND COATED PIPING | 37036 m/ea | 2027-05-01 | 30% | 3개 PO 분리 발주 | 황윤섭 책임 | 박지애 매니저
536 | SAC2 | 배관 | PI0010 | RTR PIPING | 88019 m/ea | 2026-08-01 | 99.6% |  | 황윤섭 책임 | 박지애 매니저
537 | SAC2 | 배관 | PI0021 | FORGED FITTING | 12932 ea | 2026-06-01 | 86.3% |  | 박지애 매니저 | 강택기 책임
538 | SAC2 | 배관 | PI0022 | WROUGHT FITTING | 43820 ea | 2026-05-01 | 99.9% | 3개 PO 분리 발주, Sub-P.O 1개(Sub P.O 1개 IDR 제출) | 황윤섭 책임 | 박지애 매니저
539 | SAC2 | 배관 | PI0023 | FABRICATED SPOOL FITTING | 216 ea | 2026-10-01 | 88% |  | 황윤섭 책임 | 박지애 매니저
540 | SAC2 | 배관 | PI0024 | CROSS FITTING | 557 ea | 2026-04-30 | 100% | IDR 제출 완료, VIRB 진행중 | 박지애 매니저 | 강택기 책임
541 | SAC2 | 배관 | PI0031 | FLANGE | 62025 ea | 2026-10-01 | 99.2% | 4개 PO 분리 발주 | 박지애 매니저 | 강택기 책임
542 | SAC2 | 배관 | PI0032 | BOLT & NUT | 405076 ea | 2026-08-01 | 99.8% |  | 황윤섭 책임 | 박지애 매니저
543 | SAC2 | 배관 | PI0033 | GASKET | 119030 ea | 2026-07-01 | 97.2% |  | 박지애 매니저 | 강택기 책임
544 | SAC2 | 배관 | PI0037 | PIPE SUPPORT | 76908.63 ea | NA | NA | Non inspectable | 황윤섭 책임 | 박지애 매니저
545 | SAC2 | 배관 | PI0038 | SPRING SUPPORT | 170 ea | NA | NA | Non inspectable | 황윤섭 책임 | 박지애 매니저
546 | SAC2 | 배관 | PI0041 | FORGED VALVE | 22116 ea | 2026-11-01 | 80% | Sub P.O 1개 Oxygen Service Valve (Sub Vendor 제작분) 현장 도착한 Valve 226ea 중 49ea에서 Sealing Damage 발생함. Project 요구사항에 따라서 Sealing 되어야 하며, 문제 발생한 49ea 의 Valve는 Vendor로 반출할 예정(Italy). 추 후 재발 방지를 위한 검사 주기 확대관련 협의 진행 예정 | 박지애 매니저 | 강택기 책임
547 | SAC2 | 배관 | PI0042 | CASTING VALVE | 7506 ea | 2026-12-01 | 71% | 4개 PO 분리 발주(1개 P.O IDR 제출) | 황윤섭 책임 | 박지애 매니저
548 | SAC2 | 배관 | PI0043 | BALL VALVE | 2699 ea | 2026-12-01 | 66.5% | 3개 PO 분리 발주, Sub-P.O 1개(2개 P.O IDR 제출) | 황윤섭 책임 | 박지애 매니저
549 | SAC2 | 배관 | PI0044 | BUTTERFLY VALVE | 235 ea | 2026-10-01 | 55.7% | 3개 PO 분리 발주 | 박지애 매니저 | 강택기 책임
550 | SAC2 | 배관 | PI0045 | DUAL PLATE CHECK VALVE | 148 ea | 2026-09-01 | 54% |  | 박지애 매니저 | 강택기 책임
551 | SAC2 | 배관 | PI0046 | NON SLAM CHECK VALVE | 178 ea | 2026-09-01 | 83% |  | 황윤섭 책임 | 박지애 매니저
552 | SAC2 | 배관 | PI0047 | PLUG VALVE | 1250 ea | 2026-12-01 | 55.4% | 3개 PO 분리 발주 Aramco Monitoring 검사원의 Comment 발생 (12건: Painting 7, 자재추적 2, PMI 1, Report 2) 으로. Vendor와 Clarification 중 | 황윤섭 책임 | 박지애 매니저
553 | SAC2 | 배관 | PI0049 | BRONZE VALVE | 2824 ea | 2026-09-01 | 64.38% |  | 박지애 매니저 | 강택기 책임
554 | SAC2 | 배관 | PI0050 | DUCTILE IRON EPOXY LINED VALVE | 891 ea | 2026-10-01 | 86.8% | 3개 PO 분리 발주 | 박지애 매니저 | 강택기 책임
555 | SAC2 | 배관 | PI0051 | POST INDICATE VALVE | 158 ea | 2026-05-30 | 100% | IDR 제출 완료, VIRB 진행중 | 황윤섭 책임 | 박지애 매니저
556 | SAC2 | 배관 | PI0061 | STRAINER | 155 ea | 2026-06-01 | 100% | IDR 제출 예정 | 황윤섭 책임 | 박지애 매니저
557 | SAC2 | 배관 | PI0062 | STEAM TRAP |  | NA | NA | Non inspectable | 황윤섭 책임 | 박지애 매니저
558 | SAC2 | 배관 | PI0063 | HOSE & CONNECTOR |  | NA | NA | Non inspectable | 황윤섭 책임 | 박지애 매니저
559 | SAC2 | 배관 | PI0065 | INJECTION QUILL |  | NA | NA | Non inspectable | 황윤섭 책임 | 박지애 매니저
560 | SAC2 | 배관 | PI0066 | STEAM TRACING PACKAGE | 8763 ea | 2026-12-01 | 7.69% |  | 황윤섭 책임 | 박지애 매니저
561 | SAC2 | 배관 | PI0069 | MECHANICAL INTERLOCK |  | NA | NA | Non inspectable | 박지애 매니저 | 강택기 책임
562 | SAC2 | 배관 | PI0070 | CARBON CANISTER |  | NA | NA | Non inspectable | 박지애 매니저 | 강택기 책임
563 | SAC2 | 배관 | PI0081 | PENSTOCK VALVE |  | NA | NA | Non inspectable | 박지애 매니저 | 강택기 책임
564 | ALOM | 장치 | ME-001 | HRSG (PRESSURE PART) | Embedded Material 1 set Casing 1 set Expansion Joint & Bellow 1 set Module 1 set HP/LP/IP Drum 3 set Deaerator 1set External Piping 1lot Internal Piping 1lot Pipe Hanger & Support 1 lot Safety Valve 1 set Control Valve, MOV Silencer 1 lot Electrical & I&C 2 set Stack Damper 1EA Steel Structure 1 lot Inlet/Outlet Duct 1 set Stack 1 set | 2026-06-30 | 95% | HRSG 잔여 공급 분 (Sub-Component) 남아있음 | 정진우 책임 | N/A (현시점 지정 불필요)
565 | ALOM | 장치 | ME-002 | AIR COOLED CONDENSER |  | 2027-02-20 | 17% |  | 나광조 책임 | 석우경 매니저
566 | ALOM | 장치 | ME-003 | STEAM BYPASS SYSTEM |  | 2027-12-01 | 0% |  | 석우경 매니저 | N/A (현시점 지정 불필요)
567 | ALOM | 장치 | ME-004 | NATURAL GAS SUPPLY SYSTEM |  | 완료 | 100% |  | 석우경 매니저 | N/A (현시점 지정 불필요)
568 | ALOM | 장치 | ME-005 | ELECTRIC HEATER |  | 완료 | 100% | - | 석우경 매니저
569 | ALOM | 장치 | ME-006 | FIN FAN AIR COOLER |  | 완료 | 100% | - | 석우경 매니저
570 | ALOM | 회전 | ME-007 | BOILER FEEDWATER PUMP |  | 완료 | 100% | - | 석우경 매니저
571 | ALOM | 회전 | ME-008 | CONDENSATE EXTRACTION PUMP |  | 완료 | 100% | - | 석우경 매니저
572 | ALOM | 회전 | ME-009 | GENERAL SERVICE PUMP |  | 완료 | 100% | - | 석우경 매니저
573 | ALOM | 회전 | ME-010 | SUMP PUMP |  | 2027-12-01 | 100% | FIDB 제출 필요 | 석우경 매니저 | N/A (현시점 지정 불필요)
574 | ALOM | 장치 | ME-011 | SHOP FABRICATED TANK |  | 완료 | 100% | - | 석우경 매니저
575 | ALOM | 회전 | ME-012 | AIR COMPRESSOR |  | 완료 | 100% | - | 석우경 매니저
576 | ALOM | 회전 | ME-013 | CRANE & HOIST |  | 2027-12-01 | 100% | FIDB 제출 필요 | 석우경 매니저
577 | ALOM | 장치 | ME-014 | EXHAUST GAS BYPASS SYSTEM |  | 2026-10-01 | 5% |  | 나광조 책임
578 | ALOM | 회전 | ME-015 | CHILLER PACKAGE |  | 완료 | 100% |  | 석우경 매니저 | N/A (현시점 지정 불필요)
579 | ALOM | 장치 | ME-017 | AUXILIARY BOILER |  | 완료 | 100% | - | 석우경 매니저
580 | ALOM | 장치 | EN-001 | WATER & WASTEWATER TREATMENT SYSTEM |  | 2027-12-01 | 100% | FIDB 제출 필요 | 석우경 매니저 | N/A (현시점 지정 불필요)
581 | ALOM | 회전 | EN-002 | CHEMICAL DOSING SYSTEM |  | 2027-12-01 | 100% | FIDB 제출 필요 | 석우경 매니저
582 | ALOM | 기타 | EN-003 | LABORATORY |  | 2027-12-01 | 100% | FIDB 제출 필요 | 석우경 매니저
583 | ALOM | 배관 | PP-001 | PIPE(AS SMLS) | 6959.63 m | 2027-12-01 | 100% | FIDB 제출 필요 | 석우경 매니저
584 | ALOM | 배관 | PP-002 | PIPE(AS WELDED) | 28 pcs | 2027-12-01 | 100% | FIDB 제출 필요 | 석우경 매니저
585 | ALOM | 배관 | PP-003 | PIPE(SS SMLS) | 402 pcs | 2027-12-01 | 100% | FIDB 제출 필요 | 석우경 매니저
586 | ALOM | 배관 | PP-004 | PIPE(SS WELDED) | 7134.5 m | 2027-12-01 | 100% | FIDB 제출 필요 | 석우경 매니저
587 | ALOM | 배관 | PP-005 | PIPE(CS SMLS) | 38301.5 m | 2027-12-01 | 100% | FIDB 제출 필요 | 석우경 매니저
588 | ALOM | 배관 | PP-006 | PIPE(CS WELDED) | 1644.5 m | 2027-12-01 | 100% | FIDB 제출 필요 | 석우경 매니저
589 | ALOM | 배관 | PP-007 | DOUBLE WALLED PIPING | 60 pcs | 2026-06-01 | 0% | FIDB 제출 필요 | 석우경 매니저
590 | ALOM | 배관 | PP-008 | FORGED FITTING | 20624 ea | 2027-12-01 | 100% | FIDB 제출 필요 | 석우경 매니저
591 | ALOM | 배관 | PP-009 | WROUGHT FITTING | 8320 ea | 2027-12-01 | 100% | FIDB 제출 필요 | 석우경 매니저
592 | ALOM | 배관 | PP-010 | FLANGE | 4481 ea | 2027-12-01 | 100% | FIDB 제출 필요 | 석우경 매니저
593 | ALOM | 배관 | PP-011 | GASKET | 6786 ea | 2027-12-01 | 100% | FIDB 제출 필요 | 석우경 매니저 | N/A (현시점 지정 불필요)
594 | ALOM | 배관 | PP-012 | BOLT & NUT | 35416 ea | 2027-12-01 | 100% | FIDB 제출 필요 | 석우경 매니저 | N/A (현시점 지정 불필요)
595 | ALOM | 배관 | PP-013 | FORGED VALVE | 3781 ea | 2027-12-01 | 100% | FIDB 제출 필요 | 석우경 매니저 | N/A (현시점 지정 불필요)
596 | ALOM | 배관 | PP-014 | PIPING MATERIAL FOR STORAGE TANK(OUMACHE-I) |  | 2027-12-01 | 100% | FIDB 제출 필요 | 석우경 매니저
597 | ALOM | 배관 | PP-014-1 | CASTING VALVE | 6 ea | 2027-12-01 | 100% | FIDB 제출 필요 | 석우경 매니저
598 | ALOM | 배관 | PP-015 | BUTTERFLY VALVE | 200 ea | 2027-12-01 | 100% | FIDB 제출 필요 | 석우경 매니저
599 | ALOM | 배관 | PP-016 | BALL VALVE | 122 ea | 2027-12-01 | 100% | FIDB 제출 필요 | 석우경 매니저
600 | ALOM | 배관 | PP-017 | PSV | 43 ea | 2027-12-01 | 100% | FIDB 제출 필요 | 석우경 매니저
601 | ALOM | 배관 | PP-018 | EXPANSION JOINT & FLEXIBLE HOSE | 32 ea | 2027-12-01 | 92% |  | 석우경 매니저 | N/A (현시점 지정 불필요)
602 | ALOM | 배관 | PP-019 | TRAP | 51 ea | 2027-12-01 | 100% | FIDB 제출 필요 | 석우경 매니저
603 | ALOM | 배관 | PP-020 | STRAINER | 76 ea | 2027-12-01 | 100% | FIDB 제출 필요 | 석우경 매니저
604 | ALOM | 배관 | PP-021 | HANGER & SUPPORT | 13414 ea | 2027-12-01 | 100% | FIDB 제출 필요 | 석우경 매니저 | N/A (현시점 지정 불필요)
605 | ALOM | 배관 | PP-023 | SHOP FABRICATED PIPING | 32603 pcs (fitting,flange) / 49379 m(piping) | 2027-12-01 | 100% | FIDB 제출 필요 | 석우경 매니저 | N/A (현시점 지정 불필요)
606 | ALOM | 배관 | PP-024 | INSULATION |  | 2027-12-01 | 0% |  | 석우경 매니저 | N/A (현시점 지정 불필요)
607 | ALOM | 배관 | PP-026 | COATING | 628 pcs | 2027-12-01 | 87% | Coated Pipe | 석우경 매니저 | N/A (현시점 지정 불필요)
608 | ALOM | 배관 | PP-A03 | CLADDING |  | 2027-12-01 | 0% | Cladding Pipe | 석우경 매니저 | N/A (현시점 지정 불필요)
609 | ALOM | 전기 | EL-003 | POWER TRANSFORMERS |  | 2027-12-01 | 100% | FIDB 제출 필요 | 윤희수 책임
610 | ALOM | 전기 | EL-004 | GCB |  | 완료 | 100% | - | 석우경 매니저
611 | ALOM | 전기 | EL-005 | IPB |  | 2027-12-01 | 100% | FIDB 제출 필요 | 윤희수 책임
612 | ALOM | 전기 | EL-006 | MV SWGR |  | 2027-12-01 | 100% | FIDB 제출 필요 | 윤희수 책임
613 | ALOM | 전기 | EL-007 | LV SWGR AND MCC | 478 ea | 2026-05-01 | 100% | FIDB 제출 필요 | 윤희수 책임 | N/A (현시점 지정 불필요)
614 | ALOM | 전기 | EL-008 | DC AND UPS SYSTEM | 40 sets | 2027-12-01 | 0% |  | 윤희수 책임 | N/A (현시점 지정 불필요)
615 | ALOM | 전기 | EL-009 | PROTECTION AND METERING PANEL |  | 완료 | 100% | - | 석우경 매니저
616 | ALOM | 전기 | EL-010 | FIRE ALARM SYSTEM | 8 sets | 2027-12-01 | 0% |  | 윤희수 책임 | N/A (현시점 지정 불필요)
617 | ALOM | 전기 | EL-011 | CATHODIC PROTECTION SYSTEM |  | 완료 | 100% | - | 석우경 매니저
618 | ALOM | 전기 | ALOM-BM-EL-001 | BM - POWER AND CONTROL CABLES | 7,7500 m 518,000 m 558,600 m 231,600 m 65,500 m | 2027-12-01 | 20% |  | 윤희수 책임 | N/A (현시점 지정 불필요)
619 | ALOM | 전기 | ALOM-BM-EL-002 | BM - CABLE TRAYS |  | 완료 | 100% |  | 석우경 매니저 | N/A (현시점 지정 불필요)
620 | ALOM | 전기 | ALOM-BM-EL-003 | BM - CONDUIT AND ACCESSORIES |  | 완료 | 100% |  | 석우경 매니저 | N/A (현시점 지정 불필요)
621 | ALOM | 전기 | ALOM-BM-EL-004 | BM - GROUNDING AND LIGHTNING PROTECTION SYSTEM |  | 완료 | 100% | - | 석우경 매니저
622 | ALOM | 계장 | CI-001 | DISTRIBUTED CONTROL SYSTEM(DCS) |  | 2027-12-01 | 100% | FIDB 제출 필요 | 윤희수 책임
623 | ALOM | 계장 | CI-002 | CONTINUOUS EMISSION MONITORING SYSTEM(CEMS) |  | 완료 | 100% | - | 석우경 매니저
624 | ALOM | 계장 | CI-003 | STEAM & WATER SAMPLING & ANALYSIS SYSTEM(SWAS) |  | 2027-12-01 | 100% | FIDB 제출 필요 | 윤희수 책임
625 | ALOM | 계장 | CI-004 | VIBRATION MONITORING SYSTEM(VMS) |  | 완료 | 100% | - | 석우경 매니저
626 | ALOM | 계장 | CI-005 | CONTROL VALVE |  | 2027-12-01 | 100% | FIDB 제출 필요 | 석우경 매니저
627 | ALOM | 계장 | CI-006 | FLOW ELEMENT AND SIGHT GLASS |  | 완료 | 100% | - | 석우경 매니저
628 | ALOM | 계장 | CI-007 | LEVEL SWITCH |  | 2027-12-01 | 100% | FIDB 제출 필요 | 윤희수 책임
629 | ALOM | 계장 | CI-008 | TRANSMITTER |  | 완료 | 100% | - | 윤희수 책임
630 | ALOM | 계장 | CI-009 | LOCAL INDICATOR |  | 완료 | 100% | - | 윤희수 책임
631 | ALOM | 계장 | CI-001 | BM-INSTRUMENT BULK MATERIALS |  | 2027-12-01 | 100% | FIDB 제출 필요 | 석우경 매니저 | N/A (현시점 지정 불필요)
632 | ALOM | 계장 | CI-011 | MISCELLANEOUS EQUIPMENT FOR C&I |  | 2027-12-01 | 0% | 준공 6개월 전 시점에서 발주 예정 | 석우경 매니저 | N/A (현시점 지정 불필요)
633 | ALOM | 계장 | CI-012 | MOV (GATE & GLOBE) |  | 2027-12-01 | 100% | FIDB 제출 필요 | 석우경 매니저
634 | ALOM | 계장 | CI-013 | INSTRUMENTATION BULK |  | 2027-12-01 | 95% |  | 윤희수 책임 | N/A (현시점 지정 불필요)
635 | ALOM | 공조 | HV-001 | HVAC EQUIPMENT |  | 완료 | 100% |  | 석우경 매니저 | N/A (현시점 지정 불필요)
636 | ALOM | 공조 | HV-002 | GT VENTILATION DUCT |  | 완료 | 100% |  | 석우경 매니저 | N/A (현시점 지정 불필요)
637 | ALOM | 철골 | AR-001 | STRUCTURAL STEEL |  | 완료 | 100% | - | 고팔라크리스낸 매니저
638 | VEQU | 회전 | QT1-RFQ-M-001 | STG AND AUXILIARIES |  | 완료 | 100% | 26년 3월 FIDB 접수 완료 (종결) | 강태준 책임 | 장동철 책임
639 | VEQU | 장치 | QT1-RFQ-M-002 | BOILER (PC, USC) AND AUXILIAIRES |  | 완료 | 100% |  | 고팔라크리스낸 매니저 | 서민 책임
640 | VEQU | 장치 | QT1-RFQ-M-003 | ASH HANDLING SYSTEM |  | 완료 | 100% |  | 나광조 책임 | 서민 책임
641 | VEQU | 장치 | QT1-RFQ-M-004 | COAL HANDLING SYSTEM |  | 완료 | 100% |  | 강택기 책임 | 나광조 책임
642 | VEQU | 장치 | QT1-RFQ-M-004 | STOP GATE | 3 Lot | 완료 | 100% |  | 고팔라크리스낸 매니저 | 서민 책임
643 | VEQU | 장치 | QT1-RFQ-M-005 | ELECTROSTATIC PRECIPITATOR |  | 완료 | 100% |  | 고팔라크리스낸 매니저 | 서민 책임
644 | VEQU | 회전 | QT1-RFQ-M-006 | ID FAN |  | 완료 | 100% |  | 강태준 책임 | 장동철 책임
645 | VEQU | 장치 | QT1-RFQ-M-007 | INTAKE FACILITY |  | 2026-05-01 | 100% | FIDB 제출 필요 | 강태준 책임 | 장동철 책임
646 | VEQU | 회전 | QT1-RFQ-M-008 | CWPS |  | 완료 | 100% | - | 강태준 책임
647 | VEQU | 장치 | QT1-RFQ-M-009 | CONDENSER WITH VACUUM SYSTEM |  | 완료 | 100% | - | 나광조 책임
648 | VEQU | 장치 | QT1-RFQ-M-010 | CTCS AND DEBRIS FILTER | 2 Unit (378 MT) | 완료 | 100% |  | 고팔라크리스낸 매니저 | 윤희수 책임
649 | VEQU | 회전 | QT1-RFQ-M-011 | CONDENSATE EXTRACTION PUMP |  | 완료 | 100% | - | 강태준 책임
650 | VEQU | 장치 | QT1-RFQ-M-012 | FW HEATER |  | 완료 | 100% |  | 나광조 책임 | 서민 책임
651 | VEQU | 장치 | QT1-RFQ-M-013 | DEAERATOR AND FW STORAGE TANK |  | 완료 | 100% | - | 나광조 책임
652 | VEQU | 회전 | QT1-RFQ-M-014 | BOILER FEEDWATER PUMPS |  | 완료 | 100% | - | 강태준 책임
653 | VEQU | 장치 | QT1-RFQ-M-015 | CCW COOLER |  | 완료 | 100% | - | 나광조 책임
654 | VEQU | 회전 | QT1-RFQ-M-016 | COMPRESSED AIR SYSTEM |  | 2026-05-01 | 98% |  | 강태준 책임 | 장동철 책임
655 | VEQU | 회전 | QT1-RFQ-M-017 | CRANE & HOIST |  | 완료 | 100% |  | 강태준 책임 | 장동철 책임
656 | VEQU | 장치 | QT1-RFQ-M-018 | FIELD ERECTED TANK |  | 완료 | 100% |  | 고팔라크리스낸 매니저 | 윤희수 책임
657 | VEQU | 장치 | QT1-RFQ-M-019 | SHOP FABRICATED TANK |  | 완료 | 100% |  | 고팔라크리스낸 매니저 | 윤희수 책임
658 | VEQU | 회전 | QT1-RFQ-M-020 | GENERAL SERVICE PUMP (HORIZONTAL) |  | 완료 | 100% |  | 강태준 책임 | 장동철 책임
659 | VEQU | 회전 | QT1-RFQ-M-021 | GENERAL SERVICE PUMP (VERTICAL) |  | 완료 | 100% |  | 강태준 책임 | 장동철 책임
660 | VEQU | 장치 | QT1-RFQ-M-022 | AUX. BOILER PACKAGE |  | 완료 | 100% |  | 나광조 책임 | 서민 책임
661 | VEQU | 장치 | QT1-RFQ-M-023 | H2 PLANT |  | 완료 | 100% |  | 강태준 책임 | 장동철 책임
662 | VEQU | 장치 | QT1-RFQ-M-024 | SERVICE GAS (N2, CO2) SYSTEM |  | 완료 | 100% |  | 고팔라크리스낸 매니저 | 서민 책임
663 | VEQU | 장치 | QT1-RFQ-M-026 | STACKER AND RECLAIMER |  | 2026-05-30 | 99.7% |  | 강택기 책임 | 나광조 책임
664 | VEQU | 장치 | QT1-RFQ-M-029 | VACUUM CLEANING SYSTEM |  | 2026-12-01 | 0% |  | 강태준 책임 | 장동철 책임
665 | VEQU | 철골 | QT1-RFQ-M-032 | STEEL STRUCTURE & COAL BUNKER FOR BOILER | 19726 MT | 2026-05-30 | 99% | FIDB 불필요 | 고팔라크리스낸 매니저 | 윤희수 책임
666 | VEQU | 장치 | QT1-RFQ-W-001 | WATER&WASTEWATER TREATMENT SYSTEM |  | 완료 | 99.98% |  | 나광조 책임 | 서민 책임
667 | VEQU | 장치 | QT1-RFQ-W-002 | CONDENSATE POLISHING SYSTEM | 1 Unit | 2026-05-30 | 99.8% | FIDB 불필요 | 고팔라크리스낸 매니저 | 서민 책임
668 | VEQU | 장치 | QT1-RFQ-W-003 | GAS CHLORINATION SYSTEM |  | 2026-05-30 | 97.5% |  | 강택기 책임 | 윤희수 책임
669 | VEQU | 회전 | QT1-RFQ-W-004 | CHEMICAL DOSING SYSTEM |  | 완료 | 100% |  | 나광조 책임 | 서민 책임
670 | VEQU | 장치 | QT1-RFQ-MS-003 | NH3 SUPPLY SYSTEM |  | 완료 | 100% |  | 나광조 책임 | 서민 책임
671 | VEQU | 장치 | QT1-RFQ-MS-002 | SEA WATER FGD SYSTEM |  | 2026-05-01 | 99.8% |  | 강태준 책임 | 장동철 책임
672 | VEQU | 장치 | QT1-RFQ-W-007 | LABORATORY SYSTEM |  | 완료 | 100% |  | 석우경 매니저 | 나광조 책임
673 | VEQU | 배관 | QT1-RFQ-P-001 | A/S PIPES (SEAMLESS) |  | 완료 | 100% | (VO 가능성 高) | 석우경 매니저 | 나광조 책임
674 | VEQU | 배관 | QT1-RFQ-P-002 | A/S PIPES (SEAM) |  | 완료 | 100% | (VO 가능성 高) | 석우경 매니저 | 나광조 책임
675 | VEQU | 배관 | QT1-RFQ-P-003 | C/S PIPES (SEAMLESS) |  | 완료 | 100% |  | 석우경 매니저 | 나광조 책임
676 | VEQU | 배관 | QT1-RFQ-P-004 | C/S PIPES (SEAM) |  | 완료 | 100% |  | 석우경 매니저 | 나광조 책임
677 | VEQU | 배관 | QT1-RFQ-P-005 | S/S PIPES (SEAMLESS) |  | 완료 | 100% |  | 석우경 매니저 | 나광조 책임
678 | VEQU | 배관 | QT1-RFQ-P-006 | S/S PIPES (SEAM) |  | 완료 | 100% | - | 석우경 매니저
679 | VEQU | 배관 | QT1-RFQ-P-008 | WROUGHT FITTING |  | 완료 | 100% | (VO 가능성 高) | 석우경 매니저 | 나광조 책임
680 | VEQU | 배관 | QT1-RFQ-P-009 | FORGED FITTING |  | 완료 | 100% | (VO 가능성 高) | 석우경 매니저 | 나광조 책임
681 | VEQU | 배관 | QT1-RFQ-P-010 | FLANGE |  | 완료 | 100% |  | 고팔라크리스낸 매니저 | 나광조 책임
682 | VEQU | 배관 | QT1-RFQ-P-011 | GASKET |  | 완료 | 100% |  | 석우경 매니저 | 나광조 책임
683 | VEQU | 배관 | QT1-RFQ-P-012 | BOLT/NUT |  | 완료 | 100% |  | 석우경 매니저 | 나광조 책임
684 | VEQU | 배관 | QT1-RFQ-P-013 | CASTING VALVE (MANUAL) |  | 완료 | 100% | 2개 PO [MANUAL, 4500#: 100.0% / MANUAL, upto 2500#: 100.0%] | 석우경 매니저 | 나광조 책임
685 | VEQU | 배관 | QT1-RFQ-P-014 | FORGED VALVE (MANUAL) |  | 완료 | 100% |  | 석우경 매니저 | 나광조 책임
686 | VEQU | 배관 | QT1-RFQ-P-015 | BUTTERFLY VALVE (MANUAL) |  | 완료 | 100% |  | 석우경 매니저 | 나광조 책임
687 | VEQU | 배관 | QT1-RFQ-P-016 | BALL VALVE (MANUAL) |  | 완료 | 100% |  | 석우경 매니저 | 나광조 책임
688 | VEQU | 배관 | QT1-RFQ-P-017 | STRAINER |  | 완료 | 100% |  | 고팔라크리스낸 매니저 | 윤희수 책임
689 | VEQU | 배관 | QT1-RFQ-P-018 | STEAM/AIR TRAP |  | 완료 | 100% |  | 고팔라크리스낸 매니저 | 윤희수 책임
690 | VEQU | 배관 | QT1-RFQ-P-019 | FLEXIBLE & EXPANSION JOINT |  | 완료 | 100% |  | 고팔라크리스낸 매니저 | 윤희수 책임
691 | VEQU | 배관 | QT1-RFQ-P-020 | HANGER & SUPPORT |  | 완료 | 100% |  | 고팔라크리스낸 매니저 | 윤희수 책임
692 | VEQU | 배관 | QT1-RFQ-P-021 | HDPE |  | 완료 | 100% | - | 석우경 매니저
693 | VEQU | 배관 | QT1-RFQ-P-022 | CPVC |  | 완료 | 100% | - | 석우경 매니저
694 | VEQU | 배관 | QT1-RFQ-P-023 | COATED/LINED PIPE |  | 완료 | 100% | - | 석우경 매니저
695 | VEQU | 배관 | QT1-RFQ-P-030 | GRP PIPING (FOR SW FGD) |  | 완료 | 100% |  | 석우경 매니저 | 나광조 책임
696 | VEQU | 계장 | QT1-RFQ-I-001 | DISTRIBUTED CONTROL SYSTEM (DCS) | 1 lot | 완료 | 100% |  | 윤희수 책임 | 이해석 책임
697 | VEQU | 계장 | QT1-RFQ-I-002 | VIBRATION MONITORING SYSTEM (VMS) | 2 sets | 완료 | 100% |  | 윤희수 책임 | 이해석 책임
698 | VEQU | 계장 | QT1-RFQ-I-003 | CONTINUOUS EMISSION MONITORING SYSTEM (CEMS) | 2 sets | 완료 | 100% |  | 윤희수 책임
699 | VEQU | 계장 | QT1-RFQ-I-004 | STEAM/WATER SAMPLING AND ANALYZING SYSTEM (SWAS) | 2 sets | 완료 | 100% |  | 윤희수 책임
700 | VEQU | 계장 | QT1-RFQ-I-005 | CONTROL VALVE |  | 완료 | 100% |  | 석우경 매니저 | 나광조 책임
701 | VEQU | 계장 | QT1-RFQ-I-006 | FIELD TRANSMITTER | 751 ea | 완료 | 100% |  | 윤희수 책임
702 | VEQU | 계장 | QT1-RFQ-I-007 | LOCAL INDICATOR | 556 ea | 완료 | 100% |  | 윤희수 책임
703 | VEQU | 계장 | QT1-RFQ-I-008 | LEVEL INSTRUMENT | 108 ea | 완료 | 100% |  | 윤희수 책임 | 이해석 책임
704 | VEQU | 계장 | QT1-RFQ-I-009 | FLOW ELEMENT AND SIGHT GLASS | 215 ea | 완료 | 100% |  | 윤희수 책임 | 이해석 책임
705 | VEQU | 계장 | QT1-RFQ-I-010 | MOTORIZED OPERATING VALVE (GATE & GLOBE TYPE) |  | 완료 | 100% | - | 석우경 매니저
706 | VEQU | 계장 | QT1-RFQ-I-011 | MOTORIZED OPERATING VALVE (BUTTERFLY TYPE) |  | 완료 | 100% | - | 석우경 매니저
707 | VEQU | 계장 | QT1-RFQ-I-015 | INSTRUMENT INSTALLATION MATERIALS | 1 lot | 완료 | 100% |  | 윤희수 책임 | 이해석 책임
708 | VEQU | 계장 | QT1-RFQ-I-016 | I&C CABLE |  | 완료 | 100% |  | 술탄 매니저 | 윤희수 책임
709 | VEQU | 계장 | QT1-RFQ-I-017 | I&C CABLE CONDUIT AND ACCESSORIES |  | 완료 | 100% |  | 술탄 매니저 | 윤희수 책임
710 | VEQU | 계장 | QT1-RFQ-I-018 | I&C CABLE ACCESSORIES |  | 완료 | 100% | - | 술탄 매니저 | 윤희수 책임
711 | VEQU | 계장 | QT1-RFQ-I-012 | STEAM BYPASS SYSTEM |  | 완료 | 100% | - | 석우경 매니저
712 | VEQU | 계장 | QT1-RFQ-I-013 | SAFETY VALVE |  | 완료 | 100% |  | 석우경 매니저 | 나광조 책임
713 | VEQU | 계장 | QT1-RFQ-I-019 | COMBINED NON RETURN CHECK VALVE (COMBINED NRV) |  | 완료 | 100% | - | 석우경 매니저
714 | VEQU | 전기 | QT1-RFQ-E-001 | 500KV EHV OVERHEAD LINE | 2 sets | 완료 | 100% |  | 윤희수 책임 | 이해석 책임
715 | VEQU | 전기 | QT1-RFQ-E-002 | GENERATOR STEP-UP TRANSFORMER | 2 units | 완료 | 100% |  | 윤희수 책임 | 이해석 책임
716 | VEQU | 전기 | QT1-RFQ-E-003 | UNIT AUXILIARY TRANSFORMER | 4 units | 완료 | 100% |  | 윤희수 책임 | 이해석 책임
717 | VEQU | 전기 | QT1-RFQ-E-004 | GENERATOR CIRCUIT BREAKER | 2 units | 완료 | 100% |  | 윤희수 책임 | 이해석 책임
718 | VEQU | 전기 | QT1-RFQ-E-005 | ISOLATED PHASE BUSDUCT | 1,261m | 완료 | 100% |  | 윤희수 책임 | 이해석 책임
719 | VEQU | 전기 | QT1-RFQ-E-006 | EMERGENCY DIESEL GENERATOR | 2 units | 완료 | 100% |  | 윤희수 책임 | 이해석 책임
720 | VEQU | 전기 | QT1-RFQ-E-007 | PROTECTION AND METERING SYSTEM | 1 lot | 완료 | 100% |  | 윤희수 책임
721 | VEQU | 전기 | QT1-RFQ-E-008 | MV SWITCHGEAR | 136 ea | 완료 | 100% |  | 윤희수 책임 | 이해석 책임
722 | VEQU | 전기 | QT1-RFQ-E-009 | LV SWITCHGEAR AND MCC | 429 ea | 완료 | 100% |  | 윤희수 책임 | 이해석 책임
723 | VEQU | 전기 | QT1-RFQ-E-010 | DC AND UPS SYTEM | 5 sets | 완료 | 100% |  | 윤희수 책임
724 | VEQU | 전기 | QT1-RFQ-E-011 | CATHODIC PROTECTION SYSTEM | 1 lot | 완료 | 100% |  | 윤희수 책임 | 이해석 책임
725 | VEQU | 전기 | QT1-RFQ-E-013 | COMMUNICATION SYSTEM 1 TELEPHONE & LAN SYSTEM 2 PUBLIC ADDRESS SYSTEM 3 RADIO SYSTEM 4 CCTV SYSTEM 5 SLAVE CLOCK SYSTEM 6 INSTRUSION ALARM SYSTEM 7 UNINTERRUPTED POWER SUPPLY SYSTEM | 7 sets | 완료 | 100% | FIDB 불 필요 | 윤희수 책임 | 이해석 책임
726 | VEQU | 전기 | QT1-RFQ-E-014 | CABLE | 1,705,719 m | 2026-05-30 | 95% |  | 술탄 매니저 | 윤희수 책임
727 | VEQU | 전기 | QT1-RFQ-E-015 | CABLE TRAY | 47648 m | 2026-05-30 | 97% |  | 술탄 매니저 | 윤희수 책임
728 | VEQU | 전기 | QT1-RFQ-E-016 | CONDUIT AND CABLE ACCESSORIES | 60,674 m | 2026-05-30 | 97% |  | 술탄 매니저 | 윤희수 책임
729 | VEQU | 전기 | QT1-RFQ-E-017 | GROUNDING AND LIGHTNING PROTECTION | 84,496 m/ea | 완료 | 100% | FIDB 불필요 | 윤희수 책임 | 이해석 책임
730 | VEQU | 전기 | QT1-RFQ-E-018 | LIGHTING FIXTURE AND SAMLL POWER | 11,413 EA | 완료 | 100% |  | 술탄 매니저 | 윤희수 책임
731 | VEQU | 전기 | QT1-RFQ-E-019 | CABLE ACCESSORIES | 2,592,892 ea | 완료 | 100% | FIDB 불필요 | 윤희수 책임 | 이해석 책임
732 | VEQU | 전기 | QT1-RFQ-E-020 | GROUNDING CABLE | 1 lot | 완료 | 100% |  | 술탄 매니저 | 윤희수 책임
733 | IBRU | 철골 | RN2120-001 | ANCHOR BOLT |  | 완료 | 100% | - | 고팔라크리스낸 매니저
734 | IBRU | 철골 | RN2130-001 | SHOP FABRICATED STRUCTURAL STEEL |  | 완료 | 100% | - | 고팔라크리스낸 매니저
735 | IBRU | 공조 | RN2140-001 | HVAC EQUIPMENT |  | 완료 | 100% | - | 이해석 책임
736 | IBRU | 공조 | RN2140-002 | HVAC CONTROL |  | 완료 | 100% | - | 이해석 책임
737 | IBRU | 장치 | RN2151-304 | DRUMS (CS & SS LESS THAN 30TON) |  | 완료 | 100% | - | 정진우 책임
738 | IBRU | 장치 | RN2151-501 | FILTER & COALESCER |  | 완료 | 100% | - | 정진우 책임
739 | IBRU | 장치 | RN2151-701 | SULPHUR LOCKS |  | 완료 | 100% | - | 정진우 책임
740 | IBRU | 장치 | RN2153-101 | AIR COOLED HEAT EXCHANGER (MODULE) |  | 완료 | 100% | - | 정진우 책임
741 | IBRU | 장치 | RN2153-201 | SULPHUR CONDENSERS |  | 완료 | 100% | - | 정진우 책임
742 | IBRU | 장치 | RN2153-202 | SHELL AND TUBE HEAT EXCHANGERS (D-TYPE) |  | 완료 | 100% | - | 정진우 책임
743 | IBRU | 장치 | RN2153-206 | SHELL AND TUBE HEAT EXCHANGERS (CS, SS) (MODULE+SITE) |  | 완료 | 100% | - | 정진우 책임
744 | IBRU | 장치 | RN216G-202 | STATIC MIXER |  | 완료 | 100% | - | 정진우 책임
745 | IBRU | 장치 | RN216G-203 | DESUPERHEATER |  | 완료 | 100% | - | 정진우 책임
746 | IBRU | 장치 | RN216G-205 | EJECTOR |  | 완료 | 100% | - | 정진우 책임
747 | IBRU | 장치 | RN2151-306 | BULLET TANK |  | 완료 | 100% | - | 정진우 책임
748 | IBRU | 장치 | RN2153-204 | SHELL AND TUBE HEAT EXCHANGERS (ALLOY, CLAD, DUPLEX) |  | 완료 | 100% | - | 정진우 책임
749 | IBRU | 장치 | RN2153-205 | SHELL AND TUBE HEAT EXCHANGERS (HIC CS) |  | 완료 | 100% | - | 정진우 책임
750 | IBRU | 장치 | RN2153-207 | SHELL AND TUBE HEAT EXCHANGERS (CS, SS) |  | 완료 | 100% | - | 정진우 책임
751 | IBRU | 장치 | RN2152-501 | PLATFORM AND LADDER |  | 완료 | 100% | - | 고팔라크리스낸 매니저
752 | IBRU | 장치 | RN2154-101 | ATMOSPHERIC STORAGE TANKS-I (HDEC AREA) |  | 완료 | 100% |  | 고팔라크리스낸 매니저
753 | IBRU | 장치 | RN2154-102 | ATMOSPHERIC STORAGE TANKS-II (JGC AREA) |  | 완료 | 100% |  | 고팔라크리스낸 매니저
754 | IBRU | 장치 | RN2158-500 | MIXER |  | 완료 | 100% | - | 정진우 책임
755 | IBRU | 회전 | RN2155-222 | CAUSTIC SODA DISSOLUTION PACKAGE |  | 완료 | 100% | - | 장동철 책임
756 | IBRU | 회전 | RN2155-321 | SULPHUR SOLIDIFICATION PACKAGE |  | 완료 | 100% | - | 고팔라크리스낸 매니저
757 | IBRU | 회전 | RN2155-521 | SOLID SULPHUR HANDLING AND LOADING FACILITY |  | 완료 | 100% | - | 장동철 책임
758 | IBRU | 회전 | RN2155-621 | WEIGHING BRIDGE |  | 완료 | 100% | - | 장동철 책임
759 | IBRU | 회전 | RN2155-622 | SOLID SULPHUR BAGGING AND PALLETIZING PACKAGE |  | 완료 | 100% | - | 장동철 책임
760 | IBRU | 회전 | RN2155-721 | WORKSHOP EQUIPMENT |  | 완료 | 100% |  | 장동철 책임
761 | IBRU | 장치 | RN2156-101 | FIRED HEATER |  | 완료 | 100% | - | 정진우 책임
762 | IBRU | 장치 | RN2157-301 | SRU BURNER, CHAMBER & WHB & INCINERATOR PKG |  | 완료 | 100% | - | 정진우 책임
763 | IBRU | 회전 | RN2158-203 | API 672 AIR COMPRESSOR PACKAGE (STEAM TURBINE 2, MOTOR 1) |  | 완료 | 100% | - | 장동철 책임
764 | IBRU | 회전 | RN2158-101 | API 610 HEAVY DUTY CENTRIFUGAL PUMPS (BB5) |  | 완료 | 100% | - | 장동철 책임
765 | IBRU | 회전 | RN2158-102 | API 610 CENTRIFUGAL PUMPS (HORIZONTAL TYPE) |  | 완료 | 100% | - | 장동철 책임
766 | IBRU | 회전 | RN2158-103 | API 610 CENTRIFUGAL PUMPS (VERTICAL TYPE) |  | 완료 | 100% | - | 고팔라크리스낸 매니저
767 | IBRU | 회전 | RN2158-104 | NON-API CENTRIFUGAL PUMPS |  | 완료 | 100% | - | 고팔라크리스낸 매니저
768 | IBRU | 회전 | RN2158-108 | SULPHUR PUMPS |  | 완료 | 100% | - | 장동철 책임
769 | IBRU | 회전 | RN2158-109 | NFPA 20 FIRE WATER PUMPS |  | 완료 | 100% | - | 장동철 책임
770 | IBRU | 회전 | RN2158-111 | API 674 RECIPROCATING PUMP |  | 완료 | 100% | - | 장동철 책임
771 | IBRU | 장치 | RN215A-221 | COOLING TOWER SAND FILTER PKG |  | 완료 | 100% | - | 나광조 책임
772 | IBRU | 회전 | RN215A-301 | COOLING TOWER |  | 완료 | 100% | - | 장동철 책임
773 | IBRU | 회전 | RN215A-401 | CHILLER PACKAGE |  | 완료 | 100% | - | 정진우 책임
774 | IBRU | 장치 | RN215A-501 | AIR DRYERS PACKAGE |  | 완료 | 100% | - | 정진우 책임
775 | IBRU | 회전 | RN215A-601 | N2 GENERATION, LIN STORAGE AND VAPORIZATION PKG |  | 2026-04-30 | 100% | Distillation column 재 제작 (4/20 Pneumatic Test 및 Final Inspection 예정) | 장동철 책임
776 | IBRU | 회전 | RN215A-801 | WASTE WATER TREATMENT PACKAGE |  | 완료 | 100% | - | 장동철 책임
777 | IBRU | 장치 | RN215A-Z01 | SPENT CAUSTIC TREATMENT PACKAGE |  | 완료 | 100% | - | 고팔라크리스낸 매니저
778 | IBRU | 회전 | RN215A-901 | CHEMICAL INJECTION PACKAGE |  | 완료 | 100% | - | 정진우 책임
779 | IBRU | 장치 | RN215B-401 | DEAERATOR |  | 완료 | 100% | - | 정진우 책임
780 | IBRU | 소방/안전 | RN215Z-002 | SAFETY EQUIPMENT & MOBILE EQUIPMENT |  | 완료 | 100% |  | 고팔라크리스낸 매니저
781 | IBRU | 소방/안전 | RN215Z-003 | BUILDING FIREFIGHTING EQUIPMENT |  | 완료 | 100% |  | 고팔라크리스낸 매니저
782 | IBRU | 배관 | RN216A-101 | CARBON STEEL AND LTCS SEAMLESS PIPES |  | 완료 | 100% | - | 석우경 매니저
783 | IBRU | 배관 | RN216A-102 | CARBON STEEL AND LTCS WELDED PIPES |  | 완료 | 100% | - | 석우경 매니저
784 | IBRU | 배관 | RN216A-103 | LOW ALLOY STEEL SEAMLESS PIPES |  | 완료 | 100% | - | 석우경 매니저
785 | IBRU | 배관 | RN216A-105 | STAINLESS STEEL SEAMLESS PIPES |  | 완료 | 100% | - | 강태준 책임
786 | IBRU | 배관 | RN216A-106 | STAINLESS STEEL WELDED PIPES |  | 완료 | 100% | - | 강태준 책임
787 | IBRU | 배관 | RN216A-109 | GRP PIPES AND PIPING COMPONENTS |  | 완료 | 100% | - | 강태준 책임
788 | IBRU | 배관 | RN216A-110 | PVC PIPES AND PIPING COMPONENTS |  | 완료 | 100% | - | 강태준 책임
789 | IBRU | 배관 | RN216A-112 | HDPE PIPES AND PIPING COMPONENTS |  | 완료 | 100% | - | 강태준 책임
790 | IBRU | 배관 | RN216B-131 | CAST STEEL VALVES |  | 완료 | 100% | - | 강태준 책임
791 | IBRU | 배관 | RN216B-135 | FORGED STEEL VALVES |  | 완료 | 100% | - | 강태준 책임
792 | IBRU | 배관 | RN216B-137 | BALL VALVES |  | 완료 | 100% | - | 강태준 책임
793 | IBRU | 배관 | RN216B-139 | BUTTERFLY VALVES |  | 완료 | 100% | - | 강태준 책임
794 | IBRU | 배관 | RN216B-142 | DUAL PLATE CHECK VALVES |  | 완료 | 100% | - | 강태준 책임
795 | IBRU | 배관 | RN216B-143 | PLUG VALVES |  | 완료 | 100% | - | 강태준 책임
796 | IBRU | 배관 | RN216B-144 | BRONZE VALVES |  | 완료 | 100% | - | 강태준 책임
797 | IBRU | 배관 | RN216B-145 | DIAPHRAGM VALVES |  | 완료 | 100% | - | 강태준 책임
798 | IBRU | 배관 | RN216B-149 | UNLISTED VALVES |  | 완료 | 100% | - | 강태준 책임
799 | IBRU | 배관 | RN216C-161 | WROUGHT FITTING (BUTT WELDING FITTING) |  | 완료 | 100% | - | 강태준 책임
800 | IBRU | 배관 | RN216C-164 | FORGED STEEL FITTINGS |  | 완료 | 100% | - | 강태준 책임
801 | IBRU | 배관 | RN216D-171 | FLANGES |  | 완료 | 100% | - | 고팔라크리스낸 매니저
802 | IBRU | 배관 | RN216D-171-B | FLANGES |  | 완료 | 100% | - | 고팔라크리스낸 매니저
803 | IBRU | 배관 | RN216E-181 | BOLTS AND NUTS |  | 완료 | 100% | VO 진행 중 | 석우경 매니저
804 | IBRU | 배관 | RN216F-191 | GASKETS |  | 완료 | 100% | VO 진행 중 | 석우경 매니저
805 | IBRU | 배관 | RN216G-201 | STRAINERS |  | 완료 | 100% | - | 고팔라크리스낸 매니저
806 | IBRU | 배관 | RN216G-204 | SILENCERS |  | 완료 | 100% | - | 고팔라크리스낸 매니저
807 | IBRU | 배관 | RN216G-206 | STEAM TRAPS |  | 완료 | 100% | - | 강태준 책임
808 | IBRU | 배관 | RN216G-211 | FLAME ARRESTORS |  | 완료 | 100% | - | 고팔라크리스낸 매니저
809 | IBRU | 배관 | RN216G-215 | RUBBER EXPANSION JOINTS |  | 완료 | 100% | - | 고팔라크리스낸 매니저
810 | IBRU | 배관 | RN216G-315 | BLOWDOWN VALVES |  | 완료 | 100% | - | 강태준 책임
811 | IBRU | 배관 | RN216G-316 | RAM VALVES |  | 완료 | 100% | - | 강태준 책임
812 | IBRU | 배관 | RN216G-604 | SAMPLE PROBES AND INJECTION NOZZLES |  | 완료 | 100% | - | 고팔라크리스낸 매니저
813 | IBRU | 배관 | RN216G-608 | VALVE INTERLOCKING DEVICES |  | 완료 | 100% |  | 고팔라크리스낸 매니저
814 | IBRU | 배관 | RN216G-611 | FLEXIBLE METAL TUBES AND HOSE CONNECTOR |  | 완료 | 100% | - | 고팔라크리스낸 매니저
815 | IBRU | 배관 | RN216G-612 | HOSE & HOSE COUPLING |  | 완료 | 100% | - | 고팔라크리스낸 매니저
816 | IBRU | 배관 | RN216G-616 | TUBES AND TUBE FITTINGS |  | 완료 | 100% | - | 고팔라크리스낸 매니저
817 | IBRU | 배관 | RN216G-620 | PRE-INSULATED TUBE |  | 완료 | 100% | - | 고팔라크리스낸 매니저
818 | IBRU | 배관 | RN216G-621 | STEAM AND CONDENSATE MANIFOLD |  | 완료 | 100% | - | 고팔라크리스낸 매니저
819 | IBRU | 배관 | RN216G-622 | VACUUM BREAKER |  | 완료 | 100% | - | 석우경 매니저
820 | IBRU | 배관 | RN216K-704 | SPRING SUPPORTS, STRUTS, AND SNUBBERS |  | 완료 | 100% | - | 고팔라크리스낸 매니저
821 | IBRU | 계장 | RN2173-101 | ELECTRONIC FIELD TRANSMITTERS |  | 완료 | 100% | - | 이해석 책임
822 | IBRU | 계장 | RN2173-202 | VARIABLE AREA TYPE FLOW INSTRUMENTS |  | 완료 | 100% | - | 이해석 책임
823 | IBRU | 계장 | RN2173-203 | VORTEX TYPE FLOW INSTRUMENTS |  | 완료 | 100% | - | 이해석 책임
824 | IBRU | 계장 | RN2173-204 | ULTRASONIC FLOW INSTRUMENTS |  | 완료 | 100% | - | 이해석 책임
825 | IBRU | 계장 | RN2173-208 | CORIOLIS & ELECTRO MAGNETIC FLOW INSTRUMENTS |  | 완료 | 100% | - | 이해석 책임
826 | IBRU | 계장 | RN2173-303 | RADAR LEVEL TRANSMITTERS |  | 완료 | 100% | - | 이해석 책임
827 | IBRU | 계장 | RN2173-402 | THERMOCOUPLES AND RTDS & WELLS |  | 완료 | 100% | - | 이해석 책임
828 | IBRU | 계장 | RN2173-403 | MULTIPOINT TEMPERATURE ELEMENT |  | 완료 | 100% | - | 이해석 책임
829 | IBRU | 계장 | RN2173-501 | PRESSURE & TEMPERATURE GAUGES |  | 완료 | 100% | - | 이해석 책임
830 | IBRU | 계장 | RN2173-601 | FLOW ELEMENTS |  | 완료 | 100% | - | 이해석 책임
831 | IBRU | 계장 | RN2174-101 | CONTROL VALVES |  | 완료 | 100% |  | 강태준 책임
832 | IBRU | 계장 | RN2174-201 | ON-OFF & MOTOR OPERATED VALVES - BALL TYPE |  | 완료 | 100% | - | 강태준 책임
833 | IBRU | 계장 | RN2174-202 | ON-OFF & MOTOR OPERATED VALVES - BUTTERFLY TYPE |  | 완료 | 100% | - | 강태준 책임
834 | IBRU | 계장 | RN2174-204 | ON-OFF & MOTOR OPERATED VALVES - GATE |  | 완료 | 100% | - | 강태준 책임
835 | IBRU | 계장 | RN2174-401 | PRESSURE REGULATOR |  | 완료 | 100% | - | 고팔라크리스낸 매니저
836 | IBRU | 계장 | RN216G-602 | SAMPLING SYSTEMS |  | 완료 | 100% | - | 이해석 책임
837 | IBRU | 계장 | RN2176-001 | FIRE AND GAS DEVICES |  | 완료 | 100% | - | 최종현 책임
838 | IBRU | 계장 | RN2178-101 | INSTRUMENT CABLE TRAYS |  | 완료 | 100% | - | 최종현 책임
839 | IBRU | 계장 | RN2175-101 | ANALYZER SYSTEM |  | 완료 | 100% | - | 이해석 책임
840 | IBRU | 계장 | RN2178-201 | INSTRUMENT CABLES |  | 완료 | 100% | - | 최종현 책임
841 | IBRU | 계장 | RN2178-203 | INSTRUMENT JUNCTION BOXES |  | 완료 | 100% | - | 최종현 책임
842 | IBRU | 계장 | RN2178-204 | INSTRUMENT CABLE GLANDS |  | 완료 | 100% | - | 최종현 책임
843 | IBRU | 계장 | RN2178-306 | TUBES & TUBE FITTINGS |  | 완료 | 100% | - | 최종현 책임
844 | IBRU | 계장 | RN2178-601 | INSTRUMENT BULK MATERIALS |  | 완료 | 100% |  | 최종현 책임
845 | IBRU | 계장 | RN2178-103 | INSTRUMENT CABLE TRANSITS |  | 완료 | 100% | - | 최종현 책임
846 | IBRU | 계장 | RN216G-505 | LEVEL GAUGES & SIGHT GLASSES |  | 완료 | 100% | - | 이해석 책임
847 | IBRU | 전기 | RN2180-101 | ELECTRICAL BULK MATERIALS |  | 완료 | 100% | - | 이해석 책임
848 | IBRU | 전기 | RN2180-102 | CABLE TERMINATION & SPLICING KITS |  | 완료 | 100% | - | 이해석 책임
849 | IBRU | 전기 | RN2180-111 | CABLE GLAND |  | 완료 | 100% | - | 이해석 책임
850 | IBRU | 전기 | RN2180-121 | CABLE TRAY |  | 완료 | 100% | - | 이해석 책임
851 | IBRU | 전기 | RN2181-701 | ELECTRICAL MISCELLANEOUS PANEL |  | 완료 | 100% | - | 이해석 책임
852 | IBRU | 전기 | RN2182-211 | LOCAL CONTROL STATION AND ISOLATION SWITCH |  | 완료 | 100% | - | 이해석 책임
853 | IBRU | 전기 | RN2182-601 | POWER & CONTROL CABLES |  | 완료 | 100% | - | 이해석 책임
854 | IBRU | 전기 | RN2183-101 | OUTDOOR DISTRIBUTION PANEL |  | 완료 | 100% | - | 이해석 책임
855 | IBRU | 전기 | RN2183-231 | OUTDOOR LIGHTING FIXTURE, JB & SOCKET OULET |  | 완료 | 100% | - | 이해석 책임
856 | IBRU | 전기 | RN2183-102 | INDOOR DISTRIBUTION PANEL |  | 완료 | 100% | - | 이해석 책임
857 | IBRU | 전기 | RN2183-232 | INDOOR LIGHTING FIXTURE, JB & SOCKET OULET |  | 완료 | 100% | - | 이해석 책임
858 | IBRU | 전기 | RN2185-001 | FIRE ALARM SYSTEM |  | 완료 | 100% | - | 이해석 책임
859 | IBRU | 전기 | RN2188-001 | ELECTRICAL HEAT TRACING SYSTEM |  | 완료 | 100% | - | 이해석 책임
860 | IBRU | 기타 | RN21C1-001/002 | CATALYST |  | 완료 | 100% | - | 고팔라크리스낸 매니저
861 | IBRU | 기타 | RN21C2-002 | CHEMICAL AND LUBE OILS |  | 완료 | 100% |  | 고팔라크리스낸 매니저
862 | CSSP | 회전 | MR-MR-001 | GTG PACKAGE | 1 item / 5 sets | 2028-03-01 | 0% |  | 서민 책임
863 | CSSP | 회전 | MR-MR-002 | FUEL GAS COMPRESSOR PACKAGE | 1 item / 3 sets |  |  |  | 서민 책임
864 | CSSP | 회전 | MR-MR-003 | AIR COMPRESSOR | 3 items / 6 sets |  |  |  | 서민 책임
865 | CSSP | 회전 | MR-MR-004 | SHIPPING PUMP | 1 item / 5 sets |  |  |  | 서민 책임
866 | CSSP | 회전 | MR-MR-005 | CENTRIFUGAL PUMP (BB) | 2 items / 23 sets |  |  |  | 서민 책임
867 | CSSP | 회전 | MR-MR-006 | CENTRIFUGAL PUMP (VS) | 2 items / 18 sets |  |  |  | 서민 책임
868 | CSSP | 회전 | MR-MR-007 | CENTRIFUGAL HORIZONTAL PUMP | 15 items / 35 sets |  |  |  | 서민 책임
869 | CSSP | 회전 | MR-MR-008 | SEALLESS PUMP | 15 items / 42 sets |  |  |  | 서민 책임
870 | CSSP | 회전 | MR-MR-009 | SUBMERSIBLE PUMP | 8 items / 31 sets |  |  |  | 서민 책임
871 | CSSP | 회전 | MR-MR-010 | ROTARY PUMP | 3 items / 9 sets |  |  |  | 서민 책임
872 | CSSP | 회전 | MR-MR-011 | PROGRESSIVE CAVITY PUMP | 2 items / 20 sets |  |  |  | 서민 책임
873 | CSSP | 회전 | MR-MR-012 | AIR OPERATED DIAPHRAGM PUMP | 9 items / 23 sets |  |  |  | 서민 책임
874 | CSSP | 회전 | MR-MR-013 | FIRE WATER PUMP PACKAGE | 2 items / 3 sets |  |  |  | 서민 책임
875 | CSSP | 회전 | MR-MR-014 | CHEMICAL INJECTION PACKAGE | 16 Set |  |  |  | 장동철 책임
876 | CSSP | 회전 | MR-MR-015 | SEAWATER INTAKE SYSTEM | Drum Screen : 2 Set, Bar Screen : 4 Set |  |  |  | 장동철 책임
877 | CSSP | 회전 | MR-MR-016 | REACTOR CLARIFIER | 10 Set |  |  |  | 장동철 책임
878 | CSSP | 회전 | MR-MR-017 | ELECTROCHLORINATION SYSTEM | Dosing Pump 4 ea Centrifugal Pump : 2 ea Storage Tank : 3 기 (Acid Cleaning, Hypochlorite) Strainer 2 ea Air Blower : 3 ea Hypochlorite Generating Module : 3 Set Ejector : 1 ea |  |  |  | 장동철 책임
879 | CSSP | 회전 | MR-MR-018 | POTABLE WATER GENERATION PACKAGE | Metering Pump : 22 EA Centr. Pump : 15 EA Tank : 4 기 Filter : 17 EA RO Module : 4 Set Turbo Charger : 5 Set |  |  |  | 장동철 책임
880 | CSSP | 회전 | MR-MR-021 | POLYMER MAKEUP SYSTEM PACKAGE | 3 Set |  |  |  | 장동철 책임
881 | CSSP | 회전 | MR-MR-022 | SEWAGE TREATMENT PAKCAGE | Metering Pump : 2 ea Centri. Pump : 9 ea Tank : 5기 Decanter : 2 ea Distribution chamber : 1 ea SBR : 2 ea Bin : 2 ae Aerator : 2 ea Air Blower : 2 ea Sludge drying bed : 6 ea |  |  |  | 장동철 책임
882 | CSSP | 회전 | MR-MR-023 | CPI & OIL SKIMMER | Oil Skimmer PKG : 2 Set Separator : 1 ea |  |  |  | 장동철 책임
883 | CSSP | 회전 | MR-MR-024 | CENTRIFUGE SYSTEM | Seawater Sludge Centrifuge : 14 ea Diesel Centrifugal Pump : 3 ea Diesel Centrifuge : 3 ea |  |  |  | 장동철 책임
884 | CSSP | 회전 | MR-MR-025 | CONVEYOR PACKAGE | Sludge Conveyor : 14 Set Bulk Sludge Conveyor : 3 Set |  |  |  | 장동철 책임
885 | CSSP | 회전 | MR-MR-026 | SUBMERSIBLE MIXER (SIDE ENTRY MIXER) | 2 items / 6 sets |  |  |  | 서민 책임
886 | CSSP | 회전 | MR-MR-027 | GOLIATH GANTRY CRANE | 1 item / 1 set |  |  |  | 서민 책임
887 | CSSP | 회전 | MR-MR-028 | CLAMSHELL BUCKET CRANE | 1 item / 4 sets |  |  |  | 서민 책임
888 | CSSP | 회전 | MR-MR-029 | CRANE & HOIST | 19 items / 30 sets |  |  |  | 서민 책임
889 | CSSP | 회전 | MR-MR-030 | MOBILE CRANE & FORKLIFT | 3 items / 3 sets |  |  |  | 서민 책임
890 | CSSP | 회전 | MR-MR-031 | TRUCK SCALE | 5 Set |  |  |  | 장동철 책임
891 | CSSP | 회전 | MR-MR-032 | FUEL DISPENSER UNIT | 8 Set |  |  | Inspection Level 4 | 장동철 책임
892 | CSSP | 회전 | MR-MR-033 | WORKSHOP EQUIPMENT |  |  |  | Inspection Level 4 | 장동철 책임
893 | CSSP | 회전 | MR-MR-034 | ELEVATOR | 2 items / 3 sets |  |  |  | 서민 책임
894 | CSSP | 소방/안전 | MR-EH-001 | FIRE FIGHTING EQUIPMENT |  |  |  | Inspection Level 4 | 장동철 책임
895 | CSSP | 소방/안전 | MR-EH-002 | GAS EXTINGUISHING SYSTEM |  |  |  | Inspection Level 4 | 장동철 책임
896 | CSSP | 장치 | MR-MS-001 | VESSEL | 19 items / 53 sets |  |  |  | 정진우 책임
897 | CSSP | 장치 | MR-MS-002 | FILTER | 2 items / 5 sets |  |  |  | 나광조 책임
898 | CSSP | 장치 | MR-MS-003 | FILTER PACKAGE | Vessel 80 sets / Blower 12 sets |  |  |  | 나광조 책임
899 | CSSP | 장치 | MR-MS-004 | VACUUM DEAERATION PACKAGE | Vessel 12 sets / Vacuum Pump Skid 28set |  |  |  | 나광조 책임
900 | CSSP | 장치 | MR-MS-005 | NITROGEN PACKAGE | 10 sets |  |  |  | 나광조 책임
901 | CSSP | 장치 | MR-MS-006 | AIR DRYER PACKAGE | 2 items / 4 sets |  |  |  | 나광조 책임
902 | CSSP | 장치 | MR-MS-007 | STORAGE TANK (AWWA D103) | Tank 17 ea |  |  |  | 정진우 책임
903 | CSSP | 장치 | MR-MS-008 | STORAGE TANK (API 650) | Tank 9 ea |  |  |  | 정진우 책임
904 | CSSP | 장치 | MR-MS-009 | GRP TANK | Tank 28 ea |  |  |  | 정진우 책임
905 | CSSP | 장치 | MR-MS-010 | STATIC MIXER | 7 items / 56 sets |  |  |  | 고팔라크리스낸 매니저
906 | CSSP | 장치 | MR-MS-012 | STRAINER | 2 items / 16 sets |  |  |  | 고팔라크리스낸 매니저
907 | CSSP | 장치 | MR-MS-013 | VENT STACK | 2 items / 2 sets |  |  |  | 고팔라크리스낸 매니저
908 | CSSP | 장치 | MR-MS-014 | PIG LAUNCHER | 2 items / 2 sets |  |  |  | 나광조 책임
909 | CSSP | 장치 | MR-MS-015 | AIR ELIMINATOR | 1 items / 3 sets |  |  |  | 고팔라크리스낸 매니저
910 | CSSP | 장치 | MR-MS-016 | GEODESIK COVER | 5 items / 24 sets |  |  |  | 고팔라크리스낸 매니저
911 | CSSP | 장치 | MR-MS-017 | CARBON DEODORIZER | 2 items / 7 sets |  |  |  | 고팔라크리스낸 매니저
912 | CSSP | 장치 | MR-MS-018 | ELECTRIC HEATER | 1 items / 3 sets |  |  |  | 정진우 책임
913 | CSSP | 장치 | MR-MS-019 | CALCITE FILTER | 1 items / 2 sets |  |  |  | 정진우 책임
914 | CSSP | 장치 | MR-MS-020 | HYDROPNEUMATIC TANK | 3 items / 3 sets |  |  | Internal Type (Bladder Internal) 적용으로 MS001 Vessel PO에서 분리 발주 | 정진우 책임
915 | CSSP | 장치 | MR-MS-021 | PENSTOCK & STOPGATE | 3 items / 5 sets |  |  |  | 나광조 책임
916 | CSSP | 배관 | PI-0001 | CS SMLS PIPE | 873.43 ton |  |  |  | 석우경 매니저
917 | CSSP | 배관 | PI-0002 | CS WELDED PIPE | 2644.81 ton |  |  |  | 강태준 책임
918 | CSSP | 배관 | PI-0003 | SS SMLS PIPE | 164.9 ton |  |  |  | 석우경 매니저
919 | CSSP | 배관 | PI-0004 | SS WELDED PIPE | 25.69 ton |  |  |  | 강태준 책임
920 | CSSP | 배관 | PI-0005 | FORGED FITTING | 13.71 ton |  |  |  | 석우경 매니저
921 | CSSP | 배관 | PI-0006 | WROUGHT FITTING | 344.12 ton |  |  |  | 강태준 책임
922 | CSSP | 배관 | PI-0007 | FLANGE | 2182.92 ton |  |  |  | 강태준 책임
923 | CSSP | 배관 | PI-0008 | GASKET | 46.38 ton |  |  |  | 석우경 매니저
924 | CSSP | 배관 | PI-0009 | BOLT&NUTS | 889.47 ton |  |  |  | 석우경 매니저
925 | CSSP | 배관 | PI-0010 | FORGED VALVE | 1156 EA |  |  |  | 강태준 책임
926 | CSSP | 배관 | PI-0011 | CASTING VALVE | 61 EA |  |  |  | 강태준 책임
927 | CSSP | 배관 | PI-0012 | BALL VALVE | 3898 EA |  |  |  | 강태준 책임
928 | CSSP | 배관 | PI-0013 | ECCENTRIC PLUG VALVE | 138 EA |  |  |  | 강태준 책임
929 | CSSP | 배관 | PI-0014 | DUAL PLATE CHECK VALVE | 222 EA |  |  |  | 강태준 책임
930 | CSSP | 배관 | PI-0015 | BUTTERFLY VALVE | 988 EA |  |  |  | 강태준 책임
931 | CSSP | 배관 | PI-0016 | BRONZE VALVE | 1353 EA |  |  |  | 강태준 책임
932 | CSSP | 배관 | PI-0017 | PIV | 202 EA |  |  |  | 강태준 책임
933 | CSSP | 배관 | PI-0018 | PTFE LINED | 1772.1 M/EA |  |  |  | 강태준 책임
934 | CSSP | 배관 | PI-0019 | GRV PIPING | 2305.62 ton |  |  |  | 석우경 매니저
935 | CSSP | 배관 | PI-0020 | HDPE PIPING | 83.25 ton |  |  |  | 석우경 매니저
936 | CSSP | 배관 | PI-0021 | CPVC PIPING | 112.61 ton |  |  |  | 석우경 매니저
937 | CSSP | 배관 | PI-0022 | STRAINER | 121 EA |  |  |  | 강태준 책임
938 | CSSP | 배관 | PI-0023 | CHEMICAL INJECTION FITTING | 46 set |  |  |  | 석우경 매니저
939 | CSSP | 배관 | PI-0024 | FLAME ARRESTOR | 3 set |  |  |  | 석우경 매니저
940 | CSSP | 배관 | PI-0026 | FLEXIBLE HOSE & HOSE COUPLING | 1628 set |  |  |  | 석우경 매니저
941 | CSSP | 배관 | PI-0027 | AIR RELEASE VENT & AIR TRAP | 41 EA |  |  |  | 강태준 책임
942 | CSSP | 배관 | PI-0028 | EXPANSION JOINT | 42 EA |  |  |  | 강태준 책임
943 | CSSP | 배관 | PI-0029 | SPRING SUPPORT | 119 EA |  |  |  | 강태준 책임
944 | CSSP | 배관 | PI-0030 | INT+EXT COATING | 5060.43 ton |  |  |  | 강태준 책임
945 | CSSP | 배관 | PI-0031 | TELESCOPIC VALVE | 10 EA |  |  |  | 강태준 책임
946 | CSSP | 배관 | PI-0032 | OIL STOP VALVE | 18 EA |  |  |  | 강태준 책임
947 | CSSP | 배관 | PL-0003 | ISOLATING JOINT | 3 set |  |  |  | 석우경 매니저
948 | CSSP | 철골 | STEEL STRUTURE | STEEL STRUTURE | 17,000 ton |  |  |  | 고팔라크리스낸 매니저
949 | CSSP | 공조 | MR-HV-001 | HVAC EQUIPMENT (HVAC CONTROL 포함) |  |  |  |  | 장동철 책임 | 윤희수 책임
950 | CSSP | 전기 | MR-EL-0001 | 33KV GIS | 55 bays |  |  |  | 윤희수 책임 | 이해석 책임
951 | CSSP | 전기 | MR-EL-0002 | HV SWGR/MCC, BUS DUCT |  |  |  |  | 윤희수 책임 | 이해석 책임
952 | CSSP | 전기 | MR-EL-0003 | LV SWGR/MCC, BUS DUCT |  |  |  |  | 윤희수 책임 | 이해석 책임
953 | CSSP | 전기 | MR-EL-0004 | ECMS |  |  |  |  | 윤희수 책임 | 이해석 책임
954 | CSSP | 전기 | MR-EL-0005 | POWER TRANSFORMER & NGR | 69 units |  |  |  | 윤희수 책임 | 이해석 책임
955 | CSSP | 전기 | MR-EL-0006 | UPS & DC SYSTEM |  |  |  |  | 윤희수 책임 | 이해석 책임
956 | CSSP | 전기 | MR-EL-0007 | EMERGENCY DIESEL GENERATOR |  |  |  |  | 윤희수 책임 | 이해석 책임
957 | CSSP | 전기 | MR-EL-0008 | SOLAR POWER SUPPLY SYSTEM & LOCAL EQUIPMENT ROOM (LER) |  |  |  |  | 윤희수 책임 | 이해석 책임
958 | CSSP | 전기 | MR-EL-0009 | DISTRIBUTION SUBSTATION (DSS) |  |  |  |  | 윤희수 책임 | 이해석 책임
959 | CSSP | 전기 | MR-EL-0010 | CATHODIC PROTECTION SYSTEM |  |  |  |  | 윤희수 책임 | 이해석 책임
960 | CSSP | 전기 | MR-EL-0011 | ELEC. HEAT TRACING SYSTEM |  |  |  |  | 술탄 매니저 | 윤희수 책임
961 | CSSP | 전기 | MR-EL-0012 | FIRE ALARM SYSTEM |  |  |  |  | 술탄 매니저 | 윤희수 책임
962 | CSSP | 전기 | MR-EL-0013 | LIGHTING SYSTEM |  |  |  |  | 술탄 매니저 | 윤희수 책임
963 | CSSP | 전기 | MR-EL-0015 | POWER AND LIGHTING DISTRIBUTION PANEL |  |  |  |  | 윤희수 책임 | 이해석 책임
964 | CSSP | 전기 | MR-EL-0018 | CABLE TRAY |  |  |  |  | 술탄 매니저 | 윤희수 책임
965 | CSSP | 전기 | MR-EL-0019 | LCS & JUNCTION BOX |  |  |  |  | 술탄 매니저 | 윤희수 책임
966 | CSSP | 전기 | MR-EL-0020 | POWER & CONTROL CABLE |  |  |  |  | 윤희수 책임 | 이해석 책임
967 | CSSP | 전기 | MR-EL-0021 | SIGNAL CABLE |  |  |  |  | 윤희수 책임 | 이해석 책임
968 | CSSP | 전기 | MR-EL-0022 | EARTHING & LIGHTNING |  |  |  |  | 술탄 매니저 | 윤희수 책임
969 | CSSP | 전기 | MR-EL-0023 | CABLE GLAND |  |  |  |  | 술탄 매니저 | 윤희수 책임
970 | CSSP | 전기 | MR-EL-0024 | CABLE TERMINATION KIT |  |  |  |  | 술탄 매니저 | 윤희수 책임
971 | CSSP | 전기 | MR-EL-0025 | CONDUIT & FITTING |  |  |  |  | 술탄 매니저 | 윤희수 책임
972 | CSSP | 전기 | MR-EL-0026 | ELECTRICAL BULK MATERIAL |  |  |  |  | 술탄 매니저 | 윤희수 책임
973 | CSSP | 통신 | MR-TE-0001 | TELECOMMUNICATION SYSTEM |  |  |  |  | 윤희수 책임 | 이해석 책임
974 | CSSP | 계장 | MR-IC-0001 | INTEGRATED CONTROL & SAFETY SYSTEM (ICSS) |  |  |  |  | 윤희수 책임 | 강인묵 책임
975 | CSSP | 계장 | MR-IC-0002 | MACHINE CONDITION MONITORING SYSTEM (MCMS) |  |  |  |  | 윤희수 책임 | 강인묵 책임
976 | CSSP | 계장 | MR-IC-0003 | CUSTODY TRANSFER METERING SYSTEM |  |  |  |  | 강인묵 책임 | 윤희수 책임
977 | CSSP | 계장 | MR-IC-0004 | LEAK DETECTION SYSTEM |  |  |  |  | 강인묵 책임 | 윤희수 책임
978 | CSSP | 계장 | MR-IC-0005 | ANALYSER SYSTEM WITH SHELTER |  |  |  |  | 강인묵 책임 | 윤희수 책임
979 | CSSP | 계장 | MR-IC-0006 | ON-OFF VALVE AND MOV (BALL) |  |  |  |  | 강태준 책임
980 | CSSP | 계장 | MR-IC-0007 | ON-OFF VALVE (SOLENOID) |  |  |  |  | 강태준 책임
981 | CSSP | 계장 | MR-IC-0008 | ON-OFF VALVE AND MOV (BUTTERFLY) |  |  |  |  | 강태준 책임
982 | CSSP | 계장 | MR-IC-0009 | MOV (PLUG) |  |  |  |  | 강태준 책임
983 | CSSP | 계장 | MR-IC-0010 | MOV (BUTTERFLY, 600# FBE) |  |  |  |  | 강태준 책임
984 | CSSP | 계장 | MR-IC-0011 | CONTROL VALVE |  |  |  |  | 강태준 책임
985 | CSSP | 계장 | MR-IC-0012 | PRESSURE REGULATOR |  |  |  |  | 강태준 책임
986 | CSSP | 계장 | MR-IC-0013 | PRESSURE SAFETY VALVE AND RUPTURE DISK |  |  |  |  | 강태준 책임
987 | CSSP | 계장 | MR-IC-0014 | MAGNETIC FLOWMETER AND FLOW SWITCH |  |  |  |  | 강인묵 책임 | 윤희수 책임
988 | CSSP | 계장 | MR-IC-0015 | POSITIVE DISPLACEMENT FLOWMETER |  |  |  |  | 강인묵 책임 | 윤희수 책임
989 | CSSP | 계장 | MR-IC-0016 | ACTIVE CHECK VALVE |  |  |  |  | 강태준 책임
990 | CSSP | 계장 | MR-IC-0017 | TRANSMITTERS |  |  |  |  | 강인묵 책임 | 윤희수 책임
991 | CSSP | 계장 | MR-IC-0018 | LOCAL GAUGE |  |  |  |  | 술탄 매니저 | 윤희수 책임
992 | CSSP | 계장 | MR-IC-0019 | FLOW ELEMENT |  |  |  |  | 강인묵 책임 | 윤희수 책임
993 | CSSP | 계장 | MR-IC-0020 | LEVEL INSTRUMENT AND LEVEL SWITCH |  |  |  |  | 강인묵 책임 | 윤희수 책임
994 | CSSP | 계장 | MR-IC-0021 | LEVEL GAUGE |  |  |  |  | 강인묵 책임 | 윤희수 책임
995 | CSSP | 계장 | MR-IC-0022 | GAS DETECTOR, HORN AND BEACON |  |  |  |  | 술탄 매니저 | 윤희수 책임
996 | CSSP | 계장 | MR-IC-0023 | ULTRASONIC FLOWMETER |  |  |  |  | 강인묵 책임 | 윤희수 책임
997 | CSSP | 계장 | MR-IC-0101 | INSTRUMENT CABLE |  |  |  |  | 술탄 매니저 | 윤희수 책임
998 | CSSP | 계장 | MR-IC-0102 | INSTRUMENT CABLE TRAY |  |  |  |  | 술탄 매니저 | 윤희수 책임
999 | CSSP | 계장 | MR-IC-0103 | INSTRUMENT JUNTION BOX |  |  |  |  | 술탄 매니저 | 윤희수 책임
1000 | CSSP | 계장 | MR-IC-0104 | INSTRUMENT CABLE GLAND |  |  |  |  | 술탄 매니저 | 윤희수 책임
1001 | CSSP | 계장 | MR-IC-0105 | INSTRUMENT TUBE & FITTING |  |  |  |  | 강인묵 책임 | 윤희수 책임
1002 | CSSP | 계장 | MR-IC-0106 | INSTRUMENT PIPE & FITTING |  |  |  |  | 강인묵 책임 | 윤희수 책임
1003 | CSSP | 계장 | MR-IC-0107 | INSTRUMENT CONDUIT & FITTING |  |  |  |  | 술탄 매니저 | 윤희수 책임
1004 | CSSP | 계장 | MR-IC-0108 | INSTRUMENT BLOCK VALVE, AIR MANIFOLD |  |  |  |  | 강인묵 책임 | 윤희수 책임
1005 | CSSP | 계장 | MR-IC-0109 | MISC BULK |  |  |  |  | 술탄 매니저 | 윤희수 책임
1006 | CSSP | 계장 | MR-IC-0110 | INSTRUMENT SUPPORT & CONSUMABLE |  |  |  |  | 술탄 매니저 | 윤희수 책임
1007 | CSSP | 기타 | MR-PR-001 | SPECIALTY CHEMICALS |  |  |  |  | 장동철 책임
1008 | CSSP | 기타 | MR-PR-002 | COMMODITY CHEMICALS |  |  |  |  | 장동철 책임
1009 | CSSP | 기타 | MR-PR-002 | LABORATORY EQUIPMENT |  |  |  | Inspection Level 4 | 장동철 책임
1010 | PNG1 | 철골 | R-2130-002 | FABRICATED STRUCTURAL STEEL FOR PRE-SHUTDOWN & SHUTDOWN | - |  |  |  | 고팔라크리스낸 매니저 | 나광조 책임
1011 | PNG1 | 철골 | S120-001 | CHEMICAL ANCHOR BOLT FOR PRE-SHUTDOWN & SHUTDOWN |  |  |  |  | 고팔라크리스낸 매니저 | 나광조 책임
1012 | PNG1 | 장치 | R-2154-101 | STORAGE TANK | 2 |  |  |  | 나광조 책임 | 고팔라크리스낸 매니저
1013 | PNG1 | 회전 | R-2155-501 | LNG LOADING ARM | 5 |  |  |  | 서민 책임 | 강태준 책임
1014 | PNG1 | 회전 | R-2155-504 | CONDENSATE LOADING HOSE & HOSE REEL | 3 |  |  |  | 강태준 책임 | 서민 책임
1015 | PNG1 | 회전 | R-2155-507 | TELESCOPIC KNUCKLE BOOM CRANE | 1 |  |  |  | 강태준 책임 | 서민 책임
1016 | PNG1 | 회전 | R-2158-103 | SEA WATER INTAKE PUMP | TBA |  |  |  | 강태준 책임 | 서민 책임
1017 | PNG1 | 회전 | R-2158-104 | NON-API PUMP | 3 |  |  |  | 강태준 책임 | 서민 책임
1018 | PNG1 | 회전 | R-2158-112 | BETWEEN BEARING PUMP | 7 |  |  |  | 강태준 책임 | 서민 책임
1019 | PNG1 | 회전 | R-2158-401 | STEAM TURBINE GENERATOR (YOC → SOC) | 2 |  |  |  | 서민 책임 | 강태준 책임
1020 | PNG1 | 회전 | R-2158-402 | GAS TURBINE GENERATOR (YOC → SOC) | 3 |  |  |  | 서민 책임 | 강태준 책임
1021 | PNG1 | 장치 | R-215A-101 | AIR COOLED VACUUM STEAM CONDENSER PACKAGE (YOC → SOC) | 2 |  |  |  | 나광조 책임 | 고팔라크리스낸 매니저
1022 | PNG1 | 장치 | R-215A-201 | SEA WATER INTAKE CHLORINATION UNIT | 1 |  |  |  | 나광조 책임 | 고팔라크리스낸 매니저
1023 | PNG1 | 회전 | R-215A-202 | HIGHLY DEMINERALIZED WATER GENERATION PACKAGE & BLOWDOWN NEUTRALIZATION PACKAGE | 2 |  |  |  | 서민 책임 | 강태준 책임
1024 | PNG1 | 회전 | R-215A-901 | CHEMICAL INJECTION PACKAGE | 3 |  |  |  | 서민 책임 | 강태준 책임
1025 | PNG1 | 장치 | R-215B-201 | HEAT RECOVERY STEAM GENERATOR (HRSG) | 3 |  |  |  | 나광조 책임 | 고팔라크리스낸 매니저
1026 | PNG1 | 장치 | R-215B-401 | DEAERATOR | 1 |  |  |  | 고팔라크리스낸 매니저 | 나광조 책임
1027 | PNG1 | 장치 | R-216G-221 | PIG RECEIVER | TBA |  |  |  | 나광조 책임 | 고팔라크리스낸 매니저
1028 | PNG1 | 배관 | R-216G-353 | PIPELINE VALVES | TBA |  |  |  | 석우경 매니저 | 강태준 책임
1029 | PNG1 | 배관 | R-216G-354 | HYDROCARBON SENSING VALVES (SPILL STOP VALVE) | 6 |  |  |  | 석우경 매니저 | 강태준 책임
1030 | PNG1 | 배관 | R-216Z-902 | PIPELINE PIPES AND FITTINGS | TBA |  |  |  | 장동철 책임 | 엥흐철멍 매니저
1031 | PNG1 | 배관 | R-2174-102 | STEAM CONDITIONING VALVES WITH DUMP TUBE | 4 |  |  |  | 엥흐철멍 매니저 | 장동철 책임
1032 | PNG1 | 배관 | S16G-615 | INSULATION GASKET KITS |  |  |  |  | 장동철 책임 | 엥흐철멍 매니저
1033 | PNG1 | 소방/안전 | S15D-002 | FIRE FIGHTING EQUIPMENT |  |  |  |  | 장동철 책임 | 엥흐철멍 매니저
1034 | PNG1 | 소방/안전 | S15D-003 | LIFE BUOYS |  |  |  |  | 장동철 책임 | 엥흐철멍 매니저
1035 | PNG1 | 계장 | R-2174-204 | ON-OFF VALVES (GATE) |  |  |  |  | 석우경 매니저 | 강태준 책임
1036 | PNG1 | 계장 | R-2174-402 | PILOT ACTUATED BUTTERFLY VALVES |  |  |  |  | 석우경 매니저 | 강태준 책임
1037 | PNG1 | 기타 | R-21C2-101 | CHEMICALS | - |  |  |  | 석우경 매니저 | 강태준 책임

## 출장현황
출장자 | 출장목적 | 프로젝트 | 품목 | 방문업체 | 국가 | 출발일 | 복귀일
석우경 매니저 | FAT | VEQU | ID FAN | TLT TURBO | 중국 | 2025-01-05 | 2025-01-11
최영준 책임 | PIM | STA4 | INCINERATOR - CHAMBER & STACK | MORIMATSU | 중국 | 2025-01-06 | 2025-01-09
이해석 책임 | FAT | SHN1 | AC,DC UPS | GUTOR | 말레이시아 | 2025-01-19 | 2025-01-23
강택기 책임 | PIM | STA4 | ON-OFF VALVE BUTTERFLY | IMI | 사우디 | 2025-01-20 | 2025-01-21
최종현 책임 | PIM | SAC2 | ANALYZER SYSTEM | ABB | 사우디 | 2025-01-20 | 2025-01-24
서민 책임 | PIM | STA4 | CHEMICAL INJECTION PKG | SAUDI WELLS | 사우디 | 2025-01-21 | 2025-01-24
강택기 책임 | PIM | STA4 | ON-OFF VALVE GATE | L&T VALVE | 사우디 | 2025-01-22 | 2025-01-23
정진우 책임 | PIM | STA4 | FLARE PKG - DERRICK STURCTURE | DSD-FERROMETALCO | 이집트 | 2025-01-23 | 2025-01-25
정진우 책임 | PIM | STA4 | FLARE PKG - MPGF | ZEECO MIDDLE EAST | 사우디 | 2025-02-03 | 2025-02-07
최우석 책임 | PIM | STA4 | FLARE PKG - MPGF | ZEECO MIDDLE EAST | 사우디 | 2025-02-03 | 2025-02-07
정진우 책임 | PIM | STA4 | INCINERATOR PKG - BURNER & SKID | ZEECO MIDDLE EAST | 사우디 | 2025-02-03 | 2025-02-07
최우석 책임 | PIM | STA4 | INCINERATOR PKG - BURNER & SKID | ZEECO MIDDLE EAST | 사우디 | 2025-02-03 | 2025-02-07
나광조 책임 | Monitoring | SHN1 | DAMPER (DIVERTER, GUILLOTINE, LOUVER) | 남광엔지니어링 | 대한민국 | 2025-02-06 | 2025-02-06
이해석 책임 | Monitoring | SHN1 | PCS | 요코가와 | 대한민국 | 2025-02-12 | 2025-02-12
윤희수 책임 | FAT | SHN1 | DISTRIBUTION TRANSFORMER | 효성중공업 | 대한민국 | 2025-02-17 | 2025-02-19
나광조 책임 | 업체실사 | SHN1 | DIVERTER DAMPER | TS 넥스젠 | 대한민국 | 2025-02-17 | 2025-02-17
이해석 책임 | FAT | SHN1 | MV SWITCH GEAR | LS ELECTRIC | 대한민국 | 2025-02-17 | 2025-02-18
강태준 책임 | PIM | SHN1 | REGENERATIVE THERMAL OXIDIZER (RTO) PACKAGE | 삼경이엔씨 | 대한민국 | 2025-02-19 | 2025-02-20
최영준 책임 | 업체실사 | STA4 | AIR RELEASE VALVE | PROSAVE | 대한민국 | 2025-03-04 | 2025-03-05
최우석 책임 | 업체실사 | STA4 | AIR RELEASE VALVE | PROSAVE | 대한민국 | 2025-03-04 | 2025-03-05
최영준 책임 | Monitoring | MIP6 | ELECTRIC HEATER | CHROMALOX | 미국 | 2025-03-09 | 2025-03-16
최영준 책임 | Monitoring | SM12 | ELECTRIC HEATER | CHROMALOX | 미국 | 2025-03-09 | 2025-03-16
윤희수 책임 | FAT | STA4 | 230KV POWER TRANSFORMER | HYOSUNG NANTONG | 중국 | 2025-03-17 | 2025-03-20
정진우 책임 | PIM | STA4 | ACTIVATED CARBON FILTER PACKAGE | FILTREX SRL | 이탈리아 | 2025-03-24 | 2025-03-26
최우석 책임 | PIM | STA4 | ACTIVATED CARBON FILTER PACKAGE | FILTREX SRL | 이탈리아 | 2025-03-24 | 2025-03-26
정진우 책임 | Monitoring | STA4 | INCINERATOR PKG - CHAMBER & STACK | MORIMATSU | 중국 | 2025-03-27 | 2025-03-28
최우석 책임 | Monitoring | STA4 | INCINERATOR PKG - CHAMBER & STACK | MORIMATSU | 중국 | 2025-03-27 | 2025-03-28
이해석 책임 | 공장검사 | SHN1 | LV SWGR | 광명전기 | 대한민국 | 2025-04-03 | 2025-04-04
정진우 책임 | PIM | STA4 | ACTIVATED CARBON FILTER PACKAGE | FABTECH INTERNATIONAL | UAE | 2025-04-07 | 2025-04-10
최우석 책임 | PIM | STA4 | ACTIVATED CARBON FILTER PACKAGE | FABTECH INTERNATIONAL | UAE | 2025-04-07 | 2025-04-10
서민 책임 | 공장검사 | STA4 | COOLING WATER PUMP | FLOWSERVE | 이탈리아 | 2025-04-13 | 2025-04-16
윤희수 책임 | FAT | SHN1 | 33KV GIS | 효성중공업 | 대한민국 | 2025-04-13 | 2025-04-18
이해석 책임 | 공장검사 | SHN1 | CRACKING HEATER BURNER | 신아플랜트 | 대한민국 | 2025-04-21 | 2025-04-21
최우석 책임 | 업체실사 | STA4 | C/S SEAMLESS PIP | HONGDA (흥양 SUB-VENDOR) | 중국 | 2025-04-21 | 2025-04-24
장동철 책임 | 교육 | - | VALVE ACADEMY | PK VALVE | 대한민국 | 2025-04-24 | 2025-04-25
이해석 책임 | FAT | SHN1 | LOAD SHEDDING | 코리아데이타 | 대한민국 | 2025-04-28 | 2025-04-29
나광조 책임 | PIM | SHN1 | REGENERATIVE THERMAL OXIDIZER (RTO) PACKAGE | 대상이엔지 | 대한민국 | 2025-05-08 | 2025-05-09
나광조 책임 | Monitoring | SHN1 | STEEL STRUCTURE | KIC | 대한민국 | 2025-05-29 | 2025-05-29
최우석 책임 | 업체실사 | STA4 | PRESSURE VESSEL OF FLARE PKG & INCIERATOR | PERTON (ZEECO SUB-VENDOR) | 사우디 | 2025-05-13 | 2025-05-22
정진우 책임 | PIM | STA4 | INCINERATOR PKG - STANDARD FLANGE | WUXI PAIKE (ZEECO SUB-VENDOR) | 중국 | 2025-05-20 | 2025-05-22
서민 책임 | FAT | STA4 | BLOW DOWN PUMP(MR-006) | DMW(일본) | 일본 | 2025-06-15 | 2025-06-17
이해석 책임 | PIM | SHN1 | CRACKING HEATER BURNER | 신아플랜트 | 대한민국 | 2025-06-10 | 2025-06-10
서민 책임 | 공장검사 | STA4 | AIR COMPRESSOR PKG | 현대마린엔진(HHI 터보기계 SUB-VENDOR) | 대한민국 | 2025-07-15 | 2025-07-15
서민 책임 | 현안미팅 | STA4 | AIR COMPRESSOR PKG | HHI 터보기계 | 대한민국 | 2025-07-29 | 2025-07-29
유요석 팀장 | 업체실사 | STA4 | FBE COATING / KNIFE GATE VALVE & STRAINER | 우성플로텍 | 대한민국 | 2025-07-31 | 2025-08-01
나광조 책임 | FAT | SHN1 | FAN | 서원풍력 | 대한민국 | 2025-07-15 | 2025-07-15
나광조 책임 | FAT | SHN1 | DIVERTER DAMPER | TS 넥스젠(남광엔지니어링 임대공장) | 대한민국 | 2025-07-25 | 2025-07-28
윤희수 책임 | 공장검사 | STA4 | MV CABLE | BAHRA ADVANCED CABLE | 사우디 | 2025-08-08 | 2025-08-12
윤희수 책임 | 공장검사 | STA4 | CRP PANEL | HITACHI ENERGY | 사우디 | 2025-08-13 | 2025-08-16
서민 책임 | 업체실사 | STA4 | SIDE ENTRY MIXER | 하도 | 대한민국 | 2025-08-12 | 2025-08-12
서민 책임 | 공장검사 | STA4 | AIR COMPRESSOR PKG | HHI 터보기계 | 대한민국 | 2025-08-20 | 2025-08-20
서민 책임 | FAT | STA4 | AIR COMPRESSOR PKG | HHI 터보기계 | 대한민국 | 2025-09-01 | 2025-09-02
서민 책임 | 공장검사 | STA4 | AIR COMPRESSOR PKG | HHI 터보기계 | 대한민국 | 2025-09-04 | 2025-09-04
정진우 책임 | 공장검사 | STA4 | FILTER | XINXIANG SHENGDA FILTRATION TECHNIQUE | 중국 | 2025-09-02 | 2025-09-04
서민 책임 | FAT | STA4 | AIR COMPRESSOR PKG | HHI 터보기계 | 대한민국 | 2025-09-08 | 2025-09-09
윤희수 책임 | Monitoring | SHN1 | CERAMIC INSULATOR | 태성쎄라믹 | 대한민국 | 2025-09-24 | 2025-09-24
서민 책임 | 공장검사 | STA4 | AIR COMPRESSOR PKG | HHI 터보기계 | 대한민국 | 2025-09-26 | 2025-09-26
서민 책임 | 공장검사 | STA4 | AIR COMPRESSOR PKG | HHI 터보기계 | 대한민국 | 2025-09-30 | 2025-09-30
서민 책임 | FAT | STA4 | AIR COMPRESSOR PKG | HHI 터보기계 | 대한민국 | 2025-10-13 | 2025-10-14
장동철 책임 | 공장검사 | STA4 | KNIFE GATE VALVE | 동해밸브 | 대한민국 | 2025-10-22 | 2025-10-22
정진우 책임 | 공장검사 | STA4 | AIR DRYER PACKAGE | 세양기업 | 대한민국 | 2025-10-24 | 2025-10-24
서민 책임 | 공장검사 | STA4 | AIR COMPRESSOR PKG | HHI 터보기계 | 대한민국 | 2025-11-06 | 2025-11-06
강태준 책임 | 업체감사 | ALOM | EXHAUST GAS BYPASS SYSTEM | 티에스넥스젠 인천사업장 | 대한민국 | 2025-10-16 | 2025-10-17
강태준 책임 | 업체감사 | ALOM | EXHAUST GAS BYPASS SYSTEM | 티에스넥스젠 인천사업장 | 대한민국 | 2025-10-23 | 2025-10-23
나광조 책임 | PIM | ALOM | AIR COOLED CONDENSER PACKAGE | SPG DRY COOLING BELGUM | 중국 | 2025-11-04 | 2025-11-07
강태준 책임 | 공장검사 | STA4 | WROUGHT FITTING | 태광 | 대한민국 | 2025-11-06 | 2025-11-06
강태준 책임 | 공장검사 | STA4 | FBE COATING / LINING | 세보테크놀로지 | 대한민국 | 2025-11-17 | 2025-11-17
서민 책임 | 공장검사 | STA4 | AIR COMPRESSOR PKG | HHI 터보기계 | 대한민국 | 2025-11-18 | 2025-11-19
서민 책임 | 공장검사 | STA4 | AIR COMPRESSOR PKG | HHI 터보기계 | 대한민국 | 2025-11-21 | 2025-11-21
강태준 책임 | 업체실사 | CSSP | VALVE | DHV VALVE & FOUNDRY | 중국 | 2025-11-24 | 2025-11-24
강태준 책임 | 업체실사 | CSSP | VALVE | SUFA | 중국 | 2025-11-25 | 2025-11-25
강태준 책임 | 업체실사 | CSSP | VALVE | NEWAY VALVE | 중국 | 2025-11-26 | 2025-11-26
강태준 책임 | 업체실사 | CSSP | FBE COATING / LINING | TYHOO | 중국 | 2025-11-27 | 2025-11-27
강태준 책임 | 업체실사 | CSSP | FLANGE / FITTING | ZHONGNAN HEAVY INDUSTRIES | 중국 | 2025-11-28 | 2025-11-28
서민 책임 | 공장검사 | STA4 | AIR COMPRESSOR PKG | HHI 터보기계 | 대한민국 | 2025-11-26 | 2025-11-27
강인묵 책임 | 공장검사 | STA4 | HV SWGR | AL-FANAR | 사우디 | 2025-11-25 | 2025-12-11
강인묵 책임 | 공장검사 | STA4 | MV CABLE | HABARA CABLE | 사우디 | 2025-12-01 | 2025-12-01
강인묵 책임 | 공장검사 | STA4 | ANALYZER | YOGOKAWA | 사우디 | 2025-12-03 | 2025-12-03
윤희수 책임 | 공장검사 | STA4 | ETHAN COMPRESSOR | HITACHI | 일본 | 2025-12-07 | 2025-12-10
강택기 책임 | Monitoring | STA4 | KNIFE GATE VALVE | 동해밸브 | 대한민국 | 2025-12-23 | 2025-12-23
나광조 책임 | Monitoring | MIP6 | ELECTRIC HEATER | CHROMALOX INC. | 미국 | 2026-01-20 | 2026-02-06
강택기 책임 | 공장검사 | STA4 | KNIFE GATE VALVE | 동해밸브 | 대한민국 | 2026-02-10 | 2026-02-10
강인묵 책임 | FAT | STA4 | ECS PANEL | AL-FANAR | 사우디 | 2026-02-23 | 2026-03-09
유요석 팀장 | 업체실사 | STA4 | OIL SKIMMER FOR STORAGE TANK | TTS | 대한민국 | 2026-02-26 | 2026-02-26
강태준 책임 | 업체실사 | STA4 | OIL SKIMMER FOR STORAGE TANK | TTS | 대한민국 | 2026-02-26 | 2026-02-26
강태준 책임 | 업체실사 | CSSP | SPOOL FABRICATION & EXTERNAL/INTERNAL COATING | 웰텍 | 대한민국 | 2026-03-04 | 2026-03-04
유요석 팀장 | 업체실사 | CSSP | SPOOL FABRICATION & EXTERNAL/INTERNAL COATING | 주성이엔지 | 대한민국 | 2026-03-05 | 2026-03-05
강태준 책임 | 업체실사 | CSSP | SPOOL FABRICATION & EXTERNAL/INTERNAL COATING | 주성이엔지 | 대한민국 | 2026-03-05 | 2026-03-05

## 주요현안
Title | Owner | Project_Code | Action_Required
Knife Gate Valve 표면 처리불량 | 임효원 책임 | STA4 | FBE 작업 진행 중
N2 Receiver 폭발 사고 관련 추가 제작 Item 검사 절차 협의 | 장동철 책임 | SM12 | SVL & Inspection Level 협의 중 (SAIR)
Produced Water Booster Pump 관련 Casing 파손 | 서민 책임 | MIP6 | 결함 판독을 위해 현장에서 RT 수행 예정
N2 Generation Package 성능 미달 | 장동철 책임 | IBRU | 제작 및 검사 진행 중
Bypass Valve 현장시험 불합격 | 석우경 매니저 | VEQU
LV Switchgear 내부 부식 발생 | 윤희수 책임 | ALOM | 재제작 진행 중 (5월말 FAT 예상)
원소재 성적서 검토 시스템 | 장동철 책임 | 플랜트구매품질팀 | 경영분석팀 & IT지원팀 협의 중
Punch 관리방법 개선 | 이해석 책임 | 플랜트구매품질팀 | 추진안 준비 중
TPA Workshop | 장동철 책임 | 플랜트구매품질팀 | 금주 중 참석자 확정 및 사전 설문 완료 예정
TPA 실행 비용 분석 및 입찰 예산 적정성 검증 | 강태준 책임 | 플랜트구매품질팀 | 프로젝트별 TPA 청산자료 1차 가공 완료